## Dummy Data
Generating example Agile data
| Exactly | From | Weighting for randomisation | To | Randomised
Start date | 2017-12-04 |  |  |  |  | CumuFlow table
X number of initial stories | 20 |  |  |  |  | Issue | Defining | Ready | In Progress | Review | Done
List skills required and spread across stories | [5 empty] | ID#1 | 2017-12-04 |  | 2017-12-06 | 2017-12-15
Potentially import actual stories & skills | [5 empty] | ID#2 | 2017-12-04 |  | 2017-12-06 |  | 2018-01-02
X people in team | 5 |  |  |  |  | ID#3 | 2017-11-23 | 2017-11-28
List skills possessed by each developer | [5 empty] | ID#4 | 2017-10-17 | 2017-10-17 | 2017-12-04 |  | 2018-01-02
Getting a story to "Ready" takes X hours |  | 4 | -¦----- | 16 | Per story | ID#5 | 2017-11-15
Each story is "In Progress" for X hours |  | 8 | ---¦--- | 80 | Per story | … | … | … | … | … | …
Each story is in "Review" for X hours |  | 2 | -¦----- | 8 | Per story | --> predicted end date
X% chance of a Blocker introduced for a story |  | 10 | ---¦--- | 30 | Per story, per day
Blockers add X days to story completion time |  | 1 | -----¦- | 4 | Per blocker | * Review Cumulative Flow diagrams at different stages in project
X% chance of new story being added |  | 10 | ---¦--- | 30 | Per day | * Review frequency bins for Completion Time
X% chance of bug(s) found for story |  | 20 | ---¦--- | 50 | Per story | * Tweak predictive graphs to get more accurate?
Bug(s) take X hours to resolve |  | 16 | ----¦-- | 32 | Per bug | * Measure the actual parameter metrics as project progresses to re-run simulation?
X% chance of each team member being unavailable |  | 10 | ---¦--- | 20 | Per individual, per day
Unavailability lasts for X days |  | 1 | ---¦--- | 4 | Per unavailability
Capacity (hours) of each developer per day |  | 2 | --¦---- | 6 | Per individual, per day | DevTime table
System testing lasts X days | % of Story count |  |  |  |  | Date | Dev#1 | Dev#2 | Dev#3 | Dev#4 | Dev#5
Rework from system testing adds X stories |  | 2 | ---¦--- | 10 | Per project | 2017-12-04 | 2 | 6 | 4 | 4 | 5
Rework from user acceptance adds X stories |  | 0 | -¦----- | 3 | Per project | 2017-12-05 | 6 | 6 | 4 | 5 | 4
Bank holidays + Developer holidays | From JSON file |  |  |  |  | 2017-12-06 | 4 | 4 | 4 | 0 | 4
[6 empty] | 2017-12-07 | 4 | 5 | 4 | 0 | 2
[6 empty] | 2017-12-08 | 6 | 3 | 4 | 0 | 2
Simulation process | [5 empty] | 2017-12-09 | 5 | 3 | 4 | 2 | 2
Populate initial CumuFlow table of issues and randomised hours per phase | [5 empty] | … | … | … | … | … | …
Populate initial DevTime table (inc Absences: 0hrs)
Main loop: Repeat until no more stories incomplete in CumuFlow table:
Increment date | [5 empty] | Input min/max/best guess for each metric
For each story | [5 empty] | Run simulation for best case/worst case/best guess
Calculate whether Blocker happens | [5 empty] | --> prediction of end date(s) with no estimation
Add randomised Blocker time to Story time | [5 empty] | Can update parameters with actual project metrics so far and re-run simulation as project progresses
Repeat until no more dev time available | [5 empty] | After a set period, calculate estimate completion date regularly during simulation and compare at end
Decrement available Story Phases by amount of dev hours available | [5 empty] | Use extrapolation of Done line and Frequency Bins to calculate estimate
If Story Phase complete add Date to CumuFlow table for that story | [5 empty] | --> Show if estimates are accurate and what factors affect them?
If Story Completed then calculate Bugs found
For each bug: | [5 empty] | Estimation of completion date via Done Rate Extrapolation or Frequency Bins calculation do not take account of new stories created, bugs found etc
Randomise time required for each bug
Add Bug as issue in CumuFlow table | [5 empty] | Assign skills to Stories and Developers
Add randomised days for System Testing (% of total stories) | [5 empty] | --> Run simulations before and after adding new resource with specific skills
Randomise new stories for from System Testing - add to CumuFlow table
Randomise new stories from User Acceptance - add to CumuFlow table
Perform main loop until no more Stories incomplete in CumuFlow table
End --> simulated end date, cumulative flow graph, frequency bins of completion time
Can now view CumuFlow graph half way through project and try to predict simulated end date

## Dummy CumuFlow (50 days)
Date | CountGrooming | CountWIP | CountReview | CountDone | DoneTrend
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 8 | 6 | 0 | 0 | 4 | 0

## Dummy CumuFlow (complete)
Date | CountGrooming | CountWIP | CountReview | CountDone
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-21 | 10 | 2 | 0 | 8 | 1 | 0 | 0 | 0 | 0
2018-01-22 | 10 | 0 | 1 | 9 | 3 | 0 | 0 | 0 | 0
2018-01-23 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-24 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-25 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-26 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-27 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-28 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 4 | 3
2018-01-29 | 8 | 0 | 1 | 11 | 1 | 0 | 0 | 0 | 0
2018-01-30 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-01-31 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-01 | 7 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-02 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-03 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-04 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-05 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-06 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-07 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-08 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-09 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-10 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-11 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-12 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-13 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-14 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-15 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-16 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-17 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-18 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-19 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-20 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-21 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-22 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-23 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 4
2018-02-24 | 2 | 4 | 0 | 14 | 0 | 0 | 0 | 0 | 0
2018-02-25 | 2 | 3 | 1 | 14 | 5 | 0 | 0 | 0 | 0
2018-02-26 | 2 | 0 | 1 | 17 | 4 | 2 | 0 | 0 | 0
2018-02-27 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-02-28 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-02 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-03 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-04 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-05 | 0 | 2 | 0 | 18 | 0 | 2 | 0 | 0 | 2
2018-03-06 | 0 | 0 | 0 | 20 | 0 | 0 | 4 | 4 | 3

## LinearEstimates
Date | StartError | Last5Error | Grooming | WIP | Review | Done | LinearFromStart | LinearFromLast5
2017-12-01 |  |  | 15 | 0 | 0 | 0
2017-12-04 |  |  | 15 | 0 | 0 | 0
2017-12-05 |  |  | 15 | 0 | 0 | 0
2017-12-06 |  |  | 15 | 0 | 0 | 0
2017-12-07 |  |  | 15 | 0 | 0 | 0
2017-12-08 |  |  | 15 | 0 | 0 | 0
2017-12-11 |  |  | 15 | 0 | 0 | 0
2017-12-12 |  |  | 15 | 0 | 0 | 0
2017-12-13 |  |  | 15 | 0 | 0 | 0
2017-12-14 |  |  | 15 | 0 | 0 | 0
2017-12-15 |  |  | 14 | 1 | 0 | 0
2017-12-18 |  |  | 14 | 1 | 0 | 0
2017-12-19 |  |  | 14 | 1 | 0 | 0
2017-12-20 |  |  | 14 | 1 | 0 | 0
2017-12-21 |  |  | 14 | 1 | 0 | 0
2017-12-22 |  |  | 13 | 1 | 1 | 0
2017-12-25 | 223 |  | 14 | 1 | 0 | 1 | 2018-12-20
2017-12-26 | 239 |  | 14 | 1 | 0 | 1 | 2019-01-05
2017-12-27 | 255 |  | 14 | 1 | 0 | 1 | 2019-01-21
2017-12-28 | 271 |  | 14 | 1 | 0 | 1 | 2019-02-06
2017-12-29 | 287 |  | 14 | 1 | 0 | 1 | 2019-02-22
2018-01-01 | 335 |  | 14 | 1 | 0 | 1 | 2019-04-11
2018-01-02 | 95 |  | 14 | 0 | 0 | 2 | 2018-08-14
2018-01-03 | 96 |  | 14 | 0 | 0 | 2 | 2018-08-15
2018-01-04 | 111 |  | 13 | 1 | 0 | 2 | 2018-08-30
2018-01-05 | 112 |  | 13 | 1 | 0 | 2 | 2018-08-31
2018-01-08 | 143 |  | 13 | 1 | 0 | 2 | 2018-10-01
2018-01-09 | 144 |  | 12 | 1 | 1 | 2 | 2018-10-02
2018-01-10 | 48 |  | 12 | 1 | 0 | 3 | 2018-06-28
2018-01-11 | 49 |  | 12 | 1 | 0 | 3 | 2018-06-29
2018-01-12 | 63 |  | 12 | 1 | 0 | 3 | 2018-07-13
2018-01-15 | 79 |  | 12 | 1 | 0 | 3 | 2018-07-29
2018-01-16 | 80 |  | 12 | 0 | 1 | 3 | 2018-07-30
2018-01-17 | 18 |  | 10 | 2 | 0 | 4 | 2018-05-29
2018-01-18 | 31 |  | 10 | 2 | 0 | 4 | 2018-06-11
2018-01-19 | 32 |  | 10 | 2 | 0 | 4 | 2018-06-12
2018-01-22 | 47 |  | 10 | 2 | 0 | 4 | 2018-06-27
2018-01-23 | 48 |  | 10 | 2 | 0 | 4 | 2018-06-28
2018-01-24 | 49 |  | 10 | 1 | 1 | 4 | 2018-06-29
2018-01-25 | 26 |  | 11 | 0 | 1 | 5 | 2018-06-06
2018-01-26 | -6 | -50 | 11 | 0 | 0 | 6 | 2018-05-05 | 2018-03-22
2018-01-29 | -3 | -47 | 11 | 0 | 0 | 6 | 2018-05-08 | 2018-03-25
2018-01-30 | 9 | -46 | 11 | 0 | 0 | 6 | 2018-05-20 | 2018-03-26
2018-01-31 | 10 | -34 | 9 | 2 | 0 | 6 | 2018-05-21 | 2018-04-07
2018-02-01 | 11 | -33 | 9 | 2 | 0 | 6 | 2018-05-22 | 2018-04-08
2018-02-02 | 12 | -32 | 9 | 2 | 0 | 6 | 2018-05-23 | 2018-04-09
2018-02-05 | 26 | -18 | 9 | 2 | 0 | 6 | 2018-06-06 | 2018-04-23
2018-02-06 | 27 | -17 | 9 | 0 | 2 | 6 | 2018-06-07 | 2018-04-24
2018-02-07 | -13 | -53 | 10 | 0 | 0 | 8 | 2018-04-28 | 2018-03-19
2018-02-08 | -12 | -52 | 8 | 2 | 0 | 8 | 2018-04-29 | 2018-03-20
2018-02-09 | -11 | -51 | 8 | 2 | 0 | 8 | 2018-04-30 | 2018-03-21
2018-02-12 | 2 | -38 | 8 | 2 | 0 | 8 | 2018-05-13 | 2018-04-03
2018-02-13 | 3 | -37 | 8 | 2 | 0 | 8 | 2018-05-14 | 2018-04-04
2018-02-14 | 4 | -36 | 8 | 2 | 0 | 8 | 2018-05-15 | 2018-04-05
2018-02-15 | 5 | -25 | 8 | 2 | 0 | 8 | 2018-05-16 | 2018-04-16
2018-02-16 | 6 | -24 | 8 | 1 | 1 | 8 | 2018-05-17 | 2018-04-17
2018-02-19 | -1 | -31 | 10 | 0 | 0 | 10 | 2018-05-10 | 2018-04-10
2018-02-20 | 0 | -30 | 9 | 1 | 0 | 10 | 2018-05-11 | 2018-04-11
2018-02-21 | 1 | -29 | 9 | 1 | 0 | 10 | 2018-05-12 | 2018-04-12
2018-02-22 | 2 | -28 | 9 | 1 | 0 | 10 | 2018-05-13 | 2018-04-13
2018-02-23 | 3 | -27 | 9 | 1 | 0 | 10 | 2018-05-14 | 2018-04-14
2018-02-26 | -11 | -38 | 7 | 2 | 0 | 11 | 2018-04-30 | 2018-04-03
2018-02-27 | -1 | -37 | 7 | 2 | 0 | 11 | 2018-05-10 | 2018-04-04
2018-02-28 | 0 | -36 | 7 | 2 | 0 | 11 | 2018-05-11 | 2018-04-05
2018-03-01 | 1 | -35 | 7 | 2 | 0 | 11 | 2018-05-12 | 2018-04-06
2018-03-02 | 2 | -34 | 7 | 2 | 0 | 11 | 2018-05-13 | 2018-04-07
2018-03-05 | 5 | -22 | 7 | 2 | 0 | 11 | 2018-05-16 | 2018-04-19
2018-03-06 | 6 | -21 | 7 | 1 | 1 | 11 | 2018-05-17 | 2018-04-20
2018-03-07 | -1 | -33 | 7 | 0 | 1 | 12 | 2018-05-10 | 2018-04-08
2018-03-08 | 0 | -24 | 7 | 0 | 1 | 12 | 2018-05-11 | 2018-04-17
2018-03-09 | -7 | -31 | 8 | 0 | 0 | 13 | 2018-05-04 | 2018-04-10
2018-03-12 | -4 | -28 | 6 | 2 | 0 | 13 | 2018-05-07 | 2018-04-13
2018-03-13 | -3 | -19 | 6 | 2 | 0 | 13 | 2018-05-08 | 2018-04-22
2018-03-14 | -2 | -18 | 6 | 2 | 0 | 13 | 2018-05-09 | 2018-04-23
2018-03-15 | 7 | -17 | 6 | 2 | 0 | 13 | 2018-05-18 | 2018-04-24
2018-03-16 | 8 | -16 | 6 | 2 | 0 | 13 | 2018-05-19 | 2018-04-25
2018-03-19 | 11 | -5 | 6 | 2 | 0 | 13 | 2018-05-22 | 2018-05-06
2018-03-20 | 12 | -4 | 6 | 2 | 0 | 13 | 2018-05-23 | 2018-05-07
2018-03-21 | 13 | -3 | 6 | 2 | 0 | 13 | 2018-05-24 | 2018-05-08
2018-03-22 | 14 | -2 | 6 | 1 | 1 | 13 | 2018-05-25 | 2018-05-09
2018-03-23 | -7 | -19 | 2 | 4 | 0 | 15 | 2018-05-04 | 2018-04-22
2018-03-26 | -4 | -10 | 2 | 4 | 0 | 15 | 2018-05-07 | 2018-05-01
2018-03-27 | -3 | -9 | 2 | 4 | 0 | 15 | 2018-05-08 | 2018-05-02
2018-03-28 | -2 | -8 | 2 | 4 | 0 | 15 | 2018-05-09 | 2018-05-03
2018-03-29 | -1 | -7 | 2 | 4 | 0 | 15 | 2018-05-10 | 2018-05-04
2018-03-30 | 0 | 0 | 2 | 4 | 0 | 15 | 2018-05-11 | 2018-05-11
2018-04-02 | 9 | 3 | 2 | 4 | 0 | 15 | 2018-05-20 | 2018-05-14
2018-04-03 | 10 | 4 | 2 | 4 | 0 | 15 | 2018-05-21 | 2018-05-15
2018-04-04 | -9 | -17 | 1 | 1 | 2 | 17 | 2018-05-02 | 2018-04-24
2018-04-05 | -24 | -32 | 1 | 1 | 0 | 19 | 2018-04-17 | 2018-04-09
2018-04-06 | -23 | -31 | 1 | 1 | 0 | 19 | 2018-04-18 | 2018-04-10
2018-04-09 | -20 | -26 | 1 | 1 | 0 | 19 | 2018-04-21 | 2018-04-15
2018-04-10 | -19 | -25 | 1 | 1 | 0 | 19 | 2018-04-22 | 2018-04-16
2018-04-11 | -18 | -24 | 1 | 1 | 0 | 19 | 2018-04-23 | 2018-04-17
2018-04-12 | -17 | -27 | 1 | 1 | 0 | 20 | 2018-04-24 | 2018-04-14
2018-04-13 | -16 | -24 | 1 | 1 | 0 | 20 | 2018-04-25 | 2018-04-17
2018-04-16 | -13 | -21 | 1 | 1 | 0 | 20 | 2018-04-28 | 2018-04-20
2018-04-17 | -12 | -20 | 1 | 1 | 0 | 20 | 2018-04-29 | 2018-04-21
2018-04-18 | -11 | -17 | 1 | 1 | 0 | 20 | 2018-04-30 | 2018-04-24
2018-04-19 | -10 | -16 | 1 | 1 | 0 | 20 | 2018-05-01 | 2018-04-25
2018-04-20 | -7 | -15 | 1 | 1 | 0 | 20 | 2018-05-04 | 2018-04-26
2018-04-23 | -12 | -15 | 1 | 0 | 0 | 21 | 2018-04-29 | 2018-04-26
2018-04-24 | -11 | -14 | 0 | 1 | 0 | 21 | 2018-04-30 | 2018-04-27
2018-04-25 | -10 | -13 | 0 | 1 | 0 | 21 | 2018-05-01 | 2018-04-28
2018-04-26 | -9 | -12 | 0 | 1 | 0 | 21 | 2018-05-02 | 2018-04-29
2018-04-27 | -7 | -10 | 0 | 0 | 1 | 21 | 2018-05-04 | 2018-05-01
2018-04-30 | -4 | -7 | 0 | 0 | 1 | 21 | 2018-05-07 | 2018-05-04
2018-05-01 | -4 | -5 | 1 | 0 | 0 | 22 | 2018-05-07 | 2018-05-06
2018-05-02 | -3 | -4 | 1 | 0 | 0 | 22 | 2018-05-08 | 2018-05-07
2018-05-03 | -2 | -3 | 0 | 1 | 0 | 22 | 2018-05-09 | 2018-05-08
2018-05-04 | 0 | -1 | 0 | 1 | 0 | 22 | 2018-05-11 | 2018-05-10
2018-05-07 | 2 | 1 | 1 | 0 | 0 | 23 | 2018-05-13 | 2018-05-12
2018-05-08 | 3 | 2 | 1 | 0 | 0 | 23 | 2018-05-14 | 2018-05-13
2018-05-09 | 4 | 3 | 0 | 1 | 0 | 23 | 2018-05-15 | 2018-05-14
2018-05-10 | 5 | 5 | 0 | 1 | 0 | 23 | 2018-05-16 | 2018-05-16
2018-05-11 | 0 | 0 | 0 | 0 | 0 | 24 | 2018-05-11 | 2018-05-11

## MonteCarlo
Monte Carlo 1000 run |  |  |  | Parameters
Completion Date | Row Labels | Frequency | 2017-12-01 | Start Date
2018-04-17 | 2018-02-27 | 1 | 15 | User Stories
2018-04-20 | 2018-03-01 | 1 | 5 | Developers
2018-03-27 | 2018-03-02 | 3 | 4-16hrs | Grooming Phase
2018-03-06 | 2018-03-06 | 4 | 8-80hrs | In Progress Phase | =16-104hrs
2018-03-14 | 2018-03-07 | 2 | 2-8hrs | Review Phase
2018-03-28 | 2018-03-09 | 1 | 30% | Chance of bug raised on story
2018-06-01 | 2018-03-12 | 3 | 8-32hrs | Work required to resolve bug
2018-05-11 | 2018-03-13 | 7 | 20% | Chance of developer being absent
2018-03-28 | 2018-03-14 | 3 | 1-4days | Length of developer absence
2018-04-26 | 2018-03-15 | 3 | 2-6hrs | Developer capacity per day
2018-04-20 | 2018-03-16 | 9 | to do | Chance of new stories raised per week
2018-04-30 | 2018-03-19 | 3 | to do | Degree of dependency
2018-05-08 | 2018-03-20 | 4 | to do | Breadth of dependency
2018-04-16 | 2018-03-21 | 11 | to do | Chance of being blocked on a story
2018-03-22 | 2018-03-22 | 9 | to do | Length of block on story
2018-04-18 | 2018-03-23 | 10
2018-03-22 | 2018-03-26 | 13
2018-05-22 | 2018-03-27 | 18
2018-04-24 | 2018-03-28 | 18
2018-03-23 | 2018-03-29 | 13
2018-04-20 | 2018-03-30 | 15
2018-05-21 | 2018-04-02 | 11
2018-03-23 | 2018-04-03 | 19
2018-04-05 | 2018-04-04 | 13
2018-04-27 | 2018-04-05 | 18
2018-03-15 | 2018-04-06 | 23
2018-05-16 | 2018-04-09 | 13
2018-04-19 | 2018-04-10 | 25
2018-05-16 | 2018-04-11 | 30
2018-05-14 | 2018-04-12 | 16
2018-04-26 | 2018-04-13 | 14
2018-04-11 | 2018-04-16 | 23
2018-04-17 | 2018-04-17 | 15
2018-04-19 | 2018-04-18 | 19
2018-04-23 | 2018-04-19 | 27
2018-04-02 | 2018-04-20 | 25
2018-04-19 | 2018-04-23 | 20
2018-06-06 | 2018-04-24 | 20
2018-04-20 | 2018-04-25 | 26
2018-05-10 | 2018-04-26 | 29
2018-03-30 | 2018-04-27 | 14
2018-04-30 | 2018-04-30 | 15
2018-04-10 | 2018-05-01 | 13
2018-05-16 | 2018-05-02 | 17
2018-03-30 | 2018-05-03 | 20
2018-05-14 | 2018-05-04 | 16
2018-04-25 | 2018-05-07 | 12
2018-04-19 | 2018-05-08 | 16
2018-03-28 | 2018-05-09 | 10
2018-05-28 | 2018-05-10 | 17
2018-04-17 | 2018-05-11 | 15
2018-04-13 | 2018-05-14 | 16
2018-04-20 | 2018-05-15 | 20
2018-04-24 | 2018-05-16 | 18
2018-05-25 | 2018-05-17 | 9
2018-05-15 | 2018-05-18 | 15
2018-04-25 | 2018-05-21 | 14
2018-06-06 | 2018-05-22 | 14
2018-04-24 | 2018-05-23 | 9
2018-03-21 | 2018-05-24 | 15
2018-04-26 | 2018-05-25 | 11
2018-05-07 | 2018-05-28 | 12
2018-04-23 | 2018-05-29 | 14
2018-04-16 | 2018-05-30 | 9
2018-05-18 | 2018-05-31 | 10
2018-04-25 | 2018-06-01 | 6
2018-05-29 | 2018-06-04 | 6
2018-05-16 | 2018-06-05 | 5
2018-04-27 | 2018-06-06 | 12
2018-04-11 | 2018-06-07 | 8
2018-04-18 | 2018-06-08 | 7
2018-05-28 | 2018-06-11 | 3
2018-06-06 | 2018-06-12 | 2
2018-05-18 | 2018-06-13 | 3
2018-05-29 | 2018-06-14 | 9
2018-04-12 | 2018-06-15 | 4
2018-04-04 | 2018-06-18 | 2
2018-04-18 | 2018-06-19 | 4
2018-05-09 | 2018-06-20 | 7
2018-05-16 | 2018-06-21 | 2
2018-04-10 | 2018-06-22 | 2
2018-04-25 | 2018-06-25 | 3
2018-06-06 | 2018-06-26 | 4
2018-04-30 | 2018-06-27 | 1
2018-05-09 | 2018-06-28 | 2
2018-06-26 | 2018-07-02 | 4
2018-05-14 | 2018-07-03 | 1
2018-03-22 | 2018-07-04 | 1
2018-05-15 | 2018-07-05 | 2
2018-04-11 | 2018-07-09 | 2
2018-05-25 | 2018-07-11 | 1
2018-05-23 | 2018-07-18 | 2
2018-03-21 | 2018-07-19 | 1
2018-07-04 | 2018-07-24 | 1
2018-05-29 | 2018-07-27 | 1
2018-05-25 | 2018-08-02 | 1
2018-06-06 | 2018-08-07 | 1
2018-03-26 | 2018-08-09 | 1
2018-05-04 | 2018-08-14 | 1
2018-06-08 | Grand Total | 1000
2018-04-20
2018-03-06
2018-04-10
2018-04-10
2018-06-15
2018-04-23
2018-03-22
2018-03-01
2018-04-25
2018-07-09
2018-05-29
2018-04-09
2018-06-22
2018-04-26
2018-06-15
2018-04-18
2018-04-23
2018-04-25
2018-05-03
2018-04-13
2018-03-27
2018-04-26
2018-03-28
2018-03-21
2018-05-09
2018-04-26
2018-04-24
2018-03-21
2018-04-13
2018-04-09
2018-04-12
2018-04-05
2018-05-31
2018-04-11
2018-05-29
2018-05-14
2018-06-28
2018-03-27
2018-05-11
2018-06-05
2018-05-18
2018-04-19
2018-03-30
2018-05-23
2018-06-01
2018-04-12
2018-05-08
2018-03-29
2018-03-19
2018-05-31
2018-03-26
2018-04-05
2018-04-11
2018-03-29
2018-05-16
2018-03-27
2018-05-29
2018-05-10
2018-04-30
2018-04-19
2018-05-09
2018-04-06
2018-05-18
2018-05-10
2018-04-20
2018-04-02
2018-06-04
2018-05-03
2018-04-05
2018-05-16
2018-05-02
2018-05-10
2018-06-07
2018-05-15
2018-05-18
2018-03-28
2018-04-12
2018-04-25
2018-04-09
2018-05-08
2018-06-06
2018-04-24
2018-03-13
2018-05-31
2018-05-16
2018-04-12
2018-04-04
2018-05-17
2018-06-06
2018-05-15
2018-04-16
2018-08-09
2018-04-11
2018-04-04
2018-04-12
2018-04-19
2018-05-16
2018-05-18
2018-05-24
2018-07-02
2018-04-06
2018-04-09
2018-04-12
2018-04-20
2018-04-03
2018-04-03
2018-03-21
2018-03-26
2018-05-22
2018-04-26
2018-04-16
2018-04-06
2018-03-30
2018-04-18
2018-04-11
2018-05-08
2018-04-05
2018-05-24
2018-05-24
2018-04-11
2018-04-04
2018-04-20
2018-03-30
2018-05-22
2018-04-03
2018-04-26
2018-03-29
2018-05-07
2018-06-05
2018-05-24
2018-04-02
2018-05-22
2018-03-12
2018-03-13
2018-06-04
2018-05-25
2018-05-28
2018-05-01
2018-05-31
2018-06-20
2018-05-15
2018-05-28
2018-03-28
2018-04-09
2018-04-20
2018-07-09
2018-05-17
2018-03-27
2018-04-04
2018-05-10
2018-04-23
2018-05-24
2018-03-27
2018-06-06
2018-04-06
2018-04-06
2018-04-16
2018-03-22
2018-04-18
2018-03-22
2018-04-25
2018-03-23
2018-04-20
2018-03-28
2018-04-25
2018-04-26
2018-03-13
2018-05-14
2018-07-05
2018-04-03
2018-05-14
2018-06-14
2018-04-27
2018-03-29
2018-03-12
2018-05-02
2018-04-10
2018-04-10
2018-04-10
2018-04-16
2018-08-02
2018-04-17
2018-03-28
2018-03-27
2018-04-17
2018-04-25
2018-04-10
2018-05-03
2018-05-18
2018-05-08
2018-04-16
2018-03-27
2018-04-25
2018-05-01
2018-05-01
2018-05-09
2018-06-14
2018-05-10
2018-05-09
2018-03-28
2018-05-15
2018-04-26
2018-06-20
2018-04-06
2018-05-28
2018-04-30
2018-03-28
2018-05-16
2018-04-19
2018-05-30
2018-04-13
2018-04-12
2018-05-04
2018-04-16
2018-05-02
2018-05-21
2018-05-31
2018-05-03
2018-04-19
2018-06-22
2018-06-20
2018-04-06
2018-06-01
2018-05-14
2018-05-18
2018-04-17
2018-05-02
2018-03-28
2018-05-10
2018-05-22
2018-05-02
2018-03-27
2018-04-06
2018-05-01
2018-04-04
2018-04-23
2018-04-24
2018-05-23
2018-06-06
2018-05-11
2018-03-26
2018-05-01
2018-04-13
2018-03-26
2018-04-25
2018-04-24
2018-03-21
2018-04-19
2018-05-24
2018-08-07
2018-05-31
2018-03-27
2018-04-30
2018-05-04
2018-06-18
2018-04-16
2018-04-13
2018-03-14
2018-03-26
2018-03-16
2018-04-03
2018-05-09
2018-03-21
2018-04-16
2018-04-03
2018-04-19
2018-04-04
2018-05-08
2018-06-12
2018-03-16
2018-05-29
2018-05-31
2018-05-15
2018-03-12
2018-04-16
2018-03-30
2018-04-03
2018-04-13
2018-04-20
2018-05-04
2018-05-24
2018-04-03
2018-05-07
2018-04-02
2018-04-20
2018-04-23
2018-04-23
2018-05-02
2018-04-04
2018-03-16
2018-05-18
2018-05-24
2018-05-16
2018-04-16
2018-05-02
2018-05-28
2018-04-06
2018-03-20
2018-04-03
2018-06-08
2018-05-15
2018-06-04
2018-05-03
2018-05-04
2018-04-16
2018-03-20
2018-03-20
2018-05-25
2018-03-27
2018-04-19
2018-05-28
2018-05-04
2018-04-26
2018-04-10
2018-06-21
2018-05-22
2018-04-16
2018-05-22
2018-04-25
2018-05-17
2018-04-18
2018-05-10
2018-04-11
2018-05-22
2018-05-11
2018-05-15
2018-04-25
2018-05-07
2018-05-28
2018-04-26
2018-05-24
2018-04-26
2018-05-01
2018-03-27
2018-04-27
2018-05-10
2018-05-22
2018-03-21
2018-04-18
2018-04-30
2018-04-10
2018-05-22
2018-05-25
2018-04-24
2018-03-13
2018-06-08
2018-06-19
2018-05-08
2018-04-30
2018-05-24
2018-06-20
2018-05-11
2018-04-30
2018-06-06
2018-04-11
2018-05-23
2018-03-30
2018-05-02
2018-07-05
2018-04-27
2018-04-13
2018-04-04
2018-04-06
2018-06-05
2018-04-17
2018-04-24
2018-03-28
2018-05-28
2018-04-11
2018-05-03
2018-03-28
2018-04-19
2018-05-04
2018-04-06
2018-04-05
2018-04-05
2018-04-16
2018-04-11
2018-06-08
2018-03-28
2018-06-07
2018-05-30
2018-04-24
2018-03-13
2018-05-28
2018-05-17
2018-06-14
2018-03-13
2018-04-16
2018-04-17
2018-04-10
2018-06-11
2018-04-11
2018-05-07
2018-03-21
2018-05-14
2018-06-19
2018-04-04
2018-05-21
2018-06-14
2018-04-05
2018-08-14
2018-04-06
2018-04-24
2018-04-23
2018-04-11
2018-04-25
2018-04-09
2018-04-05
2018-05-17
2018-05-07
2018-05-14
2018-05-15
2018-05-07
2018-03-23
2018-05-15
2018-04-04
2018-05-10
2018-04-27
2018-05-21
2018-04-18
2018-06-25
2018-05-08
2018-03-02
2018-05-24
2018-03-16
2018-04-25
2018-05-18
2018-05-15
2018-05-14
2018-04-12
2018-06-26
2018-04-18
2018-04-06
2018-03-26
2018-05-15
2018-05-30
2018-04-06
2018-05-03
2018-04-24
2018-03-30
2018-05-24
2018-04-02
2018-04-19
2018-03-28
2018-04-23
2018-04-20
2018-05-02
2018-04-02
2018-05-21
2018-04-05
2018-05-11
2018-06-15
2018-04-23
2018-07-24
2018-05-21
2018-04-27
2018-05-30
2018-05-04
2018-04-26
2018-04-03
2018-03-07
2018-05-04
2018-03-30
2018-05-03
2018-06-18
2018-03-19
2018-04-06
2018-04-25
2018-04-24
2018-04-26
2018-03-29
2018-04-11
2018-04-30
2018-06-08
2018-05-01
2018-04-23
2018-05-15
2018-04-30
2018-06-07
2018-05-03
2018-04-10
2018-05-29
2018-04-09
2018-05-03
2018-04-19
2018-06-14
2018-05-03
2018-04-06
2018-03-29
2018-03-22
2018-04-18
2018-04-12
2018-04-20
2018-05-29
2018-04-06
2018-04-23
2018-04-20
2018-04-10
2018-04-30
2018-04-30
2018-05-03
2018-04-03
2018-05-01
2018-04-16
2018-04-26
2018-05-22
2018-07-02
2018-05-18
2018-04-18
2018-04-23
2018-04-10
2018-06-19
2018-05-17
2018-04-30
2018-04-26
2018-04-18
2018-03-29
2018-04-26
2018-04-06
2018-04-17
2018-04-06
2018-05-14
2018-03-06
2018-07-02
2018-04-18
2018-07-02
2018-05-03
2018-03-14
2018-04-27
2018-06-04
2018-04-10
2018-04-12
2018-03-27
2018-07-27
2018-05-17
2018-05-14
2018-04-11
2018-05-18
2018-05-11
2018-05-30
2018-05-01
2018-07-11
2018-04-24
2018-06-12
2018-03-06
2018-04-10
2018-04-12
2018-04-11
2018-04-06
2018-04-10
2018-04-10
2018-03-16
2018-05-25
2018-04-19
2018-04-12
2018-05-07
2018-05-22
2018-03-26
2018-05-09
2018-05-29
2018-04-17
2018-04-03
2018-04-20
2018-03-30
2018-03-09
2018-05-09
2018-05-28
2018-03-15
2018-05-31
2018-04-25
2018-06-08
2018-03-27
2018-04-25
2018-04-20
2018-04-25
2018-05-29
2018-05-16
2018-05-02
2018-05-02
2018-04-18
2018-04-27
2018-04-19
2018-05-04
2018-05-14
2018-03-27
2018-05-21
2018-04-13
2018-04-19
2018-04-20
2018-03-22
2018-06-07
2018-04-12
2018-04-19
2018-04-10
2018-06-20
2018-03-30
2018-04-13
2018-05-21
2018-03-13
2018-05-01
2018-04-03
2018-04-23
2018-05-08
2018-04-19
2018-06-07
2018-03-26
2018-04-11
2018-04-26
2018-03-26
2018-05-31
2018-06-04
2018-05-11
2018-05-15
2018-04-02
2018-05-08
2018-04-09
2018-03-30
2018-04-10
2018-04-25
2018-05-10
2018-03-20
2018-04-26
2018-04-11
2018-06-07
2018-06-13
2018-05-03
2018-03-26
2018-04-05
2018-04-03
2018-06-06
2018-04-16
2018-03-16
2018-04-03
2018-04-09
2018-03-28
2018-04-09
2018-05-04
2018-05-08
2018-04-11
2018-04-23
2018-04-05
2018-04-27
2018-04-20
2018-04-03
2018-04-12
2018-03-07
2018-04-11
2018-04-11
2018-06-13
2018-04-20
2018-05-29
2018-05-25
2018-05-21
2018-05-18
2018-04-25
2018-05-18
2018-06-14
2018-06-28
2018-05-11
2018-03-02
2018-06-13
2018-04-23
2018-06-11
2018-03-29
2018-06-05
2018-03-27
2018-04-11
2018-05-10
2018-06-01
2018-06-07
2018-05-29
2018-04-24
2018-04-20
2018-04-19
2018-05-03
2018-04-06
2018-06-15
2018-05-29
2018-03-27
2018-05-02
2018-05-11
2018-05-17
2018-05-02
2018-06-26
2018-05-11
2018-06-14
2018-04-26
2018-07-18
2018-05-08
2018-04-13
2018-04-02
2018-04-25
2018-05-03
2018-04-05
2018-05-24
2018-04-04
2018-03-30
2018-05-07
2018-05-21
2018-05-10
2018-04-10
2018-03-22
2018-03-26
2018-05-08
2018-05-21
2018-04-11
2018-03-29
2018-04-17
2018-04-11
2018-04-27
2018-03-16
2018-04-27
2018-06-14
2018-05-22
2018-04-16
2018-05-30
2018-05-30
2018-05-23
2018-05-07
2018-04-19
2018-04-20
2018-05-04
2018-04-18
2018-04-11
2018-05-14
2018-04-18
2018-04-26
2018-04-26
2018-07-03
2018-04-03
2018-05-10
2018-04-17
2018-05-07
2018-03-21
2018-04-23
2018-05-09
2018-04-12
2018-05-02
2018-04-24
2018-05-15
2018-05-10
2018-05-15
2018-05-07
2018-06-19
2018-03-29
2018-04-10
2018-04-03
2018-04-05
2018-06-20
2018-05-14
2018-04-25
2018-03-23
2018-05-16
2018-05-23
2018-04-10
2018-04-19
2018-05-03
2018-03-26
2018-04-18
2018-04-10
2018-05-24
2018-05-04
2018-05-30
2018-05-11
2018-04-19
2018-04-25
2018-07-19
2018-04-11
2018-03-29
2018-05-16
2018-04-26
2018-05-03
2018-05-22
2018-04-19
2018-04-03
2018-05-25
2018-04-19
2018-05-15
2018-04-30
2018-05-17
2018-04-02
2018-04-05
2018-04-20
2018-03-02
2018-05-23
2018-03-23
2018-05-02
2018-06-21
2018-04-17
2018-05-24
2018-04-24
2018-03-21
2018-03-28
2018-04-25
2018-05-16
2018-05-04
2018-07-18
2018-05-18
2018-05-15
2018-04-26
2018-05-11
2018-04-17
2018-05-04
2018-04-16
2018-05-03
2018-04-05
2018-04-16
2018-05-08
2018-04-11
2018-05-16
2018-04-02
2018-04-24
2018-03-23
2018-04-06
2018-06-04
2018-06-27
2018-03-23
2018-03-28
2018-05-02
2018-04-02
2018-05-15
2018-06-26
2018-05-10
2018-06-01
2018-04-24
2018-04-09
2018-04-23
2018-04-13
2018-04-27
2018-04-23
2018-05-28
2018-04-26
2018-03-30
2018-05-08
2018-06-14
2018-03-23
2018-04-04
2018-03-29
2018-05-01
2018-04-05
2018-05-23
2018-05-01
2018-05-30
2018-05-31
2018-05-16
2018-05-16
2018-05-08
2018-06-06
2018-04-10
2018-04-19
2018-06-08
2018-05-21
2018-04-27
2018-05-23
2018-04-26
2018-05-10
2018-06-25
2018-02-27
2018-04-18
2018-05-02
2018-06-11
2018-06-01
2018-04-06
2018-04-26
2018-04-20
2018-05-03
2018-04-09
2018-03-15
2018-04-16
2018-05-25
2018-05-25
2018-05-04
2018-03-27
2018-04-11
2018-04-13
2018-05-11
2018-04-17
2018-04-26
2018-04-11
2018-04-05
2018-04-13
2018-05-21
2018-05-01
2018-05-21
2018-04-16
2018-06-07
2018-06-05
2018-06-25
2018-04-09
2018-06-20
2018-05-14
2018-04-24
2018-03-23
2018-03-16
2018-03-19
2018-05-11
2018-03-29
2018-03-16
2018-03-30
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
"75% chance of project completion by 16th April"

## MonteCarlo (2)
Monte Carlo 1000 run |  |  |  | Parameters
Completion Date | Row Labels | Freq | 2017-12-01 | Start Date
2018-05-10 | 2018-03-06 | 1 | 15 | User Stories
2018-06-08 | 2018-03-15 | 1 | 5 | Developers
2018-07-04 | 2018-03-16 | 1 | 4-16hrs | Grooming Phase
2018-04-12 | 2018-03-19 | 1 | 8-80hrs | In Progress Phase | =16-104hrs
2018-08-24 | 2018-03-27 | 1 | 2-8hrs | Review Phase
2018-10-05 | 2018-03-28 | 1 | 30% | Chance of bug raised on story
2018-08-10 | 2018-03-30 | 1 | 8-32hrs | Work required to resolve bug
2018-10-10 | 2018-04-02 | 2 | 20% | Chance of developer being absent
2018-08-31 | 2018-04-03 | 3 | 1-4days | Length of developer absence
2018-05-09 | 2018-04-04 | 1 | 2-6hrs | Developer capacity per day
2018-10-11 | 2018-04-05 | 2 | 0-3 | Number of stories added every 4w
2018-07-25 | 2018-04-06 | 2 | to do | Degree of dependency
2018-09-21 | 2018-04-09 | 5 | to do | Breadth of dependency
2018-08-09 | 2018-04-10 | 3 | to do | Chance of being blocked on a story
2018-08-14 | 2018-04-11 | 1 | to do | Length of block on story
2018-11-01 | 2018-04-12 | 4
2018-12-20 | 2018-04-13 | 4
2019-02-01 | 2018-04-16 | 2
2018-12-11 | 2018-04-17 | 2
2018-09-14 | 2018-04-18 | 6
2018-10-08 | 2018-04-19 | 1
2018-07-03 | 2018-04-20 | 2
2018-09-27 | 2018-04-23 | 4
2018-04-12 | 2018-04-24 | 1
2018-06-27 | 2018-04-25 | 5
2018-05-08 | 2018-04-26 | 4
2018-12-24 | 2018-04-27 | 2
2018-06-15 | 2018-04-30 | 2
2018-05-11 | 2018-05-01 | 8
2018-10-18 | 2018-05-02 | 6
2018-06-14 | 2018-05-03 | 10
2018-05-07 | 2018-05-04 | 6
2018-10-24 | 2018-05-07 | 10
2018-06-01 | 2018-05-08 | 14
2018-08-10 | 2018-05-09 | 12
2018-10-08 | 2018-05-10 | 13
2018-07-06 | 2018-05-11 | 5
2018-08-15 | 2018-05-14 | 1
2018-05-25 | 2018-05-15 | 1
2018-08-08 | 2018-05-16 | 3
2018-09-19 | 2018-05-17 | 2
2018-05-08 | 2018-05-18 | 4
2018-06-11 | 2018-05-21 | 3
2018-05-10 | 2018-05-22 | 8
2018-08-31 | 2018-05-23 | 9
2018-09-03 | 2018-05-24 | 7
2018-08-21 | 2018-05-25 | 12
2018-09-27 | 2018-05-28 | 5
2018-06-08 | 2018-05-29 | 8
2018-10-18 | 2018-05-30 | 10
2018-05-31 | 2018-05-31 | 12
2018-07-04 | 2018-06-01 | 13
2018-10-16 | 2018-06-04 | 11
2018-08-29 | 2018-06-05 | 14
2018-05-22 | 2018-06-06 | 10
2018-05-08 | 2018-06-07 | 12
2018-05-07 | 2018-06-08 | 15
2018-06-08 | 2018-06-11 | 4
2018-07-13 | 2018-06-12 | 3
2018-07-16 | 2018-06-13 | 4
2018-08-06 | 2018-06-14 | 3
2018-07-27 | 2018-06-15 | 3
2018-04-05 | 2018-06-18 | 7
2018-05-31 | 2018-06-19 | 10
2018-07-13 | 2018-06-20 | 5
2018-08-02 | 2018-06-21 | 8
2018-07-05 | 2018-06-22 | 6
2018-07-03 | 2018-06-25 | 9
2018-10-18 | 2018-06-26 | 5
2018-08-07 | 2018-06-27 | 9
2018-10-19 | 2018-06-28 | 5
2018-09-24 | 2018-06-29 | 9
2018-09-11 | 2018-07-02 | 12
2018-10-26 | 2018-07-03 | 15
2018-05-29 | 2018-07-04 | 10
2018-05-23 | 2018-07-05 | 12
2018-04-25 | 2018-07-06 | 18
2018-11-20 | 2018-07-09 | 6
2018-12-11 | 2018-07-10 | 5
2018-08-03 | 2018-07-11 | 2
2018-05-25 | 2018-07-12 | 4
2018-07-19 | 2018-07-13 | 5
2018-05-22 | 2018-07-16 | 2
2018-07-12 | 2018-07-17 | 7
2018-08-17 | 2018-07-18 | 6
2018-12-13 | 2018-07-19 | 11
2018-04-13 | 2018-07-20 | 2
2018-08-21 | 2018-07-23 | 7
2018-06-05 | 2018-07-24 | 8
2018-05-22 | 2018-07-25 | 14
2018-07-30 | 2018-07-26 | 13
2018-07-26 | 2018-07-27 | 14
2018-05-31 | 2018-07-30 | 12
2018-08-08 | 2018-07-31 | 11
2018-05-29 | 2018-08-01 | 11
2018-07-24 | 2018-08-02 | 11
2018-07-26 | 2018-08-03 | 10
2018-06-18 | 2018-08-06 | 3
2018-05-08 | 2018-08-07 | 2
2018-04-09 | 2018-08-08 | 6
2018-09-25 | 2018-08-09 | 4
2018-05-09 | 2018-08-10 | 5
2018-08-29 | 2018-08-14 | 7
2018-08-31 | 2018-08-15 | 3
2018-06-05 | 2018-08-16 | 5
2018-07-19 | 2018-08-17 | 9
2018-08-08 | 2018-08-20 | 15
2018-10-19 | 2018-08-21 | 8
2018-10-23 | 2018-08-22 | 5
2018-07-23 | 2018-08-23 | 4
2018-11-12 | 2018-08-24 | 9
2018-08-02 | 2018-08-27 | 5
2018-07-25 | 2018-08-28 | 2
2019-01-15 | 2018-08-29 | 9
2018-12-04 | 2018-08-30 | 6
2018-05-10 | 2018-08-31 | 7
2018-07-25 | 2018-09-03 | 3
2018-06-29 | 2018-09-04 | 5
2018-06-04 | 2018-09-05 | 7
2018-06-25 | 2018-09-06 | 5
2018-05-23 | 2018-09-07 | 4
2019-05-20 | 2018-09-10 | 1
2018-08-30 | 2018-09-11 | 4
2018-11-08 | 2018-09-12 | 5
2018-05-29 | 2018-09-13 | 6
2018-09-14 | 2018-09-14 | 7
2018-06-27 | 2018-09-17 | 6
2018-05-02 | 2018-09-18 | 1
2018-08-27 | 2018-09-19 | 8
2018-07-06 | 2018-09-20 | 6
2018-08-01 | 2018-09-21 | 6
2018-04-09 | 2018-09-24 | 6
2018-07-26 | 2018-09-25 | 7
2018-10-12 | 2018-09-26 | 3
2018-04-04 | 2018-09-27 | 10
2018-08-24 | 2018-09-28 | 7
2018-07-25 | 2018-10-01 | 1
2019-04-03 | 2018-10-02 | 1
2018-07-03 | 2018-10-03 | 2
2018-06-27 | 2018-10-05 | 7
2018-10-09 | 2018-10-08 | 2
2018-08-31 | 2018-10-09 | 2
2018-08-08 | 2018-10-10 | 1
2018-06-05 | 2018-10-11 | 3
2018-07-25 | 2018-10-12 | 2
2018-06-08 | 2018-10-15 | 2
2018-10-11 | 2018-10-16 | 4
2018-06-06 | 2018-10-17 | 2
2018-07-31 | 2018-10-18 | 4
2018-07-06 | 2018-10-19 | 6
2018-11-20 | 2018-10-22 | 5
2018-08-16 | 2018-10-23 | 3
2018-10-24 | 2018-10-24 | 5
2018-05-09 | 2018-10-25 | 2
2018-05-03 | 2018-10-26 | 3
2018-05-08 | 2018-10-29 | 1
2018-07-02 | 2018-10-31 | 4
2018-09-12 | 2018-11-01 | 4
2018-05-07 | 2018-11-02 | 2
2018-05-16 | 2018-11-07 | 3
2018-07-05 | 2018-11-08 | 4
2018-04-11 | 2018-11-09 | 3
2018-08-14 | 2018-11-12 | 4
2018-03-19 | 2018-11-13 | 1
2018-10-05 | 2018-11-14 | 2
2018-10-16 | 2018-11-15 | 4
2018-07-06 | 2018-11-19 | 2
2018-08-02 | 2018-11-20 | 2
2018-05-10 | 2018-11-21 | 4
2018-08-14 | 2018-11-22 | 3
2018-12-20 | 2018-11-23 | 1
2018-10-22 | 2018-11-30 | 2
2018-06-19 | 2018-12-04 | 1
2018-09-27 | 2018-12-05 | 2
2018-06-18 | 2018-12-06 | 3
2018-07-25 | 2018-12-07 | 3
2018-05-07 | 2018-12-11 | 2
2018-11-22 | 2018-12-12 | 1
2018-10-26 | 2018-12-13 | 1
2018-07-26 | 2018-12-14 | 1
2018-07-17 | 2018-12-17 | 1
2018-06-22 | 2018-12-19 | 2
2018-07-06 | 2018-12-20 | 2
2018-07-24 | 2018-12-21 | 1
2018-07-02 | 2018-12-24 | 1
2018-07-03 | 2018-12-26 | 1
2018-06-08 | 2018-12-27 | 1
2018-08-16 | 2019-01-01 | 2
2018-05-30 | 2019-01-02 | 1
2018-06-06 | 2019-01-04 | 2
2018-12-07 | 2019-01-15 | 1
2018-05-25 | 2019-01-17 | 1
2018-07-25 | 2019-01-18 | 1
2018-08-17 | 2019-01-30 | 2
2018-08-01 | 2019-01-31 | 1
2018-07-09 | 2019-02-01 | 1
2018-09-13 | 2019-02-05 | 1
2018-06-29 | 2019-02-06 | 1
2018-06-21 | 2019-02-07 | 1
2018-12-19 | 2019-02-12 | 1
2018-09-07 | 2019-02-15 | 1
2018-04-26 | 2019-03-05 | 1
2019-03-08 | 2019-03-08 | 1
2018-05-24 | 2019-03-12 | 1
2018-12-05 | 2019-03-15 | 1
2018-09-04 | 2019-04-03 | 1
2018-04-12 | 2019-04-04 | 2
2019-02-07 | 2019-04-24 | 1
2018-09-19 | 2019-05-20 | 1
2018-05-07 | Grand Total | 1000
2018-06-13
2018-05-04
2018-07-20
2018-09-17
2018-05-02
2018-04-25
2018-11-12
2018-06-22
2018-05-21
2018-03-15
2018-09-20
2018-05-01
2018-08-01
2018-09-11
2018-07-03
2018-06-26
2018-08-01
2018-08-09
2018-04-17
2018-05-04
2018-12-06
2018-07-17
2018-10-19
2019-01-30
2018-10-23
2018-06-01
2019-04-24
2018-06-05
2019-02-06
2018-05-08
2018-07-31
2018-07-06
2018-09-28
2018-06-25
2018-08-06
2018-04-03
2018-09-05
2018-06-11
2018-09-21
2018-07-12
2018-07-05
2018-07-31
2018-09-14
2018-07-03
2018-08-21
2018-06-19
2018-05-04
2018-04-09
2019-01-02
2019-01-04
2018-09-13
2018-10-15
2018-09-28
2018-09-13
2018-07-27
2018-08-03
2018-08-21
2018-05-09
2018-07-23
2018-07-18
2018-05-25
2018-05-23
2018-07-12
2018-05-01
2018-06-29
2018-11-07
2018-05-03
2018-06-01
2018-09-20
2018-06-21
2018-11-14
2019-01-17
2018-05-31
2018-04-23
2018-11-15
2018-11-09
2018-09-06
2018-11-07
2018-08-20
2018-06-19
2018-07-27
2018-05-11
2018-06-04
2018-09-03
2018-05-03
2018-06-27
2018-07-06
2018-11-30
2018-08-20
2018-06-05
2018-10-31
2018-09-13
2018-05-30
2018-07-25
2018-12-12
2018-07-30
2018-05-09
2018-06-19
2018-05-17
2018-05-10
2018-08-17
2018-07-24
2018-06-06
2018-07-30
2018-06-27
2018-06-08
2018-08-31
2018-06-20
2018-05-02
2018-05-01
2018-10-16
2018-06-13
2018-12-19
2018-07-02
2018-06-05
2018-08-29
2018-05-10
2018-06-04
2018-07-06
2018-11-12
2018-05-07
2018-04-25
2018-05-18
2018-06-18
2018-06-08
2018-08-20
2018-08-21
2018-04-12
2018-07-05
2018-07-17
2018-09-26
2018-04-09
2018-05-07
2018-07-23
2018-11-21
2018-07-05
2018-08-03
2018-05-29
2018-06-01
2018-10-17
2018-06-01
2018-05-01
2018-09-05
2018-09-21
2018-04-23
2018-11-30
2018-05-24
2018-06-08
2018-06-19
2018-08-20
2018-08-03
2018-06-06
2018-07-02
2018-09-12
2018-06-21
2018-06-08
2018-08-16
2018-05-25
2018-05-03
2018-09-25
2018-05-08
2018-08-29
2018-08-01
2018-11-07
2018-06-06
2018-04-26
2018-06-04
2018-06-29
2018-07-19
2018-07-19
2018-06-25
2018-07-17
2018-08-29
2018-09-21
2018-10-19
2018-06-21
2019-02-05
2018-05-23
2018-05-08
2018-07-27
2018-05-07
2018-07-18
2018-10-24
2018-04-23
2018-10-24
2018-07-26
2018-06-26
2018-05-31
2018-06-01
2018-06-04
2018-07-03
2018-05-29
2018-05-09
2019-01-31
2018-06-07
2018-05-09
2018-04-30
2018-10-03
2018-07-03
2018-11-01
2018-09-11
2018-09-27
2018-06-26
2018-05-18
2018-03-06
2018-08-20
2018-06-26
2018-09-04
2018-09-06
2018-08-21
2018-08-30
2018-07-17
2018-05-28
2018-06-06
2018-12-14
2018-07-19
2018-11-23
2018-05-24
2018-04-02
2018-07-10
2018-05-22
2018-05-04
2018-08-03
2018-07-06
2018-06-05
2018-04-09
2018-09-14
2018-05-10
2018-07-03
2018-06-29
2018-08-17
2018-10-05
2018-08-14
2018-07-12
2018-03-27
2018-05-23
2018-08-20
2018-11-22
2018-08-17
2018-05-31
2018-06-25
2018-06-22
2018-10-22
2018-05-23
2018-06-25
2018-09-28
2018-07-18
2018-05-03
2018-11-15
2018-05-03
2018-06-07
2018-07-04
2018-04-27
2018-11-19
2019-04-04
2018-07-31
2018-06-14
2018-04-05
2018-10-26
2018-04-06
2018-07-02
2018-07-02
2018-06-01
2018-08-28
2018-03-28
2018-10-25
2018-05-28
2018-12-26
2018-05-10
2018-06-01
2018-06-21
2018-08-10
2018-09-14
2018-08-23
2018-11-14
2018-07-04
2018-06-04
2018-09-14
2018-06-28
2018-10-19
2018-06-27
2018-08-09
2018-07-26
2018-06-06
2018-07-02
2018-06-18
2018-10-22
2018-05-30
2018-07-25
2018-11-15
2018-09-19
2018-08-20
2018-07-30
2018-09-27
2018-08-27
2018-09-25
2018-05-08
2018-11-09
2018-07-04
2018-09-10
2018-04-19
2018-08-08
2018-05-09
2018-06-29
2018-08-22
2018-08-24
2018-10-17
2018-06-07
2018-06-11
2018-08-22
2018-05-18
2018-09-19
2018-08-03
2018-08-30
2018-10-31
2018-06-25
2018-07-26
2018-08-23
2018-04-26
2018-08-24
2018-08-16
2018-06-04
2018-08-22
2019-01-01
2018-06-08
2018-07-03
2018-05-25
2018-07-13
2018-07-04
2018-11-21
2018-06-27
2018-06-07
2018-09-19
2018-06-12
2018-06-18
2018-07-27
2018-09-12
2018-05-21
2018-08-06
2018-05-23
2018-07-27
2018-07-30
2018-07-17
2018-08-02
2018-10-05
2018-07-17
2018-08-31
2018-08-31
2018-07-26
2018-04-16
2018-07-06
2018-08-15
2018-09-20
2018-09-24
2018-05-30
2018-08-24
2018-08-23
2018-06-05
2018-04-17
2018-05-18
2018-07-10
2018-08-21
2018-08-01
2018-05-02
2018-11-01
2018-09-06
2018-06-15
2018-11-22
2018-08-20
2018-08-17
2018-07-26
2018-09-14
2018-09-17
2018-08-20
2018-08-17
2018-06-21
2018-09-24
2018-08-14
2018-08-27
2018-07-26
2018-07-31
2018-09-25
2018-07-30
2018-06-25
2018-11-13
2018-07-26
2018-09-17
2018-06-21
2018-06-01
2018-09-27
2018-06-05
2018-05-24
2018-05-02
2018-06-07
2018-07-31
2018-10-19
2018-07-06
2018-07-06
2018-04-18
2018-09-05
2018-11-08
2018-06-07
2018-07-05
2018-09-28
2018-09-19
2018-06-29
2018-07-24
2018-08-14
2018-09-05
2018-08-03
2018-07-13
2018-10-25
2018-09-20
2018-07-27
2018-05-31
2018-07-09
2018-08-21
2018-07-31
2018-06-28
2018-04-20
2018-09-05
2018-07-30
2018-07-24
2018-07-11
2018-06-13
2018-07-24
2018-05-31
2018-07-05
2018-10-05
2018-08-02
2018-06-05
2018-10-31
2018-05-31
2018-10-05
2018-05-10
2018-08-01
2019-04-04
2018-05-01
2018-06-08
2018-07-27
2018-07-06
2018-05-07
2018-11-09
2018-05-22
2018-11-12
2018-09-26
2018-08-20
2018-06-19
2018-12-06
2018-05-25
2018-07-09
2018-08-29
2018-09-05
2019-03-12
2018-05-08
2018-12-21
2018-08-28
2018-04-18
2018-08-02
2018-10-02
2018-05-09
2018-10-22
2018-07-30
2018-08-20
2018-09-06
2018-05-24
2018-06-01
2018-05-08
2018-09-12
2018-05-28
2018-08-01
2018-07-25
2018-06-28
2018-06-04
2018-10-11
2018-08-02
2018-08-02
2018-05-21
2018-10-05
2018-07-06
2018-09-24
2018-09-25
2018-06-01
2018-07-09
2018-08-24
2018-09-28
2018-08-16
2018-07-31
2018-08-30
2018-08-01
2019-02-12
2018-07-06
2018-07-09
2018-07-16
2018-07-04
2018-04-10
2018-08-20
2018-08-20
2018-04-18
2018-09-28
2018-08-17
2018-12-17
2018-05-09
2018-07-26
2018-12-05
2018-08-22
2018-06-07
2018-09-17
2018-03-16
2018-04-20
2018-07-30
2018-06-01
2018-06-28
2018-07-25
2018-04-06
2018-05-01
2018-05-23
2018-07-05
2018-05-10
2018-11-21
2018-09-27
2018-09-06
2018-09-17
2018-04-02
2018-07-10
2018-05-25
2018-05-31
2018-04-25
2018-07-05
2018-06-20
2018-04-10
2018-05-08
2018-07-25
2018-05-16
2018-06-07
2018-10-09
2018-05-10
2018-05-30
2018-05-09
2018-04-18
2018-10-18
2018-09-24
2018-06-20
2018-06-21
2018-09-19
2018-11-08
2018-05-15
2018-06-07
2018-08-29
2018-04-25
2018-06-19
2019-01-18
2018-06-28
2018-07-06
2018-10-23
2018-05-10
2019-01-04
2018-07-19
2018-07-05
2018-11-02
2018-07-09
2018-07-03
2018-06-08
2018-04-10
2018-07-02
2018-06-05
2018-06-14
2018-05-30
2018-12-27
2018-09-07
2018-07-30
2018-07-06
2018-09-18
2018-08-02
2018-04-03
2018-05-03
2018-06-04
2018-05-29
2018-09-27
2018-11-21
2018-07-04
2018-09-04
2018-07-23
2018-07-04
2018-06-19
2018-09-20
2018-08-03
2018-11-19
2018-07-02
2018-05-30
2018-08-20
2018-07-19
2018-05-08
2018-05-09
2019-02-15
2018-07-11
2018-06-07
2018-05-31
2018-09-17
2018-07-03
2018-07-19
2018-04-03
2018-07-05
2018-07-26
2018-08-01
2018-06-29
2018-10-29
2018-09-12
2018-07-20
2018-07-19
2018-05-25
2018-06-11
2018-04-26
2018-09-20
2018-11-01
2018-08-24
2018-07-18
2018-06-20
2018-11-15
2018-06-12
2018-04-13
2018-07-04
2018-07-02
2018-07-02
2018-06-22
2018-08-27
2018-07-02
2018-12-06
2018-05-03
2018-06-13
2018-11-08
2018-07-27
2018-08-23
2018-05-08
2018-05-01
2018-08-09
2018-09-04
2019-01-30
2018-08-22
2018-04-18
2018-06-27
2018-08-27
2019-01-01
2018-05-28
2018-06-22
2018-08-01
2018-06-06
2018-06-08
2018-08-07
2018-05-14
2018-06-12
2018-07-18
2018-07-05
2018-05-29
2018-09-19
2018-09-13
2018-09-25
2018-07-30
2018-05-16
2018-05-02
2018-07-27
2018-07-24
2018-09-03
2018-03-30
2018-08-08
2018-09-21
2018-05-24
2018-07-10
2018-06-18
2018-07-25
2018-09-26
2018-07-06
2018-05-11
2018-05-30
2018-12-07
2018-05-04
2018-05-30
2018-09-11
2018-05-29
2018-05-22
2018-08-30
2018-07-27
2018-07-03
2018-06-05
2018-06-22
2018-09-07
2018-09-27
2018-05-25
2018-08-29
2018-07-18
2018-05-11
2018-06-15
2018-08-24
2018-06-06
2018-07-23
2018-08-10
2018-06-04
2018-04-30
2018-05-01
2019-03-05
2018-07-03
2018-05-11
2018-09-25
2018-06-29
2018-06-25
2018-05-31
2018-05-30
2018-09-27
2018-10-03
2018-06-04
2018-06-05
2018-07-31
2018-05-25
2018-07-27
2018-06-08
2018-04-27
2018-06-18
2018-07-23
2018-04-24
2018-08-03
2018-07-24
2018-10-01
2018-07-31
2018-07-25
2018-10-31
2019-03-15
2018-05-24
2018-06-06
2018-08-14
2018-06-20
2018-04-13
2018-08-20
2018-08-24
2018-05-22
2018-07-31
2018-09-28
2018-08-02
2018-09-24
2018-10-15
2018-10-22
2018-08-17
2018-09-07
2018-07-23
2018-04-18
2018-05-28
2018-05-03
2018-06-07
2018-08-29
2018-05-25
2018-08-02
2018-08-10
2018-07-19
2018-11-02
2018-05-04
2018-07-27
2018-05-07
2018-07-19
2018-10-16
2018-06-27
2018-10-12
2018-06-05
2018-07-13
2018-07-03
2018-07-10
2018-06-19
2018-05-17
2018-08-03
2018-05-23
2018-04-13
2018-06-26
2018-06-19
2018-06-07
2018-07-27
2018-10-24
2018-12-07
2018-09-13
2018-04-16
2018-06-01
2018-09-04
2018-09-21
2018-05-10
2018-06-25
2018-04-23
2018-06-08
2018-08-15
2018-08-30
2018-05-22
2018-09-05
2018-05-03
2018-07-30
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sensitivity Analysis
| Parameters | Sensitivity parameter
2017-12-01 | Start Date |  | Calculate these figures for each simulation run | Vary one parameter across many Monte Carlo runs | Plot final parameter figure against estimated completion date
5 | Developers | Number of developers
15 | User Stories | Total work for initial stories
4-16hrs | Grooming Phase
8-80hrs | In Progress Phase
2-8hrs | Review Phase
30% | Chance of bug raised on story | Total work for all bugs added
8-32hrs | Work required to resolve bug
20% | Chance of developer being absent | Average developer capacity
1-4days | Length of developer absence
2-6hrs | Developer capacity per day
0-3 | Number of stories added every 4w | Total work for all stories added
|  | Total developer capacity will always equal total work? Two sides of same coin? |  |  | How to identify if sensitivity due to combination of parameters?

## MonteCarlo (3)
ProjectCompleteDate | TotalInitialWorkHrs | NumDevs | AvgDevCapacity | TotalBugsHrs | TotalAddedStoriesHrs | Completion Date | Count of ProjectCompleteDate | Average of TotalInitialWorkHrs | Average of AvgDevCapacity | Average of TotalBugsHrs | Average of TotalAddedStoriesHrs
2018-04-03 | 891 | 5 | 625 | 39 | 0 | 2018 | 763 | 1952.5636 | 909.0079 | 204.7733 | 118.3277
2018-04-04 | 966 | 5 | 638 | 26 | 4 | Apr | 10 | 960.5 | 651.6 | 42.6 | 15.8
2018-04-06 | 984 | 5 | 664 | 36 | 39 | May | 34 | 1139.8824 | 706.0882 | 75.7353 | 37.3529
2018-04-11 | 818 | 5 | 637 | 89 | 4 | Jun | 68 | 1378.9706 | 763.5441 | 107.7353 | 57.2353
2018-04-25 | 1026 | 5 | 676 | 56 | 13 | Jul | 100 | 1567.39 | 813.53 | 147.91 | 72.19
2018-04-25 | 990 | 5 | 656 | 11 | 9 | Aug | 132 | 1805.197 | 870.8788 | 178.2955 | 100.4394
2018-04-27 | 994 | 5 | 661 | 78 | 26 | Sep | 129 | 2006.9922 | 920.8682 | 211.969 | 122.6047
2018-04-30 | 980 | 5 | 659 | 23 | 10 | Oct | 120 | 2208.3833 | 973.5 | 247.1167 | 144.2417
2018-04-30 | 998 | 5 | 666 | 39 | 26 | Nov | 93 | 2430.2043 | 1029.4624 | 278.3871 | 174.6452
2018-04-30 | 958 | 5 | 634 | 29 | 27 | Dec | 77 | 2632.8961 | 1084 | 320.7922 | 196.3636
2018-05-01 | 1005 | 5 | 684 | 79 | 20 | 2019 | 226 | 3275.854 | 1246.7035 | 431.0531 | 265.4381
2018-05-02 | 1005 | 5 | 657 | 20 | 25 | Jan | 53 | 2812.3396 | 1125.8679 | 345.1132 | 212.6981
2018-05-02 | 1024 | 5 | 692 | 81 | 10 | Feb | 47 | 3041.3191 | 1186.2766 | 396.8085 | 237.4255
2018-05-03 | 1026 | 5 | 678 | 110 | 10 | Mar | 40 | 3220.2 | 1235.225 | 433.1 | 258.5
2018-05-03 | 1037 | 5 | 672 | 58 | 14 | Apr | 35 | 3418.0571 | 1287.2857 | 453.6286 | 294.5429
2018-05-03 | 1034 | 5 | 669 | 62 | 51 | May | 18 | 3664.0556 | 1342.1667 | 506.0556 | 295.3889
2018-05-07 | 1085 | 5 | 703 | 40 | 53 | Jun | 13 | 3896.0769 | 1402.6923 | 541.2308 | 315.6154
2018-05-08 | 1155 | 5 | 697 | 82 | 35 | Jul | 12 | 4092.75 | 1450.5 | 510.6667 | 374.25
2018-05-08 | 1098 | 5 | 664 | 57 | 28 | Aug | 6 | 4246.3333 | 1496.3333 | 610.8333 | 363.8333
2018-05-08 | 1123 | 5 | 696 | 53 | 17 | Sep | 2 | 4357 | 1543.5 | 669 | 407
2018-05-08 | 1087 | 5 | 724 | 47 | 23 | Grand Total | 989 | 2254.9535 | 986.1759 | 256.4813 | 151.9444
2018-05-09 | 1106 | 5 | 691 | 47 | 52
2018-05-09 | 1117 | 5 | 680 | 46 | 34
2018-05-09 | 1093 | 5 | 713 | 86 | 23
2018-05-10 | 1019 | 5 | 689 | 90 | 32
2018-05-11 | 1131 | 5 | 663 | 117 | 0
2018-05-14 | 1141 | 5 | 709 | 90 | 42
2018-05-14 | 1058 | 5 | 696 | 114 | 17
2018-05-15 | 1229 | 5 | 726 | 85 | 52
2018-05-15 | 1164 | 5 | 700 | 82 | 38
2018-05-16 | 1295 | 5 | 743 | 53 | 40
2018-05-17 | 1235 | 5 | 751 | 81 | 39
2018-05-17 | 1132 | 5 | 702 | 72 | 53
2018-05-17 | 1113 | 5 | 715 | 86 | 26
2018-05-18 | 1170 | 5 | 719 | 53 | 67
2018-05-21 | 1186 | 5 | 735 | 75 | 32
2018-05-24 | 1155 | 5 | 728 | 137 | 66
2018-05-24 | 1079 | 5 | 690 | 118 | 30
2018-05-24 | 1133 | 5 | 708 | 78 | 69
2018-05-24 | 1252 | 5 | 759 | 77 | 80
2018-05-28 | 1260 | 5 | 716 | 110 | 25
2018-05-29 | 1341 | 5 | 739 | 29 | 62
2018-05-31 | 1376 | 5 | 758 | 89 | 55
2018-05-31 | 1292 | 5 | 741 | 71 | 50
2018-06-01 | 1277 | 5 | 702 | 55 | 31
2018-06-01 | 1222 | 5 | 728 | 50 | 61
2018-06-01 | 1158 | 5 | 742 | 135 | 58
2018-06-04 | 1350 | 5 | 758 | 79 | 81
2018-06-04 | 1329 | 5 | 750 | 72 | 75
2018-06-04 | 1284 | 5 | 737 | 88 | 35
2018-06-04 | 1398 | 5 | 783 | 73 | 28
2018-06-05 | 1225 | 5 | 729 | 151 | 36
2018-06-05 | 1267 | 5 | 758 | 72 | 45
2018-06-05 | 1342 | 5 | 751 | 69 | 51
2018-06-06 | 1268 | 5 | 733 | 111 | 27
2018-06-07 | 1299 | 5 | 729 | 42 | 72
2018-06-08 | 1333 | 5 | 719 | 65 | 38
2018-06-08 | 1437 | 5 | 781 | 89 | 117
2018-06-08 | 1364 | 5 | 776 | 137 | 63
2018-06-08 | 1322 | 5 | 717 | 27 | 82
2018-06-08 | 1448 | 5 | 766 | 139 | 37
2018-06-08 | 1294 | 5 | 757 | 100 | 60
2018-06-11 | 1365 | 5 | 730 | 73 | 56
2018-06-11 | 1340 | 5 | 754 | 181 | 17
2018-06-12 | 1309 | 5 | 746 | 97 | 46
2018-06-12 | 1532 | 5 | 813 | 114 | 79
2018-06-13 | 1321 | 5 | 757 | 94 | 45
2018-06-14 | 1358 | 5 | 752 | 99 | 9
2018-06-18 | 1311 | 5 | 737 | 71 | 50
2018-06-18 | 1350 | 5 | 781 | 131 | 32
2018-06-20 | 1392 | 5 | 795 | 93 | 71
2018-06-20 | 1357 | 5 | 787 | 79 | 95
2018-06-20 | 1397 | 5 | 770 | 55 | 75
2018-06-20 | 1408 | 5 | 788 | 160 | 38
2018-06-20 | 1365 | 5 | 762 | 50 | 60
2018-06-21 | 1475 | 5 | 764 | 89 | 44
2018-06-21 | 1381 | 5 | 759 | 115 | 54
2018-06-21 | 1328 | 5 | 733 | 124 | 41
2018-06-21 | 1424 | 5 | 767 | 95 | 59
2018-06-21 | 1480 | 5 | 787 | 121 | 58
2018-06-22 | 1373 | 5 | 763 | 141 | 30
2018-06-22 | 1302 | 5 | 736 | 109 | 30
2018-06-22 | 1421 | 5 | 773 | 129 | 54
2018-06-22 | 1422 | 5 | 778 | 117 | 43
2018-06-25 | 1431 | 5 | 799 | 111 | 106
2018-06-25 | 1286 | 5 | 736 | 142 | 79
2018-06-25 | 1462 | 5 | 781 | 94 | 49
2018-06-25 | 1438 | 5 | 792 | 56 | 89
2018-06-25 | 1422 | 5 | 804 | 216 | 85
2018-06-25 | 1360 | 5 | 743 | 168 | 45
2018-06-25 | 1349 | 5 | 751 | 99 | 46
2018-06-25 | 1346 | 5 | 744 | 107 | 87
2018-06-26 | 1397 | 5 | 773 | 162 | 90
2018-06-26 | 1333 | 5 | 754 | 204 | 85
2018-06-26 | 1401 | 5 | 732 | 120 | 40
2018-06-26 | 1403 | 5 | 773 | 130 | 53
2018-06-26 | 1409 | 5 | 782 | 155 | 31
2018-06-26 | 1540 | 5 | 817 | 106 | 33
2018-06-26 | 1376 | 5 | 801 | 146 | 60
2018-06-27 | 1473 | 5 | 791 | 89 | 70
2018-06-27 | 1445 | 5 | 764 | 86 | 48
2018-06-27 | 1321 | 5 | 744 | 107 | 69
2018-06-28 | 1491 | 5 | 789 | 158 | 39
2018-06-28 | 1475 | 5 | 793 | 65 | 73
2018-06-28 | 1470 | 5 | 823 | 110 | 91
2018-06-28 | 1485 | 5 | 772 | 94 | 117
2018-06-28 | 1413 | 5 | 763 | 122 | 24
2018-06-28 | 1275 | 5 | 715 | 154 | 15
2018-06-28 | 1535 | 5 | 779 | 139 | 16
2018-06-29 | 1463 | 5 | 805 | 57 | 98
2018-06-29 | 1492 | 5 | 771 | 63 | 116
2018-06-29 | 1451 | 5 | 782 | 175 | 55
2018-07-02 | 1461 | 5 | 815 | 221 | 49
2018-07-02 | 1477 | 5 | 780 | 90 | 71
2018-07-02 | 1402 | 5 | 743 | 146 | 50
2018-07-02 | 1460 | 5 | 770 | 161 | 52
2018-07-02 | 1362 | 5 | 780 | 120 | 93
2018-07-02 | 1450 | 5 | 813 | 166 | 73
2018-07-03 | 1430 | 5 | 796 | 125 | 70
2018-07-03 | 1455 | 5 | 770 | 132 | 44
2018-07-03 | 1565 | 5 | 809 | 117 | 88
2018-07-03 | 1463 | 5 | 775 | 84 | 75
2018-07-04 | 1458 | 5 | 800 | 172 | 67
2018-07-04 | 1368 | 5 | 764 | 121 | 27
2018-07-04 | 1486 | 5 | 785 | 63 | 73
2018-07-04 | 1572 | 5 | 839 | 98 | 70
2018-07-04 | 1403 | 5 | 809 | 165 | 73
2018-07-04 | 1516 | 5 | 763 | 174 | 27
2018-07-04 | 1459 | 5 | 774 | 87 | 75
2018-07-05 | 1325 | 5 | 769 | 208 | 47
2018-07-05 | 1616 | 5 | 841 | 97 | 63
2018-07-05 | 1544 | 5 | 816 | 162 | 81
2018-07-05 | 1467 | 5 | 779 | 153 | 42
2018-07-05 | 1572 | 5 | 813 | 112 | 82
2018-07-05 | 1550 | 5 | 826 | 125 | 59
2018-07-05 | 1480 | 5 | 820 | 129 | 38
2018-07-06 | 1439 | 5 | 750 | 93 | 66
2018-07-06 | 1537 | 5 | 800 | 104 | 33
2018-07-06 | 1594 | 5 | 831 | 145 | 49
2018-07-06 | 1481 | 5 | 803 | 84 | 60
2018-07-06 | 1548 | 5 | 849 | 167 | 42
2018-07-06 | 1647 | 5 | 818 | 101 | 106
2018-07-06 | 1541 | 5 | 801 | 157 | 56
2018-07-06 | 1508 | 5 | 802 | 60 | 38
2018-07-06 | 1388 | 5 | 790 | 212 | 37
2018-07-10 | 1613 | 5 | 776 | 73 | 68
2018-07-10 | 1519 | 5 | 817 | 117 | 63
2018-07-11 | 1511 | 5 | 806 | 127 | 115
2018-07-11 | 1486 | 5 | 791 | 239 | 31
2018-07-12 | 1445 | 5 | 797 | 238 | 67
2018-07-12 | 1607 | 5 | 841 | 157 | 78
2018-07-13 | 1521 | 5 | 794 | 217 | 55
2018-07-13 | 1579 | 5 | 834 | 133 | 79
2018-07-13 | 1558 | 5 | 828 | 194 | 39
2018-07-13 | 1632 | 5 | 819 | 124 | 78
2018-07-16 | 1532 | 5 | 808 | 151 | 79
2018-07-16 | 1563 | 5 | 799 | 67 | 121
2018-07-16 | 1517 | 5 | 774 | 76 | 77
2018-07-16 | 1517 | 5 | 770 | 106 | 93
2018-07-16 | 1618 | 5 | 794 | 97 | 82
2018-07-16 | 1528 | 5 | 803 | 189 | 38
2018-07-17 | 1591 | 5 | 811 | 146 | 74
2018-07-17 | 1482 | 5 | 820 | 187 | 44
2018-07-18 | 1717 | 5 | 841 | 175 | 67
2018-07-18 | 1552 | 5 | 812 | 137 | 71
2018-07-18 | 1664 | 5 | 855 | 207 | 79
2018-07-18 | 1556 | 5 | 813 | 162 | 72
2018-07-18 | 1746 | 5 | 867 | 159 | 69
2018-07-18 | 1640 | 5 | 813 | 147 | 69
2018-07-19 | 1755 | 5 | 855 | 141 | 91
2018-07-20 | 1539 | 5 | 794 | 118 | 71
2018-07-20 | 1572 | 5 | 789 | 195 | 78
2018-07-20 | 1732 | 5 | 807 | 84 | 79
2018-07-20 | 1625 | 5 | 831 | 172 | 79
2018-07-20 | 1560 | 5 | 813 | 82 | 111
2018-07-20 | 1529 | 5 | 793 | 132 | 79
2018-07-23 | 1555 | 5 | 791 | 84 | 84
2018-07-23 | 1543 | 5 | 820 | 139 | 123
2018-07-23 | 1483 | 5 | 798 | 163 | 47
2018-07-23 | 1491 | 5 | 794 | 121 | 82
2018-07-24 | 1608 | 5 | 811 | 193 | 73
2018-07-24 | 1597 | 5 | 832 | 193 | 61
2018-07-24 | 1608 | 5 | 831 | 167 | 73
2018-07-24 | 1644 | 5 | 838 | 190 | 90
2018-07-24 | 1557 | 5 | 816 | 155 | 68
2018-07-24 | 1673 | 5 | 862 | 227 | 26
2018-07-24 | 1498 | 5 | 821 | 249 | 82
2018-07-24 | 1583 | 5 | 802 | 117 | 96
2018-07-24 | 1672 | 5 | 804 | 107 | 84
2018-07-24 | 1643 | 5 | 864 | 156 | 135
2018-07-25 | 1665 | 5 | 826 | 208 | 65
2018-07-25 | 1612 | 5 | 845 | 152 | 82
2018-07-25 | 1518 | 5 | 791 | 111 | 79
2018-07-26 | 1741 | 5 | 870 | 231 | 101
2018-07-26 | 1567 | 5 | 836 | 206 | 61
2018-07-26 | 1674 | 5 | 814 | 172 | 49
2018-07-26 | 1718 | 5 | 840 | 142 | 85
2018-07-27 | 1694 | 5 | 858 | 121 | 80
2018-07-27 | 1828 | 5 | 909 | 135 | 133
2018-07-27 | 1636 | 5 | 841 | 125 | 80
2018-07-27 | 1639 | 5 | 825 | 295 | 100
2018-07-30 | 1745 | 5 | 855 | 128 | 84
2018-07-30 | 1641 | 5 | 825 | 78 | 138
2018-07-30 | 1625 | 5 | 859 | 179 | 110
2018-07-30 | 1652 | 5 | 829 | 157 | 85
2018-07-30 | 1711 | 5 | 852 | 184 | 46
2018-07-30 | 1718 | 5 | 840 | 205 | 60
2018-07-31 | 1711 | 5 | 826 | 103 | 94
2018-07-31 | 1688 | 5 | 837 | 204 | 57
2018-07-31 | 1526 | 5 | 791 | 137 | 85
2018-07-31 | 1642 | 5 | 835 | 171 | 94
2018-07-31 | 1603 | 5 | 807 | 186 | 55
2018-08-01 | 1690 | 5 | 828 | 124 | 121
2018-08-01 | 1709 | 5 | 811 | 112 | 121
2018-08-01 | 1715 | 5 | 849 | 92 | 115
2018-08-01 | 1675 | 5 | 881 | 190 | 80
2018-08-01 | 1689 | 5 | 832 | 121 | 91
2018-08-01 | 1783 | 5 | 883 | 172 | 110
2018-08-01 | 1828 | 5 | 872 | 129 | 67
2018-08-01 | 1651 | 5 | 804 | 143 | 51
2018-08-02 | 1728 | 5 | 865 | 179 | 61
2018-08-02 | 1604 | 5 | 807 | 163 | 48
2018-08-02 | 1696 | 5 | 849 | 184 | 120
2018-08-02 | 1705 | 5 | 837 | 132 | 113
2018-08-02 | 1718 | 5 | 848 | 161 | 107
2018-08-02 | 1718 | 5 | 845 | 157 | 69
2018-08-02 | 1650 | 5 | 835 | 242 | 70
2018-08-02 | 1761 | 5 | 856 | 197 | 74
2018-08-02 | 1710 | 5 | 852 | 224 | 88
2018-08-02 | 1710 | 5 | 852 | 147 | 71
2018-08-02 | 1629 | 5 | 811 | 110 | 40
2018-08-02 | 1666 | 5 | 840 | 167 | 108
2018-08-02 | 1782 | 5 | 836 | 128 | 99
2018-08-02 | 1693 | 5 | 832 | 156 | 66
2018-08-03 | 1867 | 5 | 879 | 198 | 90
2018-08-03 | 1872 | 5 | 861 | 87 | 103
2018-08-03 | 1600 | 5 | 765 | 65 | 91
2018-08-03 | 1777 | 5 | 854 | 167 | 83
2018-08-03 | 1744 | 5 | 845 | 172 | 64
2018-08-03 | 1719 | 5 | 851 | 181 | 63
2018-08-03 | 1808 | 5 | 859 | 95 | 142
2018-08-03 | 1742 | 5 | 840 | 195 | 86
2018-08-03 | 1703 | 5 | 864 | 214 | 81
2018-08-03 | 1692 | 5 | 861 | 185 | 53
2018-08-03 | 1704 | 5 | 834 | 125 | 68
2018-08-06 | 1723 | 5 | 850 | 149 | 113
2018-08-06 | 1852 | 5 | 880 | 147 | 120
2018-08-07 | 1883 | 5 | 866 | 58 | 133
2018-08-08 | 1722 | 5 | 875 | 190 | 138
2018-08-08 | 1798 | 5 | 897 | 204 | 96
2018-08-08 | 1815 | 5 | 867 | 190 | 75
2018-08-08 | 1772 | 5 | 891 | 222 | 96
2018-08-09 | 1848 | 5 | 891 | 167 | 67
2018-08-09 | 1624 | 5 | 827 | 209 | 65
2018-08-10 | 1755 | 5 | 875 | 97 | 132
2018-08-10 | 1844 | 5 | 924 | 231 | 121
2018-08-10 | 1767 | 5 | 834 | 135 | 90
2018-08-10 | 1833 | 5 | 899 | 191 | 118
2018-08-13 | 1875 | 5 | 883 | 125 | 132
2018-08-13 | 1779 | 5 | 840 | 135 | 111
2018-08-13 | 1809 | 5 | 885 | 221 | 90
2018-08-13 | 1807 | 5 | 895 | 116 | 147
2018-08-14 | 1702 | 5 | 863 | 201 | 118
2018-08-14 | 1827 | 5 | 887 | 148 | 115
2018-08-14 | 1809 | 5 | 892 | 180 | 96
2018-08-14 | 1762 | 5 | 863 | 186 | 58
2018-08-14 | 1709 | 5 | 844 | 192 | 90
2018-08-15 | 1895 | 5 | 888 | 108 | 94
2018-08-15 | 1790 | 5 | 869 | 164 | 90
2018-08-15 | 1769 | 5 | 876 | 196 | 102
2018-08-15 | 1700 | 5 | 844 | 241 | 74
2018-08-16 | 1878 | 5 | 885 | 183 | 147
2018-08-16 | 1828 | 5 | 879 | 141 | 101
2018-08-16 | 1913 | 5 | 928 | 115 | 78
2018-08-16 | 1832 | 5 | 877 | 153 | 142
2018-08-16 | 1763 | 5 | 890 | 218 | 96
2018-08-16 | 1863 | 5 | 911 | 253 | 89
2018-08-17 | 1900 | 5 | 897 | 262 | 62
2018-08-17 | 1865 | 5 | 900 | 194 | 122
2018-08-17 | 1735 | 5 | 841 | 183 | 85
2018-08-17 | 1908 | 5 | 877 | 156 | 87
2018-08-17 | 1797 | 5 | 893 | 232 | 90
2018-08-20 | 1906 | 5 | 903 | 122 | 118
2018-08-20 | 1757 | 5 | 897 | 191 | 111
2018-08-20 | 1744 | 5 | 844 | 145 | 142
2018-08-20 | 1871 | 5 | 903 | 290 | 111
2018-08-20 | 1774 | 5 | 865 | 157 | 50
2018-08-20 | 1922 | 5 | 899 | 114 | 118
2018-08-21 | 1737 | 5 | 825 | 185 | 83
2018-08-21 | 1792 | 5 | 849 | 233 | 71
2018-08-21 | 1854 | 5 | 877 | 204 | 118
2018-08-21 | 1837 | 5 | 900 | 209 | 81
2018-08-22 | 1769 | 5 | 866 | 253 | 59
2018-08-22 | 1900 | 5 | 886 | 229 | 49
2018-08-22 | 1750 | 5 | 875 | 257 | 106
2018-08-22 | 1810 | 5 | 882 | 171 | 65
2018-08-22 | 1872 | 5 | 867 | 167 | 91
2018-08-22 | 1701 | 5 | 819 | 94 | 121
2018-08-22 | 1621 | 5 | 835 | 228 | 62
2018-08-23 | 1840 | 5 | 865 | 192 | 132
2018-08-23 | 1688 | 5 | 861 | 149 | 122
2018-08-23 | 1752 | 5 | 839 | 189 | 99
2018-08-23 | 1753 | 5 | 839 | 167 | 129
2018-08-24 | 1856 | 5 | 859 | 213 | 87
2018-08-24 | 1821 | 5 | 877 | 138 | 79
2018-08-24 | 1725 | 5 | 870 | 268 | 99
2018-08-24 | 1807 | 5 | 834 | 93 | 169
2018-08-24 | 1713 | 5 | 847 | 131 | 76
2018-08-24 | 1785 | 5 | 883 | 200 | 95
2018-08-24 | 1946 | 5 | 869 | 198 | 80
2018-08-27 | 1799 | 5 | 866 | 200 | 99
2018-08-27 | 1978 | 5 | 944 | 187 | 124
2018-08-27 | 1873 | 5 | 886 | 208 | 104
2018-08-27 | 1919 | 5 | 908 | 219 | 125
2018-08-27 | 1933 | 5 | 912 | 218 | 118
2018-08-28 | 1949 | 5 | 890 | 142 | 103
2018-08-28 | 1879 | 5 | 921 | 275 | 94
2018-08-28 | 1828 | 5 | 853 | 208 | 85
2018-08-28 | 1848 | 5 | 885 | 222 | 132
2018-08-28 | 1967 | 5 | 912 | 128 | 139
2018-08-28 | 1806 | 5 | 847 | 230 | 105
2018-08-28 | 1851 | 5 | 894 | 141 | 121
2018-08-28 | 2005 | 5 | 932 | 254 | 117
2018-08-28 | 1735 | 5 | 872 | 238 | 99
2018-08-28 | 1896 | 5 | 866 | 185 | 103
2018-08-28 | 1863 | 5 | 913 | 264 | 79
2018-08-28 | 1891 | 5 | 895 | 171 | 166
2018-08-29 | 1868 | 5 | 874 | 155 | 135
2018-08-29 | 1975 | 5 | 877 | 159 | 95
2018-08-29 | 1981 | 5 | 910 | 209 | 110
2018-08-29 | 1787 | 5 | 889 | 214 | 99
2018-08-29 | 1715 | 5 | 844 | 192 | 99
2018-08-30 | 1950 | 5 | 898 | 197 | 140
2018-08-30 | 2052 | 5 | 915 | 160 | 139
2018-08-30 | 1926 | 5 | 890 | 101 | 160
2018-08-30 | 1829 | 5 | 870 | 187 | 101
2018-08-30 | 1911 | 5 | 871 | 127 | 142
2018-08-30 | 1803 | 5 | 875 | 230 | 75
2018-08-30 | 1927 | 5 | 886 | 133 | 131
2018-08-31 | 2018 | 5 | 917 | 241 | 116
2018-08-31 | 2001 | 5 | 945 | 274 | 101
2018-08-31 | 1810 | 5 | 879 | 201 | 167
2018-08-31 | 1977 | 5 | 935 | 229 | 126
2018-08-31 | 1944 | 5 | 929 | 242 | 92
2018-09-03 | 1730 | 5 | 851 | 187 | 91
2018-09-05 | 1888 | 5 | 916 | 220 | 88
2018-09-06 | 1978 | 5 | 928 | 268 | 95
2018-09-06 | 2032 | 5 | 914 | 104 | 157
2018-09-06 | 1915 | 5 | 890 | 139 | 116
2018-09-06 | 1951 | 5 | 918 | 237 | 121
2018-09-06 | 1795 | 5 | 889 | 263 | 86
2018-09-06 | 1822 | 5 | 851 | 236 | 87
2018-09-06 | 1926 | 5 | 921 | 201 | 139
2018-09-06 | 2057 | 5 | 940 | 245 | 73
2018-09-06 | 1960 | 5 | 897 | 248 | 107
2018-09-06 | 1858 | 5 | 878 | 177 | 115
2018-09-07 | 1861 | 5 | 867 | 189 | 73
2018-09-07 | 1999 | 5 | 902 | 134 | 126
2018-09-07 | 2022 | 5 | 938 | 200 | 116
2018-09-07 | 1957 | 5 | 902 | 236 | 123
2018-09-07 | 1863 | 5 | 866 | 153 | 113
2018-09-10 | 2044 | 5 | 918 | 167 | 114
2018-09-10 | 2071 | 5 | 936 | 166 | 97
2018-09-10 | 2007 | 5 | 919 | 232 | 109
2018-09-10 | 1938 | 5 | 905 | 337 | 88
2018-09-11 | 1923 | 5 | 935 | 232 | 112
2018-09-11 | 1909 | 5 | 863 | 144 | 125
2018-09-11 | 1952 | 5 | 912 | 177 | 138
2018-09-11 | 1888 | 5 | 899 | 152 | 131
2018-09-11 | 2026 | 5 | 921 | 139 | 121
2018-09-12 | 1991 | 5 | 924 | 152 | 98
2018-09-12 | 1997 | 5 | 910 | 225 | 66
2018-09-12 | 2083 | 5 | 919 | 187 | 94
2018-09-12 | 1872 | 5 | 886 | 209 | 131
2018-09-12 | 2014 | 5 | 954 | 225 | 162
2018-09-12 | 2015 | 5 | 945 | 309 | 100
2018-09-12 | 1874 | 5 | 883 | 179 | 130
2018-09-12 | 1910 | 5 | 934 | 224 | 194
2018-09-12 | 1852 | 5 | 885 | 268 | 103
2018-09-12 | 1990 | 5 | 899 | 228 | 141
2018-09-12 | 1896 | 5 | 921 | 205 | 137
2018-09-12 | 1868 | 5 | 912 | 259 | 99
2018-09-12 | 2158 | 5 | 936 | 180 | 118
2018-09-12 | 1889 | 5 | 913 | 226 | 136
2018-09-13 | 2049 | 5 | 920 | 110 | 194
2018-09-13 | 1928 | 5 | 872 | 171 | 132
2018-09-13 | 2095 | 5 | 942 | 173 | 154
2018-09-14 | 2044 | 5 | 907 | 237 | 88
2018-09-14 | 2064 | 5 | 931 | 261 | 111
2018-09-14 | 1983 | 5 | 907 | 154 | 161
2018-09-14 | 1929 | 5 | 887 | 190 | 121
2018-09-14 | 2087 | 5 | 945 | 101 | 174
2018-09-14 | 2051 | 5 | 888 | 206 | 129
2018-09-14 | 1944 | 5 | 915 | 192 | 122
2018-09-14 | 1980 | 5 | 916 | 236 | 100
2018-09-14 | 2020 | 5 | 922 | 257 | 134
2018-09-17 | 2003 | 5 | 928 | 153 | 87
2018-09-17 | 1966 | 5 | 904 | 301 | 79
2018-09-17 | 2069 | 5 | 933 | 148 | 147
2018-09-17 | 2047 | 5 | 931 | 158 | 137
2018-09-17 | 1916 | 5 | 877 | 180 | 94
2018-09-18 | 1947 | 5 | 904 | 122 | 159
2018-09-18 | 2004 | 5 | 922 | 245 | 99
2018-09-18 | 2048 | 5 | 961 | 265 | 119
2018-09-18 | 2022 | 5 | 928 | 227 | 152
2018-09-18 | 1944 | 5 | 908 | 212 | 91
2018-09-18 | 2039 | 5 | 956 | 317 | 89
2018-09-19 | 2002 | 5 | 928 | 249 | 94
2018-09-19 | 2002 | 5 | 888 | 266 | 123
2018-09-19 | 1838 | 5 | 893 | 246 | 128
2018-09-19 | 2008 | 5 | 896 | 158 | 152
2018-09-19 | 1910 | 5 | 874 | 301 | 68
2018-09-19 | 1932 | 5 | 892 | 272 | 108
2018-09-20 | 1935 | 5 | 901 | 232 | 87
2018-09-20 | 1914 | 5 | 933 | 286 | 115
2018-09-20 | 2105 | 5 | 932 | 229 | 154
2018-09-20 | 2025 | 5 | 908 | 168 | 107
2018-09-20 | 2043 | 5 | 939 | 325 | 96
2018-09-20 | 1944 | 5 | 897 | 138 | 107
2018-09-20 | 2056 | 5 | 923 | 151 | 149
2018-09-20 | 1907 | 5 | 921 | 236 | 116
2018-09-20 | 1977 | 5 | 912 | 98 | 177
2018-09-20 | 2009 | 5 | 931 | 184 | 175
2018-09-20 | 1912 | 5 | 924 | 268 | 144
2018-09-21 | 2158 | 5 | 951 | 136 | 158
2018-09-21 | 2021 | 5 | 928 | 254 | 119
2018-09-21 | 1961 | 5 | 898 | 282 | 124
2018-09-21 | 1793 | 5 | 883 | 295 | 113
2018-09-21 | 1997 | 5 | 896 | 201 | 97
2018-09-21 | 2112 | 5 | 945 | 187 | 131
2018-09-21 | 1986 | 5 | 898 | 184 | 135
2018-09-21 | 2067 | 5 | 935 | 198 | 106
2018-09-21 | 2081 | 5 | 922 | 219 | 121
2018-09-21 | 2163 | 5 | 955 | 183 | 153
2018-09-24 | 2118 | 5 | 938 | 216 | 121
2018-09-24 | 2006 | 5 | 969 | 222 | 122
2018-09-24 | 1956 | 5 | 912 | 242 | 105
2018-09-24 | 2049 | 5 | 953 | 207 | 109
2018-09-24 | 1897 | 5 | 892 | 225 | 118
2018-09-24 | 2147 | 5 | 967 | 276 | 112
2018-09-25 | 2017 | 5 | 940 | 260 | 96
2018-09-25 | 2034 | 5 | 911 | 221 | 125
2018-09-25 | 2091 | 5 | 953 | 235 | 125
2018-09-25 | 2119 | 5 | 950 | 232 | 90
2018-09-25 | 2173 | 5 | 987 | 160 | 166
2018-09-25 | 2051 | 5 | 923 | 283 | 94
2018-09-25 | 2098 | 5 | 927 | 220 | 118
2018-09-25 | 2134 | 5 | 949 | 258 | 156
2018-09-26 | 1929 | 5 | 890 | 187 | 128
2018-09-26 | 2123 | 5 | 981 | 87 | 208
2018-09-26 | 2079 | 5 | 921 | 224 | 98
2018-09-26 | 2132 | 5 | 961 | 145 | 130
2018-09-27 | 2156 | 5 | 964 | 170 | 129
2018-09-27 | 2105 | 5 | 942 | 220 | 166
2018-09-27 | 1927 | 5 | 896 | 133 | 172
2018-09-27 | 2219 | 5 | 949 | 166 | 111
2018-09-27 | 2041 | 5 | 953 | 311 | 98
2018-09-27 | 2079 | 5 | 913 | 166 | 135
2018-09-27 | 1934 | 5 | 905 | 264 | 78
2018-09-27 | 2079 | 5 | 958 | 279 | 128
2018-09-27 | 2101 | 5 | 957 | 292 | 100
2018-09-27 | 2058 | 5 | 939 | 212 | 143
2018-09-27 | 2240 | 5 | 965 | 184 | 125
2018-09-27 | 2176 | 5 | 967 | 205 | 190
2018-09-28 | 2071 | 5 | 927 | 144 | 160
2018-09-28 | 1985 | 5 | 953 | 325 | 141
2018-09-28 | 2009 | 5 | 918 | 283 | 122
2018-09-28 | 2063 | 5 | 893 | 239 | 134
2018-09-28 | 2115 | 5 | 954 | 158 | 187
2018-09-28 | 2126 | 5 | 924 | 186 | 96
2018-09-28 | 1978 | 5 | 898 | 244 | 96
2018-09-28 | 2230 | 5 | 986 | 264 | 129
2018-09-28 | 2239 | 5 | 1003 | 178 | 155
2018-10-02 | 2167 | 5 | 961 | 235 | 187
2018-10-02 | 2022 | 5 | 922 | 290 | 98
2018-10-03 | 2106 | 5 | 929 | 242 | 142
2018-10-04 | 2039 | 5 | 946 | 225 | 127
2018-10-04 | 2090 | 5 | 964 | 212 | 115
2018-10-04 | 2081 | 5 | 955 | 263 | 143
2018-10-05 | 2103 | 5 | 889 | 105 | 206
2018-10-05 | 2181 | 5 | 990 | 232 | 134
2018-10-05 | 2073 | 5 | 936 | 297 | 74
2018-10-05 | 1945 | 5 | 919 | 220 | 140
2018-10-08 | 2311 | 5 | 994 | 300 | 149
2018-10-08 | 2169 | 5 | 1006 | 283 | 120
2018-10-08 | 2187 | 5 | 947 | 195 | 155
2018-10-08 | 2123 | 5 | 932 | 171 | 125
2018-10-08 | 2083 | 5 | 970 | 226 | 137
2018-10-08 | 2217 | 5 | 946 | 170 | 136
2018-10-09 | 2053 | 5 | 972 | 397 | 103
2018-10-09 | 2161 | 5 | 958 | 213 | 137
2018-10-09 | 2190 | 5 | 986 | 227 | 116
2018-10-10 | 2057 | 5 | 910 | 216 | 107
2018-10-10 | 2270 | 5 | 978 | 350 | 112
2018-10-11 | 2097 | 5 | 945 | 283 | 115
2018-10-11 | 2094 | 5 | 986 | 294 | 139
2018-10-11 | 1974 | 5 | 924 | 320 | 121
2018-10-11 | 2200 | 5 | 967 | 212 | 134
2018-10-11 | 2109 | 5 | 951 | 231 | 129
2018-10-11 | 2119 | 5 | 958 | 387 | 48
2018-10-12 | 2209 | 5 | 958 | 301 | 88
2018-10-12 | 2143 | 5 | 912 | 86 | 182
2018-10-12 | 2125 | 5 | 963 | 141 | 198
2018-10-12 | 2236 | 5 | 1032 | 294 | 161
2018-10-12 | 2209 | 5 | 1000 | 309 | 139
2018-10-15 | 2042 | 5 | 968 | 313 | 165
2018-10-15 | 2171 | 5 | 974 | 288 | 120
2018-10-15 | 2082 | 5 | 930 | 251 | 176
2018-10-15 | 2066 | 5 | 953 | 233 | 130
2018-10-15 | 2309 | 5 | 994 | 271 | 136
2018-10-15 | 2165 | 5 | 942 | 168 | 134
2018-10-15 | 2177 | 5 | 998 | 226 | 143
2018-10-15 | 2262 | 5 | 966 | 234 | 135
2018-10-15 | 2089 | 5 | 934 | 158 | 154
2018-10-15 | 2088 | 5 | 975 | 312 | 171
2018-10-15 | 2172 | 5 | 935 | 234 | 96
2018-10-15 | 2234 | 5 | 989 | 336 | 133
2018-10-16 | 2377 | 5 | 1015 | 186 | 167
2018-10-16 | 2313 | 5 | 979 | 180 | 167
2018-10-16 | 2165 | 5 | 970 | 348 | 103
2018-10-16 | 2176 | 5 | 957 | 198 | 152
2018-10-16 | 2132 | 5 | 966 | 282 | 181
2018-10-16 | 2179 | 5 | 948 | 185 | 146
2018-10-17 | 2226 | 5 | 984 | 224 | 185
2018-10-17 | 2216 | 5 | 990 | 294 | 81
2018-10-17 | 2342 | 5 | 1005 | 203 | 166
2018-10-18 | 2212 | 5 | 954 | 210 | 125
2018-10-18 | 2125 | 5 | 979 | 298 | 105
2018-10-18 | 2211 | 5 | 1002 | 254 | 196
2018-10-18 | 2256 | 5 | 981 | 300 | 189
2018-10-18 | 2294 | 5 | 1025 | 255 | 153
2018-10-18 | 2192 | 5 | 970 | 237 | 136
2018-10-19 | 2151 | 5 | 978 | 316 | 134
2018-10-19 | 2244 | 5 | 988 | 204 | 166
2018-10-19 | 2265 | 5 | 1000 | 286 | 137
2018-10-19 | 2259 | 5 | 985 | 175 | 224
2018-10-19 | 2184 | 5 | 912 | 194 | 166
2018-10-19 | 2332 | 5 | 986 | 242 | 141
2018-10-19 | 2158 | 5 | 966 | 166 | 183
2018-10-19 | 2283 | 5 | 955 | 179 | 140
2018-10-19 | 2166 | 5 | 968 | 247 | 111
2018-10-19 | 2159 | 5 | 998 | 257 | 186
2018-10-19 | 2204 | 5 | 978 | 218 | 199
2018-10-19 | 2297 | 5 | 976 | 238 | 146
2018-10-19 | 2316 | 5 | 973 | 233 | 129
2018-10-19 | 2225 | 5 | 961 | 213 | 155
2018-10-22 | 2291 | 5 | 981 | 154 | 168
2018-10-22 | 2126 | 5 | 957 | 244 | 164
2018-10-22 | 2196 | 5 | 969 | 353 | 109
2018-10-22 | 2271 | 5 | 987 | 226 | 167
2018-10-22 | 2310 | 5 | 975 | 208 | 142
2018-10-23 | 2365 | 5 | 1006 | 198 | 153
2018-10-23 | 2190 | 5 | 956 | 249 | 146
2018-10-23 | 2272 | 5 | 975 | 156 | 170
2018-10-23 | 2207 | 5 | 937 | 204 | 115
2018-10-23 | 2359 | 5 | 1006 | 319 | 117
2018-10-23 | 2359 | 5 | 1006 | 288 | 104
2018-10-23 | 2242 | 5 | 984 | 219 | 121
2018-10-23 | 2138 | 5 | 976 | 205 | 153
2018-10-23 | 2125 | 5 | 920 | 241 | 98
2018-10-24 | 2305 | 5 | 975 | 315 | 127
2018-10-24 | 2093 | 5 | 979 | 408 | 127
2018-10-24 | 2070 | 5 | 969 | 297 | 145
2018-10-24 | 2208 | 5 | 959 | 156 | 174
2018-10-24 | 2239 | 5 | 1000 | 293 | 136
2018-10-24 | 2354 | 5 | 1036 | 285 | 173
2018-10-24 | 2366 | 5 | 986 | 150 | 197
2018-10-24 | 2381 | 5 | 1017 | 276 | 162
2018-10-24 | 2268 | 5 | 952 | 211 | 154
2018-10-25 | 2337 | 5 | 1004 | 283 | 151
2018-10-25 | 2289 | 5 | 975 | 225 | 113
2018-10-25 | 2376 | 5 | 1040 | 329 | 153
2018-10-25 | 2371 | 5 | 1039 | 345 | 122
2018-10-25 | 2211 | 5 | 952 | 113 | 159
2018-10-25 | 2118 | 5 | 924 | 270 | 162
2018-10-25 | 2397 | 5 | 1037 | 318 | 124
2018-10-26 | 2257 | 5 | 992 | 259 | 167
2018-10-26 | 2327 | 5 | 1004 | 244 | 124
2018-10-26 | 2315 | 5 | 993 | 265 | 178
2018-10-26 | 2200 | 5 | 997 | 312 | 118
2018-10-26 | 2252 | 5 | 958 | 257 | 153
2018-10-26 | 2326 | 5 | 1041 | 386 | 131
2018-10-26 | 2259 | 5 | 976 | 189 | 171
2018-10-26 | 2282 | 5 | 972 | 302 | 127
2018-10-26 | 2262 | 5 | 991 | 224 | 131
2018-10-26 | 2160 | 5 | 942 | 223 | 125
2018-10-26 | 2215 | 5 | 973 | 252 | 199
2018-10-26 | 2182 | 5 | 954 | 225 | 124
2018-10-29 | 2361 | 5 | 1042 | 215 | 225
2018-10-29 | 2380 | 5 | 1033 | 333 | 111
2018-10-30 | 2218 | 5 | 985 | 210 | 173
2018-10-31 | 2211 | 5 | 991 | 183 | 183
2018-10-31 | 2306 | 5 | 984 | 264 | 184
2018-11-01 | 2310 | 5 | 1011 | 290 | 162
2018-11-02 | 2410 | 5 | 1020 | 178 | 210
2018-11-02 | 2383 | 5 | 1000 | 319 | 164
2018-11-02 | 2284 | 5 | 1006 | 368 | 115
2018-11-05 | 2329 | 5 | 1021 | 281 | 156
2018-11-06 | 2331 | 5 | 1010 | 206 | 209
2018-11-06 | 2320 | 5 | 1015 | 309 | 217
2018-11-06 | 2469 | 5 | 1042 | 295 | 196
2018-11-06 | 2265 | 5 | 1025 | 313 | 152
2018-11-06 | 2344 | 5 | 1028 | 232 | 157
2018-11-07 | 2498 | 5 | 1022 | 260 | 184
2018-11-07 | 2349 | 5 | 1022 | 260 | 143
2018-11-07 | 2364 | 5 | 998 | 270 | 186
2018-11-08 | 2386 | 5 | 1030 | 255 | 178
2018-11-08 | 2280 | 5 | 995 | 264 | 125
2018-11-09 | 2337 | 5 | 1032 | 313 | 215
2018-11-09 | 2318 | 5 | 1006 | 368 | 194
2018-11-09 | 2407 | 5 | 1035 | 334 | 150
2018-11-09 | 2398 | 5 | 1015 | 309 | 187
2018-11-12 | 2380 | 5 | 1026 | 302 | 168
2018-11-12 | 2429 | 5 | 1017 | 297 | 190
2018-11-13 | 2508 | 5 | 1023 | 282 | 158
2018-11-13 | 2295 | 5 | 989 | 231 | 170
2018-11-13 | 2253 | 5 | 988 | 344 | 192
2018-11-13 | 2392 | 5 | 1008 | 231 | 147
2018-11-13 | 2488 | 5 | 1019 | 286 | 146
2018-11-13 | 2617 | 5 | 1053 | 218 | 161
2018-11-13 | 2511 | 5 | 1066 | 261 | 170
2018-11-13 | 2543 | 5 | 1081 | 280 | 187
2018-11-14 | 2288 | 5 | 973 | 225 | 156
2018-11-14 | 2408 | 5 | 1006 | 332 | 166
2018-11-14 | 2400 | 5 | 1025 | 228 | 202
2018-11-14 | 2463 | 5 | 1029 | 272 | 153
2018-11-14 | 2378 | 5 | 1023 | 222 | 214
2018-11-14 | 2458 | 5 | 1019 | 238 | 205
2018-11-14 | 2566 | 5 | 1028 | 244 | 176
2018-11-15 | 2432 | 5 | 999 | 287 | 198
2018-11-15 | 2466 | 5 | 1014 | 233 | 189
2018-11-15 | 2451 | 5 | 1009 | 231 | 157
2018-11-15 | 2488 | 5 | 1030 | 187 | 176
2018-11-15 | 2541 | 5 | 1035 | 267 | 164
2018-11-15 | 2328 | 5 | 986 | 266 | 234
2018-11-16 | 2266 | 5 | 998 | 366 | 164
2018-11-16 | 2479 | 5 | 1046 | 243 | 172
2018-11-16 | 2454 | 5 | 1050 | 390 | 152
2018-11-16 | 2330 | 5 | 1005 | 223 | 233
2018-11-16 | 2344 | 5 | 1006 | 315 | 145
2018-11-16 | 2393 | 5 | 1058 | 385 | 132
2018-11-16 | 2528 | 5 | 1079 | 210 | 214
2018-11-19 | 2377 | 5 | 991 | 274 | 149
2018-11-19 | 2438 | 5 | 1053 | 288 | 154
2018-11-19 | 2609 | 5 | 1062 | 245 | 220
2018-11-20 | 2487 | 5 | 1061 | 361 | 159
2018-11-20 | 2349 | 5 | 996 | 298 | 144
2018-11-20 | 2404 | 5 | 1023 | 382 | 118
2018-11-20 | 2486 | 5 | 1029 | 258 | 164
2018-11-20 | 2279 | 5 | 1009 | 324 | 133
2018-11-20 | 2374 | 5 | 1009 | 192 | 194
2018-11-20 | 2481 | 5 | 1035 | 186 | 233
2018-11-21 | 2537 | 5 | 1067 | 335 | 119
2018-11-21 | 2345 | 5 | 991 | 188 | 193
2018-11-21 | 2483 | 5 | 1025 | 281 | 162
2018-11-21 | 2449 | 5 | 1101 | 336 | 181
2018-11-21 | 2427 | 5 | 1045 | 312 | 153
2018-11-21 | 2449 | 5 | 1018 | 160 | 221
2018-11-21 | 2481 | 5 | 1055 | 350 | 191
2018-11-21 | 2402 | 5 | 1025 | 177 | 236
2018-11-22 | 2453 | 5 | 1031 | 237 | 169
2018-11-22 | 2358 | 5 | 1002 | 292 | 196
2018-11-22 | 2516 | 5 | 1094 | 267 | 184
2018-11-22 | 2618 | 5 | 1067 | 281 | 166
2018-11-22 | 2516 | 5 | 1043 | 328 | 160
2018-11-22 | 2424 | 5 | 994 | 232 | 192
2018-11-22 | 2332 | 5 | 1019 | 300 | 196
2018-11-23 | 2492 | 5 | 1029 | 218 | 179
2018-11-23 | 2426 | 5 | 1022 | 262 | 146
2018-11-23 | 2542 | 5 | 1077 | 389 | 159
2018-11-23 | 2417 | 5 | 1033 | 395 | 131
2018-11-23 | 2467 | 5 | 1038 | 265 | 183
2018-11-23 | 2494 | 5 | 1030 | 244 | 163
2018-11-23 | 2599 | 5 | 1029 | 238 | 200
2018-11-23 | 2620 | 5 | 1106 | 287 | 187
2018-11-23 | 2488 | 5 | 1047 | 297 | 192
2018-11-23 | 2530 | 5 | 1060 | 225 | 226
2018-11-23 | 2452 | 5 | 1013 | 217 | 167
2018-11-26 | 2501 | 5 | 1052 | 374 | 141
2018-11-26 | 2481 | 5 | 1021 | 241 | 189
2018-11-27 | 2455 | 5 | 1016 | 264 | 134
2018-11-29 | 2461 | 5 | 1067 | 389 | 174
2018-11-29 | 2423 | 5 | 1073 | 296 | 183
2018-11-29 | 2440 | 5 | 1052 | 378 | 174
2018-11-30 | 2339 | 5 | 1044 | 238 | 159
2018-11-30 | 2649 | 5 | 1065 | 269 | 177
2018-12-03 | 2542 | 5 | 1090 | 348 | 203
2018-12-03 | 2521 | 5 | 1079 | 400 | 140
2018-12-03 | 2640 | 5 | 1091 | 323 | 190
2018-12-04 | 2545 | 5 | 1095 | 254 | 187
2018-12-04 | 2449 | 5 | 1047 | 286 | 193
2018-12-04 | 2658 | 5 | 1110 | 266 | 243
2018-12-05 | 2605 | 5 | 1081 | 259 | 199
2018-12-05 | 2549 | 5 | 1046 | 271 | 202
2018-12-05 | 2619 | 5 | 1070 | 362 | 111
2018-12-06 | 2412 | 5 | 1051 | 351 | 184
2018-12-10 | 2421 | 5 | 1051 | 412 | 139
2018-12-11 | 2357 | 5 | 994 | 290 | 180
2018-12-11 | 2636 | 5 | 1111 | 365 | 178
2018-12-11 | 2661 | 5 | 1094 | 264 | 237
2018-12-11 | 2791 | 5 | 1106 | 301 | 160
2018-12-12 | 2649 | 5 | 1070 | 336 | 201
2018-12-12 | 2491 | 5 | 1059 | 309 | 199
2018-12-12 | 2708 | 5 | 1059 | 354 | 154
2018-12-12 | 2643 | 5 | 1080 | 285 | 209
2018-12-13 | 2424 | 5 | 1027 | 408 | 166
2018-12-13 | 2614 | 5 | 1099 | 313 | 229
2018-12-13 | 2495 | 5 | 1067 | 366 | 204
2018-12-13 | 2671 | 5 | 1082 | 338 | 175
2018-12-13 | 2680 | 5 | 1102 | 289 | 228
2018-12-14 | 2630 | 5 | 1082 | 359 | 165
2018-12-14 | 2730 | 5 | 1104 | 306 | 208
2018-12-14 | 2828 | 5 | 1142 | 374 | 190
2018-12-14 | 2692 | 5 | 1090 | 318 | 217
2018-12-14 | 2554 | 5 | 1068 | 266 | 237
2018-12-14 | 2529 | 5 | 1054 | 225 | 275
2018-12-17 | 2665 | 5 | 1109 | 399 | 138
2018-12-17 | 2705 | 5 | 1125 | 341 | 203
2018-12-17 | 2779 | 5 | 1129 | 249 | 256
2018-12-17 | 2698 | 5 | 1090 | 230 | 191
2018-12-18 | 2556 | 5 | 1057 | 346 | 182
2018-12-18 | 2504 | 5 | 1044 | 332 | 181
2018-12-18 | 2714 | 5 | 1075 | 178 | 193
2018-12-18 | 2525 | 5 | 1086 | 336 | 211
2018-12-18 | 2708 | 5 | 1054 | 197 | 217
2018-12-18 | 2408 | 5 | 1056 | 386 | 203
2018-12-18 | 2653 | 5 | 1077 | 335 | 203
2018-12-18 | 2554 | 5 | 1088 | 307 | 250
2018-12-18 | 2721 | 5 | 1115 | 395 | 224
2018-12-18 | 2546 | 5 | 1082 | 358 | 219
2018-12-19 | 2420 | 5 | 1060 | 440 | 160
2018-12-19 | 2608 | 5 | 1071 | 262 | 205
2018-12-19 | 2860 | 5 | 1169 | 344 | 178
2018-12-20 | 2619 | 5 | 1098 | 434 | 179
2018-12-20 | 2749 | 5 | 1131 | 325 | 194
2018-12-20 | 2681 | 5 | 1066 | 358 | 182
2018-12-20 | 2818 | 5 | 1131 | 260 | 230
2018-12-20 | 2611 | 5 | 1057 | 326 | 137
2018-12-20 | 2540 | 5 | 1071 | 388 | 196
2018-12-20 | 2935 | 5 | 1157 | 291 | 211
2018-12-21 | 2685 | 5 | 1078 | 269 | 192
2018-12-21 | 2717 | 5 | 1096 | 240 | 260
2018-12-21 | 2621 | 5 | 1091 | 394 | 144
2018-12-21 | 2606 | 5 | 1024 | 235 | 221
2018-12-21 | 2764 | 5 | 1086 | 181 | 224
2018-12-21 | 2558 | 5 | 1043 | 288 | 148
2018-12-21 | 2664 | 5 | 1088 | 279 | 215
2018-12-21 | 2649 | 5 | 1100 | 296 | 245
2018-12-21 | 2549 | 5 | 1067 | 409 | 152
2018-12-21 | 2772 | 5 | 1134 | 309 | 178
2018-12-24 | 2617 | 5 | 1061 | 276 | 231
2018-12-25 | 2650 | 5 | 1123 | 471 | 166
2018-12-25 | 2698 | 5 | 1113 | 341 | 167
2018-12-25 | 2710 | 5 | 1110 | 323 | 237
2018-12-26 | 2747 | 5 | 1116 | 505 | 151
2018-12-27 | 2747 | 5 | 1129 | 424 | 209
2018-12-27 | 2621 | 5 | 1064 | 331 | 211
2018-12-27 | 2720 | 5 | 1066 | 325 | 134
2018-12-28 | 2646 | 5 | 1083 | 353 | 185
2018-12-28 | 2573 | 5 | 1052 | 242 | 209
2018-12-31 | 2572 | 5 | 1053 | 252 | 220
2018-12-31 | 2734 | 5 | 1058 | 188 | 253
2018-12-31 | 2792 | 5 | 1134 | 355 | 222
2019-01-01 | 2621 | 5 | 1068 | 178 | 236
2019-01-01 | 2755 | 5 | 1110 | 293 | 220
2019-01-01 | 2596 | 5 | 1064 | 334 | 165
2019-01-02 | 2810 | 5 | 1153 | 355 | 214
2019-01-02 | 2738 | 5 | 1108 | 282 | 202
2019-01-02 | 2646 | 5 | 1089 | 354 | 220
2019-01-02 | 2666 | 5 | 1094 | 467 | 161
2019-01-03 | 2693 | 5 | 1103 | 266 | 262
2019-01-03 | 2727 | 5 | 1122 | 452 | 160
2019-01-04 | 2705 | 5 | 1116 | 380 | 198
2019-01-07 | 2744 | 5 | 1068 | 315 | 251
2019-01-07 | 2684 | 5 | 1090 | 306 | 176
2019-01-07 | 2795 | 5 | 1134 | 334 | 225
2019-01-07 | 2729 | 5 | 1114 | 312 | 211
2019-01-08 | 2715 | 5 | 1111 | 326 | 190
2019-01-08 | 2857 | 5 | 1153 | 323 | 214
2019-01-09 | 3018 | 5 | 1200 | 432 | 200
2019-01-09 | 2872 | 5 | 1128 | 264 | 191
2019-01-09 | 2717 | 5 | 1073 | 292 | 226
2019-01-10 | 2614 | 5 | 1028 | 302 | 194
2019-01-10 | 2867 | 5 | 1135 | 313 | 202
2019-01-11 | 2849 | 5 | 1125 | 273 | 226
2019-01-11 | 2764 | 5 | 1118 | 373 | 215
2019-01-14 | 2800 | 5 | 1120 | 302 | 230
2019-01-15 | 2922 | 5 | 1141 | 352 | 161
2019-01-15 | 2728 | 5 | 1080 | 303 | 209
2019-01-15 | 3003 | 5 | 1160 | 401 | 183
2019-01-15 | 2828 | 5 | 1157 | 359 | 247
2019-01-16 | 2773 | 5 | 1129 | 379 | 217
2019-01-17 | 2958 | 5 | 1194 | 411 | 201
2019-01-17 | 2860 | 5 | 1143 | 284 | 266
2019-01-17 | 2815 | 5 | 1135 | 378 | 225
2019-01-17 | 2817 | 5 | 1125 | 459 | 175
2019-01-17 | 2811 | 5 | 1111 | 368 | 173
2019-01-17 | 2604 | 5 | 1109 | 483 | 149
2019-01-18 | 2973 | 5 | 1169 | 354 | 264
2019-01-18 | 2810 | 5 | 1119 | 421 | 239
2019-01-18 | 2924 | 5 | 1163 | 382 | 236
2019-01-18 | 3006 | 5 | 1153 | 329 | 238
2019-01-18 | 2789 | 5 | 1089 | 351 | 197
2019-01-18 | 3062 | 5 | 1211 | 394 | 217
2019-01-22 | 2749 | 5 | 1139 | 382 | 203
2019-01-23 | 2848 | 5 | 1142 | 296 | 209
2019-01-25 | 2960 | 5 | 1160 | 242 | 258
2019-01-25 | 2858 | 5 | 1078 | 331 | 216
2019-01-25 | 2903 | 5 | 1115 | 194 | 263
2019-01-28 | 2710 | 5 | 1122 | 407 | 152
2019-01-28 | 2908 | 5 | 1157 | 301 | 267
2019-01-28 | 2857 | 5 | 1153 | 411 | 212
2019-01-29 | 2824 | 5 | 1127 | 380 | 215
2019-01-29 | 2989 | 5 | 1170 | 350 | 221
2019-01-30 | 2943 | 5 | 1167 | 359 | 251
2019-01-31 | 2840 | 5 | 1129 | 402 | 220
2019-02-01 | 2902 | 5 | 1139 | 312 | 247
2019-02-04 | 2988 | 5 | 1163 | 333 | 301
2019-02-05 | 2961 | 5 | 1170 | 407 | 226
2019-02-05 | 3003 | 5 | 1165 | 305 | 265
2019-02-05 | 2928 | 5 | 1168 | 470 | 227
2019-02-05 | 3027 | 5 | 1189 | 395 | 174
2019-02-05 | 3037 | 5 | 1186 | 299 | 300
2019-02-06 | 2988 | 5 | 1138 | 295 | 237
2019-02-06 | 3004 | 5 | 1179 | 395 | 160
2019-02-06 | 3017 | 5 | 1186 | 298 | 234
2019-02-06 | 3002 | 5 | 1172 | 319 | 198
2019-02-06 | 2958 | 5 | 1140 | 268 | 236
2019-02-07 | 3182 | 5 | 1218 | 424 | 201
2019-02-07 | 2864 | 5 | 1117 | 482 | 191
2019-02-08 | 2839 | 5 | 1117 | 325 | 275
2019-02-11 | 3236 | 5 | 1195 | 325 | 240
2019-02-11 | 2906 | 5 | 1158 | 370 | 238
2019-02-11 | 2969 | 5 | 1221 | 576 | 174
2019-02-11 | 2948 | 5 | 1180 | 482 | 233
2019-02-11 | 3034 | 5 | 1220 | 352 | 311
2019-02-12 | 2996 | 5 | 1172 | 365 | 238
2019-02-12 | 3044 | 5 | 1227 | 397 | 268
2019-02-12 | 2945 | 5 | 1152 | 401 | 213
2019-02-13 | 2959 | 5 | 1158 | 416 | 209
2019-02-13 | 3140 | 5 | 1205 | 398 | 291
2019-02-14 | 2983 | 5 | 1186 | 417 | 218
2019-02-14 | 2946 | 5 | 1185 | 427 | 228
2019-02-14 | 3083 | 5 | 1207 | 447 | 253
2019-02-15 | 3175 | 5 | 1250 | 480 | 229
2019-02-15 | 3075 | 5 | 1199 | 503 | 189
2019-02-15 | 2943 | 5 | 1189 | 431 | 238
2019-02-15 | 3148 | 5 | 1181 | 326 | 301
2019-02-18 | 3114 | 5 | 1155 | 377 | 217
2019-02-18 | 2965 | 5 | 1188 | 509 | 208
2019-02-19 | 3089 | 5 | 1181 | 243 | 264
2019-02-19 | 3042 | 5 | 1158 | 345 | 210
2019-02-20 | 3046 | 5 | 1182 | 424 | 196
2019-02-20 | 3150 | 5 | 1198 | 404 | 194
2019-02-21 | 3181 | 5 | 1209 | 308 | 320
2019-02-22 | 3139 | 5 | 1204 | 429 | 232
2019-02-22 | 3241 | 5 | 1246 | 441 | 287
2019-02-26 | 2820 | 5 | 1160 | 463 | 234
2019-02-27 | 3177 | 5 | 1202 | 437 | 217
2019-02-27 | 3172 | 5 | 1247 | 474 | 260
2019-02-28 | 3007 | 5 | 1196 | 470 | 239
2019-02-28 | 3326 | 5 | 1251 | 432 | 276
2019-02-28 | 3243 | 5 | 1246 | 454 | 262
2019-03-04 | 3082 | 5 | 1236 | 549 | 249
2019-03-05 | 3214 | 5 | 1189 | 367 | 226
2019-03-05 | 3327 | 5 | 1231 | 363 | 277
2019-03-05 | 3236 | 5 | 1221 | 455 | 241
2019-03-05 | 3123 | 5 | 1211 | 406 | 265
2019-03-06 | 3115 | 5 | 1202 | 433 | 329
2019-03-06 | 3153 | 5 | 1231 | 427 | 223
2019-03-06 | 3170 | 5 | 1207 | 395 | 264
2019-03-07 | 2934 | 5 | 1175 | 377 | 272
2019-03-07 | 3084 | 5 | 1231 | 438 | 326
2019-03-07 | 3068 | 5 | 1171 | 343 | 196
2019-03-07 | 3156 | 5 | 1254 | 530 | 199
2019-03-08 | 3066 | 5 | 1170 | 297 | 318
2019-03-08 | 3215 | 5 | 1191 | 428 | 212
2019-03-11 | 3292 | 5 | 1276 | 375 | 345
2019-03-11 | 3202 | 5 | 1218 | 312 | 282
2019-03-11 | 2958 | 5 | 1195 | 524 | 210
2019-03-11 | 3299 | 5 | 1282 | 478 | 296
2019-03-12 | 3208 | 5 | 1219 | 418 | 252
2019-03-12 | 3129 | 5 | 1211 | 463 | 198
2019-03-13 | 3208 | 5 | 1225 | 379 | 287
2019-03-13 | 3238 | 5 | 1256 | 419 | 337
2019-03-13 | 3229 | 5 | 1238 | 426 | 273
2019-03-14 | 3235 | 5 | 1206 | 374 | 280
2019-03-15 | 3183 | 5 | 1223 | 334 | 321
2019-03-15 | 3306 | 5 | 1274 | 608 | 258
2019-03-15 | 3176 | 5 | 1229 | 525 | 180
2019-03-15 | 3389 | 5 | 1291 | 445 | 199
2019-03-15 | 3175 | 5 | 1233 | 436 | 276
2019-03-15 | 3397 | 5 | 1241 | 319 | 302
2019-03-18 | 3175 | 5 | 1211 | 373 | 266
2019-03-19 | 3129 | 5 | 1227 | 552 | 205
2019-03-20 | 3496 | 5 | 1302 | 433 | 265
2019-03-25 | 3285 | 5 | 1266 | 543 | 198
2019-03-25 | 3175 | 5 | 1236 | 409 | 192
2019-03-25 | 3318 | 5 | 1285 | 525 | 291
2019-03-25 | 3408 | 5 | 1269 | 498 | 222
2019-03-26 | 3351 | 5 | 1285 | 525 | 235
2019-03-26 | 3458 | 5 | 1309 | 424 | 323
2019-03-29 | 3446 | 5 | 1282 | 399 | 250
2019-04-02 | 3473 | 5 | 1285 | 409 | 329
2019-04-02 | 3458 | 5 | 1289 | 472 | 254
2019-04-02 | 3386 | 5 | 1276 | 418 | 289
2019-04-02 | 3376 | 5 | 1271 | 465 | 224
2019-04-03 | 3345 | 5 | 1240 | 347 | 296
2019-04-04 | 3339 | 5 | 1290 | 552 | 249
2019-04-04 | 3262 | 5 | 1243 | 497 | 244
2019-04-04 | 3341 | 5 | 1280 | 451 | 329
2019-04-04 | 3281 | 5 | 1227 | 444 | 246
2019-04-05 | 3253 | 5 | 1269 | 574 | 240
2019-04-05 | 3368 | 5 | 1272 | 404 | 311
2019-04-05 | 3508 | 5 | 1309 | 392 | 249
2019-04-08 | 3480 | 5 | 1326 | 465 | 272
2019-04-08 | 3265 | 5 | 1231 | 359 | 300
2019-04-08 | 3245 | 5 | 1249 | 465 | 325
2019-04-08 | 3308 | 5 | 1257 | 436 | 267
2019-04-09 | 3351 | 5 | 1266 | 410 | 276
2019-04-10 | 3280 | 5 | 1234 | 365 | 271
2019-04-10 | 3341 | 5 | 1281 | 429 | 276
2019-04-10 | 3436 | 5 | 1293 | 485 | 244
2019-04-10 | 3604 | 5 | 1372 | 550 | 315
2019-04-11 | 3574 | 5 | 1349 | 517 | 313
2019-04-12 | 3681 | 5 | 1355 | 470 | 350
2019-04-12 | 3302 | 5 | 1247 | 531 | 279
2019-04-12 | 3387 | 5 | 1300 | 566 | 356
2019-04-16 | 3385 | 5 | 1310 | 516 | 299
2019-04-22 | 3428 | 5 | 1299 | 515 | 359
2019-04-22 | 3362 | 5 | 1268 | 445 | 247
2019-04-23 | 3452 | 5 | 1306 | 384 | 363
2019-04-24 | 3582 | 5 | 1324 | 443 | 325
2019-04-24 | 3592 | 5 | 1329 | 460 | 318
2019-04-25 | 3556 | 5 | 1300 | 369 | 317
2019-04-25 | 3496 | 5 | 1284 | 412 | 322
2019-04-25 | 3731 | 5 | 1339 | 423 | 325
2019-04-26 | 3404 | 5 | 1285 | 437 | 330
2019-05-01 | 3584 | 5 | 1309 | 416 | 269
2019-05-02 | 3578 | 5 | 1321 | 470 | 333
2019-05-02 | 3487 | 5 | 1272 | 544 | 258
2019-05-03 | 3618 | 5 | 1356 | 500 | 323
2019-05-06 | 3554 | 5 | 1294 | 382 | 270
2019-05-07 | 3623 | 5 | 1328 | 616 | 208
2019-05-09 | 3557 | 5 | 1324 | 584 | 266
2019-05-10 | 3601 | 5 | 1312 | 477 | 285
2019-05-10 | 3599 | 5 | 1309 | 479 | 308
2019-05-10 | 3756 | 5 | 1388 | 547 | 288
2019-05-13 | 3774 | 5 | 1339 | 429 | 308
2019-05-21 | 3741 | 5 | 1389 | 452 | 376
2019-05-24 | 3763 | 5 | 1399 | 621 | 264
2019-05-27 | 3657 | 5 | 1361 | 527 | 329
2019-05-27 | 3783 | 5 | 1375 | 557 | 270
2019-05-28 | 3748 | 5 | 1363 | 549 | 286
2019-05-29 | 3711 | 5 | 1312 | 405 | 338
2019-05-30 | 3819 | 5 | 1408 | 554 | 338
2019-06-06 | 3764 | 5 | 1374 | 490 | 336
2019-06-07 | 3831 | 5 | 1393 | 612 | 270
2019-06-14 | 3917 | 5 | 1418 | 488 | 295
2019-06-14 | 3728 | 5 | 1384 | 550 | 295
2019-06-18 | 3935 | 5 | 1407 | 352 | 423
2019-06-19 | 4018 | 5 | 1448 | 561 | 295
2019-06-21 | 3968 | 5 | 1405 | 478 | 329
2019-06-24 | 3912 | 5 | 1433 | 653 | 315
2019-06-25 | 3888 | 5 | 1360 | 455 | 364
2019-06-27 | 3881 | 5 | 1453 | 797 | 323
2019-06-28 | 3984 | 5 | 1425 | 610 | 289
2019-06-28 | 3795 | 5 | 1335 | 412 | 317
2019-06-28 | 4028 | 5 | 1400 | 578 | 252
2019-07-01 | 4006 | 5 | 1452 | 601 | 378
2019-07-02 | 4074 | 5 | 1434 | 472 | 264
2019-07-03 | 4001 | 5 | 1437 | 499 | 400
2019-07-03 | 3964 | 5 | 1379 | 310 | 400
2019-07-11 | 4019 | 5 | 1431 | 391 | 382
2019-07-17 | 4122 | 5 | 1449 | 479 | 426
2019-07-19 | 4172 | 5 | 1471 | 596 | 358
2019-07-22 | 4039 | 5 | 1439 | 642 | 324
2019-07-23 | 4227 | 5 | 1480 | 536 | 393
2019-07-26 | 4303 | 5 | 1488 | 414 | 405
2019-07-26 | 4138 | 5 | 1457 | 480 | 377
2019-07-31 | 4048 | 5 | 1489 | 708 | 384
2019-08-01 | 4250 | 5 | 1492 | 531 | 369
2019-08-02 | 4242 | 5 | 1489 | 619 | 331
2019-08-06 | 4223 | 5 | 1501 | 609 | 412
2019-08-14 | 4283 | 5 | 1474 | 621 | 340
2019-08-23 | 4117 | 5 | 1491 | 693 | 311
2019-08-29 | 4363 | 5 | 1531 | 592 | 420
2019-09-06 | 4330 | 5 | 1529 | 563 | 446
2019-09-20 | 4384 | 5 | 1558 | 775 | 368
Project ran out of time | 4490 | 5 | 1571 | 679 | 417
Project ran out of time | 4644 | 5 | 1570 | 597 | 440
Project ran out of time | 4677 | 5 | 1593 | 624 | 465
Project ran out of time | 4370 | 5 | 1519 | 634 | 448
Project ran out of time | 4715 | 5 | 1643 | 867 | 372
Project ran out of time | 4775 | 5 | 1602 | 663 | 404
Project ran out of time | 4566 | 5 | 1572 | 565 | 442
Project ran out of time | 4380 | 5 | 1565 | 653 | 464
Project ran out of time | 4728 | 5 | 1624 | 813 | 486
Project ran out of time | 4440 | 5 | 1566 | 810 | 398
Project ran out of time | 4359 | 5 | 1527 | 665 | 464