## Dummy Data
Generating example Agile data
| Exactly | From | Weighting for randomisation | To | Randomised
Start date | 2017-12-04 |  |  |  |  | CumuFlow table
X number of initial stories | 20 |  |  |  |  | Issue | Defining | Ready | In Progress | Review | Done
X people in team | 5 |  |  |  |  | ID#1 | 2017-12-04 |  | 2017-12-06 | 2017-12-15
Getting a story to "Ready" takes X hours |  | 4 | -¦----- | 16 | Per story | ID#2 | 2017-12-04 |  | 2017-12-06 |  | 2018-01-02
Each story is "In Progress" for X hours |  | 8 | ---¦--- | 80 | Per story | ID#3 | 2017-11-23 | 2017-11-28
Each story is in "Review" for X hours |  | 2 | -¦----- | 8 | Per story | ID#4 | 2017-10-17 | 2017-10-17 | 2017-12-04 |  | 2018-01-02
X% chance of a Blocker introduced for a story |  | 10 | ---¦--- | 30 | Per story, per day | ID#5 | 2017-11-15
Blockers add X days to story completion time |  | 1 | -----¦- | 4 | Per blocker | … | … | … | … | … | …
X% chance of new story being added |  | 10 | ---¦--- | 30 | Per day | --> predicted end date
X% chance of bug(s) found for story |  | 20 | ---¦--- | 50 | Per story
Bug(s) take X hours to resolve |  | 16 | ----¦-- | 32 | Per bug | * Review Cumulative Flow diagrams at different stages in project
X% chance of each team member being unavailable |  | 10 | ---¦--- | 20 | Per individual, per day | * Review frequency bins for Completion Time
Unavailability lasts for X days |  | 1 | ---¦--- | 4 | Per unavailability | * Tweak predictive graphs to get more accurate?
Capacity (hours) of each developer per day |  | 2 | --¦---- | 6 | Per individual, per day | * Measure the actual parameter metrics as project progresses to re-run simulation?
System testing lasts X days | % of Story count
Rework from system testing adds X stories |  | 2 | ---¦--- | 10 | Per project
Rework from user acceptance adds X stories |  | 0 | -¦----- | 3 | Per project | DevTime table
Bank holidays | From calendar |  |  |  |  | Date | Dev#1 | Dev#2 | Dev#3 | Dev#4 | Dev#5
[6 empty] | 2017-12-04 | 2 | 6 | 4 | 4 | 5
[6 empty] | 2017-12-05 | 6 | 6 | 4 | 5 | 4
Simulation process | [5 empty] | 2017-12-06 | 4 | 4 | 4 | 0 | 4
Populate initial CumuFlow table of issues and randomised hours per phase | [5 empty] | 2017-12-07 | 4 | 5 | 4 | 0 | 2
Populate initial DevTime table (inc Absences: 0hrs) | [5 empty] | 2017-12-08 | 6 | 3 | 4 | 0 | 2
Main loop: Repeat until no more stories incomplete in CumuFlow table: | [5 empty] | 2017-12-09 | 5 | 3 | 4 | 2 | 2
Increment date | [5 empty] | … | … | … | … | … | …
For each story
Calculate whether Blocker happens
Add randomised Blocker time to Story time | [5 empty] | Input min/max/best guess for each metric
Repeat until no more dev time available | [5 empty] | Run simulation for best case/worst case/best guess
Decrement available Story Phases by amount of dev hours available | [5 empty] | --> prediction of end date(s) with no estimation
If Story Phase complete add Date to CumuFlow table for that story | [5 empty] | Can update metrics and re-run simulation as project progresses
If Story Completed then calculate Bugs found | [5 empty] | After a set period, calculate estimate completion date regularly during simulation and compare at end
For each bug: | [5 empty] | Use extrapolation of Done line and Frequency Bins to calculate estimate
Randomise time required for each bug | [5 empty] | --> Show if estimates are accurate and what factors affect them?
Add Bug as issue in CumuFlow table
Add randomised days for System Testing (% of total stories) | [5 empty] | Estimation of completion date via Done Rate Extrapolation or Frequency Bins calculation do not take account of new stories created, bugs found etc
Randomise new stories for from System Testing - add to CumuFlow table
Randomise new stories from User Acceptance - add to CumuFlow table
Perform main loop until no more Stories incomplete in CumuFlow table
End --> simulated end date, cumulative flow graph, frequency bins of completion time
Can now view CumuFlow graph half way through project and try to predict simulated end date

## Dummy CumuFlow (50 days)
Date | CountGrooming | CountWIP | CountReview | CountDone | DoneTrend
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 8 | 6 | 0 | 0 | 4 | 0

## Dummy CumuFlow (complete)
Date | CountGrooming | CountWIP | CountReview | CountDone
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-21 | 10 | 2 | 0 | 8 | 1 | 0 | 0 | 0 | 0
2018-01-22 | 10 | 0 | 1 | 9 | 3 | 0 | 0 | 0 | 0
2018-01-23 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-24 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-25 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-26 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-27 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-28 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 4 | 3
2018-01-29 | 8 | 0 | 1 | 11 | 1 | 0 | 0 | 0 | 0
2018-01-30 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-01-31 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-01 | 7 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-02 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-03 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-04 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-05 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-06 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-07 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-08 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-09 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-10 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-11 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-12 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-13 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-14 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-15 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-16 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-17 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-18 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-19 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-20 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-21 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-22 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-23 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 4
2018-02-24 | 2 | 4 | 0 | 14 | 0 | 0 | 0 | 0 | 0
2018-02-25 | 2 | 3 | 1 | 14 | 5 | 0 | 0 | 0 | 0
2018-02-26 | 2 | 0 | 1 | 17 | 4 | 2 | 0 | 0 | 0
2018-02-27 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-02-28 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-02 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-03 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-04 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-05 | 0 | 2 | 0 | 18 | 0 | 2 | 0 | 0 | 2
2018-03-06 | 0 | 0 | 0 | 20 | 0 | 0 | 4 | 4 | 3