## Dummy Data
Generating example Agile data
| Exactly | From | Weighting for randomisation | To | Randomised
Start date | 2017-12-04 |  |  |  |  | CumuFlow table
X number of initial stories | 20 |  |  |  |  | Issue | Defining | Ready | In Progress | Review | Done
List skills required and spread across stories | [5 empty] | ID#1 | 2017-12-04 |  | 2017-12-06 | 2017-12-15
Potentially import actual stories & skills | [5 empty] | ID#2 | 2017-12-04 |  | 2017-12-06 |  | 2018-01-02
X people in team | 5 |  |  |  |  | ID#3 | 2017-11-23 | 2017-11-28
List skills possessed by each developer | [5 empty] | ID#4 | 2017-10-17 | 2017-10-17 | 2017-12-04 |  | 2018-01-02
Getting a story to "Ready" takes X hours |  | 4 | -¦----- | 16 | Per story | ID#5 | 2017-11-15
Each story is "In Progress" for X hours |  | 8 | ---¦--- | 80 | Per story | … | … | … | … | … | …
Each story is in "Review" for X hours |  | 2 | -¦----- | 8 | Per story | --> predicted end date
X% chance of a Blocker introduced for a story |  | 10 | ---¦--- | 30 | Per story, per day
Blockers add X days to story completion time |  | 1 | -----¦- | 4 | Per blocker | * Review Cumulative Flow diagrams at different stages in project
X% chance of new story being added |  | 10 | ---¦--- | 30 | Per day | * Review frequency bins for Completion Time
X% chance of bug(s) found for story |  | 20 | ---¦--- | 50 | Per story | * Tweak predictive graphs to get more accurate?
Bug(s) take X hours to resolve |  | 16 | ----¦-- | 32 | Per bug | * Measure the actual parameter metrics as project progresses to re-run simulation?
X% chance of each team member being unavailable |  | 10 | ---¦--- | 20 | Per individual, per day
Unavailability lasts for X days |  | 1 | ---¦--- | 4 | Per unavailability
Capacity (hours) of each developer per day |  | 2 | --¦---- | 6 | Per individual, per day | DevTime table
System testing lasts X days | % of Story count |  |  |  |  | Date | Dev#1 | Dev#2 | Dev#3 | Dev#4 | Dev#5
Rework from system testing adds X stories |  | 2 | ---¦--- | 10 | Per project | 2017-12-04 | 2 | 6 | 4 | 4 | 5
Rework from user acceptance adds X stories |  | 0 | -¦----- | 3 | Per project | 2017-12-05 | 6 | 6 | 4 | 5 | 4
Bank holidays + Developer holidays | From JSON file |  |  |  |  | 2017-12-06 | 4 | 4 | 4 | 0 | 4
[6 empty] | 2017-12-07 | 4 | 5 | 4 | 0 | 2
[6 empty] | 2017-12-08 | 6 | 3 | 4 | 0 | 2
Simulation process | [5 empty] | 2017-12-09 | 5 | 3 | 4 | 2 | 2
Populate initial CumuFlow table of issues and randomised hours per phase | [5 empty] | … | … | … | … | … | …
Populate initial DevTime table (inc Absences: 0hrs)
Main loop: Repeat until no more stories incomplete in CumuFlow table:
Increment date | [5 empty] | Input min/max/best guess for each metric
For each story | [5 empty] | Run simulation for best case/worst case/best guess
Calculate whether Blocker happens | [5 empty] | --> prediction of end date(s) with no estimation
Add randomised Blocker time to Story time | [5 empty] | Can update metrics and re-run simulation as project progresses
Repeat until no more dev time available | [5 empty] | After a set period, calculate estimate completion date regularly during simulation and compare at end
Decrement available Story Phases by amount of dev hours available | [5 empty] | Use extrapolation of Done line and Frequency Bins to calculate estimate
If Story Phase complete add Date to CumuFlow table for that story | [5 empty] | --> Show if estimates are accurate and what factors affect them?
If Story Completed then calculate Bugs found
For each bug: | [5 empty] | Estimation of completion date via Done Rate Extrapolation or Frequency Bins calculation do not take account of new stories created, bugs found etc
Randomise time required for each bug
Add Bug as issue in CumuFlow table | [5 empty] | Run simulations before and after adding new resource with specific skills
Add randomised days for System Testing (% of total stories)
Randomise new stories for from System Testing - add to CumuFlow table
Randomise new stories from User Acceptance - add to CumuFlow table
Perform main loop until no more Stories incomplete in CumuFlow table
End --> simulated end date, cumulative flow graph, frequency bins of completion time
Can now view CumuFlow graph half way through project and try to predict simulated end date

## Dummy CumuFlow (50 days)
Date | CountGrooming | CountWIP | CountReview | CountDone | DoneTrend
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 8 | 6 | 0 | 0 | 4 | 0

## Dummy CumuFlow (complete)
Date | CountGrooming | CountWIP | CountReview | CountDone
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-21 | 10 | 2 | 0 | 8 | 1 | 0 | 0 | 0 | 0
2018-01-22 | 10 | 0 | 1 | 9 | 3 | 0 | 0 | 0 | 0
2018-01-23 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-24 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-25 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-26 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-27 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-28 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 4 | 3
2018-01-29 | 8 | 0 | 1 | 11 | 1 | 0 | 0 | 0 | 0
2018-01-30 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-01-31 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-01 | 7 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-02 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-03 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-04 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-05 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-06 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-07 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-08 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-09 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-10 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-11 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-12 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-13 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-14 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-15 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-16 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-17 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-18 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-19 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-20 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-21 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-22 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-23 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 4
2018-02-24 | 2 | 4 | 0 | 14 | 0 | 0 | 0 | 0 | 0
2018-02-25 | 2 | 3 | 1 | 14 | 5 | 0 | 0 | 0 | 0
2018-02-26 | 2 | 0 | 1 | 17 | 4 | 2 | 0 | 0 | 0
2018-02-27 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-02-28 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-02 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-03 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-04 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-05 | 0 | 2 | 0 | 18 | 0 | 2 | 0 | 0 | 2
2018-03-06 | 0 | 0 | 0 | 20 | 0 | 0 | 4 | 4 | 3

## EstimateTracking
Date | StartError | Last5Error | Grooming | WIP | Review | Done | LinearFromStart | LinearFromLast5
2017-12-01 |  |  | 15 | 0 | 0 | 0
2017-12-04 |  |  | 15 | 0 | 0 | 0
2017-12-05 |  |  | 15 | 0 | 0 | 0
2017-12-06 |  |  | 15 | 0 | 0 | 0
2017-12-07 |  |  | 15 | 0 | 0 | 0
2017-12-08 |  |  | 15 | 0 | 0 | 0
2017-12-11 |  |  | 15 | 0 | 0 | 0
2017-12-12 |  |  | 15 | 0 | 0 | 0
2017-12-13 |  |  | 15 | 0 | 0 | 0
2017-12-14 |  |  | 15 | 0 | 0 | 0
2017-12-15 |  |  | 14 | 1 | 0 | 0
2017-12-18 |  |  | 14 | 1 | 0 | 0
2017-12-19 |  |  | 14 | 1 | 0 | 0
2017-12-20 |  |  | 14 | 1 | 0 | 0
2017-12-21 |  |  | 14 | 1 | 0 | 0
2017-12-22 |  |  | 13 | 1 | 1 | 0
2017-12-25 | 223 |  | 14 | 1 | 0 | 1 | 2018-12-20
2017-12-26 | 239 |  | 14 | 1 | 0 | 1 | 2019-01-05
2017-12-27 | 255 |  | 14 | 1 | 0 | 1 | 2019-01-21
2017-12-28 | 271 |  | 14 | 1 | 0 | 1 | 2019-02-06
2017-12-29 | 287 |  | 14 | 1 | 0 | 1 | 2019-02-22
2018-01-01 | 335 |  | 14 | 1 | 0 | 1 | 2019-04-11
2018-01-02 | 95 |  | 14 | 0 | 0 | 2 | 2018-08-14
2018-01-03 | 96 |  | 14 | 0 | 0 | 2 | 2018-08-15
2018-01-04 | 111 |  | 13 | 1 | 0 | 2 | 2018-08-30
2018-01-05 | 112 |  | 13 | 1 | 0 | 2 | 2018-08-31
2018-01-08 | 143 |  | 13 | 1 | 0 | 2 | 2018-10-01
2018-01-09 | 144 |  | 12 | 1 | 1 | 2 | 2018-10-02
2018-01-10 | 48 |  | 12 | 1 | 0 | 3 | 2018-06-28
2018-01-11 | 49 |  | 12 | 1 | 0 | 3 | 2018-06-29
2018-01-12 | 63 |  | 12 | 1 | 0 | 3 | 2018-07-13
2018-01-15 | 79 |  | 12 | 1 | 0 | 3 | 2018-07-29
2018-01-16 | 80 |  | 12 | 0 | 1 | 3 | 2018-07-30
2018-01-17 | 18 |  | 10 | 2 | 0 | 4 | 2018-05-29
2018-01-18 | 31 |  | 10 | 2 | 0 | 4 | 2018-06-11
2018-01-19 | 32 |  | 10 | 2 | 0 | 4 | 2018-06-12
2018-01-22 | 47 |  | 10 | 2 | 0 | 4 | 2018-06-27
2018-01-23 | 48 |  | 10 | 2 | 0 | 4 | 2018-06-28
2018-01-24 | 49 |  | 10 | 1 | 1 | 4 | 2018-06-29
2018-01-25 | 26 |  | 11 | 0 | 1 | 5 | 2018-06-06
2018-01-26 | -6 | -50 | 11 | 0 | 0 | 6 | 2018-05-05 | 2018-03-22
2018-01-29 | -3 | -47 | 11 | 0 | 0 | 6 | 2018-05-08 | 2018-03-25
2018-01-30 | 9 | -46 | 11 | 0 | 0 | 6 | 2018-05-20 | 2018-03-26
2018-01-31 | 10 | -34 | 9 | 2 | 0 | 6 | 2018-05-21 | 2018-04-07
2018-02-01 | 11 | -33 | 9 | 2 | 0 | 6 | 2018-05-22 | 2018-04-08
2018-02-02 | 12 | -32 | 9 | 2 | 0 | 6 | 2018-05-23 | 2018-04-09
2018-02-05 | 26 | -18 | 9 | 2 | 0 | 6 | 2018-06-06 | 2018-04-23
2018-02-06 | 27 | -17 | 9 | 0 | 2 | 6 | 2018-06-07 | 2018-04-24
2018-02-07 | -13 | -53 | 10 | 0 | 0 | 8 | 2018-04-28 | 2018-03-19
2018-02-08 | -12 | -52 | 8 | 2 | 0 | 8 | 2018-04-29 | 2018-03-20
2018-02-09 | -11 | -51 | 8 | 2 | 0 | 8 | 2018-04-30 | 2018-03-21
2018-02-12 | 2 | -38 | 8 | 2 | 0 | 8 | 2018-05-13 | 2018-04-03
2018-02-13 | 3 | -37 | 8 | 2 | 0 | 8 | 2018-05-14 | 2018-04-04
2018-02-14 | 4 | -36 | 8 | 2 | 0 | 8 | 2018-05-15 | 2018-04-05
2018-02-15 | 5 | -25 | 8 | 2 | 0 | 8 | 2018-05-16 | 2018-04-16
2018-02-16 | 6 | -24 | 8 | 1 | 1 | 8 | 2018-05-17 | 2018-04-17
2018-02-19 | -1 | -31 | 10 | 0 | 0 | 10 | 2018-05-10 | 2018-04-10
2018-02-20 | 0 | -30 | 9 | 1 | 0 | 10 | 2018-05-11 | 2018-04-11
2018-02-21 | 1 | -29 | 9 | 1 | 0 | 10 | 2018-05-12 | 2018-04-12
2018-02-22 | 2 | -28 | 9 | 1 | 0 | 10 | 2018-05-13 | 2018-04-13
2018-02-23 | 3 | -27 | 9 | 1 | 0 | 10 | 2018-05-14 | 2018-04-14
2018-02-26 | -11 | -38 | 7 | 2 | 0 | 11 | 2018-04-30 | 2018-04-03
2018-02-27 | -1 | -37 | 7 | 2 | 0 | 11 | 2018-05-10 | 2018-04-04
2018-02-28 | 0 | -36 | 7 | 2 | 0 | 11 | 2018-05-11 | 2018-04-05
2018-03-01 | 1 | -35 | 7 | 2 | 0 | 11 | 2018-05-12 | 2018-04-06
2018-03-02 | 2 | -34 | 7 | 2 | 0 | 11 | 2018-05-13 | 2018-04-07
2018-03-05 | 5 | -22 | 7 | 2 | 0 | 11 | 2018-05-16 | 2018-04-19
2018-03-06 | 6 | -21 | 7 | 1 | 1 | 11 | 2018-05-17 | 2018-04-20
2018-03-07 | -1 | -33 | 7 | 0 | 1 | 12 | 2018-05-10 | 2018-04-08
2018-03-08 | 0 | -24 | 7 | 0 | 1 | 12 | 2018-05-11 | 2018-04-17
2018-03-09 | -7 | -31 | 8 | 0 | 0 | 13 | 2018-05-04 | 2018-04-10
2018-03-12 | -4 | -28 | 6 | 2 | 0 | 13 | 2018-05-07 | 2018-04-13
2018-03-13 | -3 | -19 | 6 | 2 | 0 | 13 | 2018-05-08 | 2018-04-22
2018-03-14 | -2 | -18 | 6 | 2 | 0 | 13 | 2018-05-09 | 2018-04-23
2018-03-15 | 7 | -17 | 6 | 2 | 0 | 13 | 2018-05-18 | 2018-04-24
2018-03-16 | 8 | -16 | 6 | 2 | 0 | 13 | 2018-05-19 | 2018-04-25
2018-03-19 | 11 | -5 | 6 | 2 | 0 | 13 | 2018-05-22 | 2018-05-06
2018-03-20 | 12 | -4 | 6 | 2 | 0 | 13 | 2018-05-23 | 2018-05-07
2018-03-21 | 13 | -3 | 6 | 2 | 0 | 13 | 2018-05-24 | 2018-05-08
2018-03-22 | 14 | -2 | 6 | 1 | 1 | 13 | 2018-05-25 | 2018-05-09
2018-03-23 | -7 | -19 | 2 | 4 | 0 | 15 | 2018-05-04 | 2018-04-22
2018-03-26 | -4 | -10 | 2 | 4 | 0 | 15 | 2018-05-07 | 2018-05-01
2018-03-27 | -3 | -9 | 2 | 4 | 0 | 15 | 2018-05-08 | 2018-05-02
2018-03-28 | -2 | -8 | 2 | 4 | 0 | 15 | 2018-05-09 | 2018-05-03
2018-03-29 | -1 | -7 | 2 | 4 | 0 | 15 | 2018-05-10 | 2018-05-04
2018-03-30 | 0 | 0 | 2 | 4 | 0 | 15 | 2018-05-11 | 2018-05-11
2018-04-02 | 9 | 3 | 2 | 4 | 0 | 15 | 2018-05-20 | 2018-05-14
2018-04-03 | 10 | 4 | 2 | 4 | 0 | 15 | 2018-05-21 | 2018-05-15
2018-04-04 | -9 | -17 | 1 | 1 | 2 | 17 | 2018-05-02 | 2018-04-24
2018-04-05 | -24 | -32 | 1 | 1 | 0 | 19 | 2018-04-17 | 2018-04-09
2018-04-06 | -23 | -31 | 1 | 1 | 0 | 19 | 2018-04-18 | 2018-04-10
2018-04-09 | -20 | -26 | 1 | 1 | 0 | 19 | 2018-04-21 | 2018-04-15
2018-04-10 | -19 | -25 | 1 | 1 | 0 | 19 | 2018-04-22 | 2018-04-16
2018-04-11 | -18 | -24 | 1 | 1 | 0 | 19 | 2018-04-23 | 2018-04-17
2018-04-12 | -17 | -27 | 1 | 1 | 0 | 20 | 2018-04-24 | 2018-04-14
2018-04-13 | -16 | -24 | 1 | 1 | 0 | 20 | 2018-04-25 | 2018-04-17
2018-04-16 | -13 | -21 | 1 | 1 | 0 | 20 | 2018-04-28 | 2018-04-20
2018-04-17 | -12 | -20 | 1 | 1 | 0 | 20 | 2018-04-29 | 2018-04-21
2018-04-18 | -11 | -17 | 1 | 1 | 0 | 20 | 2018-04-30 | 2018-04-24
2018-04-19 | -10 | -16 | 1 | 1 | 0 | 20 | 2018-05-01 | 2018-04-25
2018-04-20 | -7 | -15 | 1 | 1 | 0 | 20 | 2018-05-04 | 2018-04-26
2018-04-23 | -12 | -15 | 1 | 0 | 0 | 21 | 2018-04-29 | 2018-04-26
2018-04-24 | -11 | -14 | 0 | 1 | 0 | 21 | 2018-04-30 | 2018-04-27
2018-04-25 | -10 | -13 | 0 | 1 | 0 | 21 | 2018-05-01 | 2018-04-28
2018-04-26 | -9 | -12 | 0 | 1 | 0 | 21 | 2018-05-02 | 2018-04-29
2018-04-27 | -7 | -10 | 0 | 0 | 1 | 21 | 2018-05-04 | 2018-05-01
2018-04-30 | -4 | -7 | 0 | 0 | 1 | 21 | 2018-05-07 | 2018-05-04
2018-05-01 | -4 | -5 | 1 | 0 | 0 | 22 | 2018-05-07 | 2018-05-06
2018-05-02 | -3 | -4 | 1 | 0 | 0 | 22 | 2018-05-08 | 2018-05-07
2018-05-03 | -2 | -3 | 0 | 1 | 0 | 22 | 2018-05-09 | 2018-05-08
2018-05-04 | 0 | -1 | 0 | 1 | 0 | 22 | 2018-05-11 | 2018-05-10
2018-05-07 | 2 | 1 | 1 | 0 | 0 | 23 | 2018-05-13 | 2018-05-12
2018-05-08 | 3 | 2 | 1 | 0 | 0 | 23 | 2018-05-14 | 2018-05-13
2018-05-09 | 4 | 3 | 0 | 1 | 0 | 23 | 2018-05-15 | 2018-05-14
2018-05-10 | 5 | 5 | 0 | 1 | 0 | 23 | 2018-05-16 | 2018-05-16
2018-05-11 | 0 | 0 | 0 | 0 | 0 | 24 | 2018-05-11 | 2018-05-11

## MonteCarlo
Monte Carlo 1000 run |  |  |  | Parameters | Start Date = 1-Dec-17
Completion Date | Row Labels | Frequency | 15 | User Stories
2018-04-17 | 27-Feb | 1 | 5 | Developers
2018-04-20 | 01-Mar | 1 | 4-16 | Grooming Phase (hrs)
2018-03-27 | 02-Mar | 3 | 8-80 | In Progress Phase (hrs)
2018-03-06 | 06-Mar | 4 | 2-8 | Review Phase (hrs)
2018-03-14 | 07-Mar | 2 | 30 | Chance of bug raised on story (%)
2018-03-28 | 09-Mar | 1 | 8-32 | Work required to resolve bug (hrs)
2018-06-01 | 12-Mar | 3 | 20 | Chance of developer being absent (%)
2018-05-11 | 13-Mar | 7 | 1-4 | Length of developer absence (days)
2018-03-28 | 14-Mar | 3 | 2-6 | Developer capacity per day (hrs)
2018-04-26 | 15-Mar | 3
2018-04-20 | 16-Mar | 9
2018-04-30 | 19-Mar | 3
2018-05-08 | 20-Mar | 4
2018-04-16 | 21-Mar | 11
2018-03-22 | 22-Mar | 9
2018-04-18 | 23-Mar | 10
2018-03-22 | 26-Mar | 13
2018-05-22 | 27-Mar | 18
2018-04-24 | 28-Mar | 18
2018-03-23 | 29-Mar | 13
2018-04-20 | 30-Mar | 15
2018-05-21 | 02-Apr | 11
2018-03-23 | 03-Apr | 19
2018-04-05 | 04-Apr | 13
2018-04-27 | 05-Apr | 18
2018-03-15 | 06-Apr | 23
2018-05-16 | 09-Apr | 13
2018-04-19 | 10-Apr | 25
2018-05-16 | 11-Apr | 30
2018-05-14 | 12-Apr | 16
2018-04-26 | 13-Apr | 14
2018-04-11 | 16-Apr | 23
2018-04-17 | 17-Apr | 15
2018-04-19 | 18-Apr | 19
2018-04-23 | 19-Apr | 27
2018-04-02 | 20-Apr | 25
2018-04-19 | 23-Apr | 20
2018-06-06 | 24-Apr | 20
2018-04-20 | 25-Apr | 26
2018-05-10 | 26-Apr | 29
2018-03-30 | 27-Apr | 14
2018-04-30 | 30-Apr | 15
2018-04-10 | 01-May | 13
2018-05-16 | 02-May | 17
2018-03-30 | 03-May | 20
2018-05-14 | 04-May | 16
2018-04-25 | 07-May | 12
2018-04-19 | 08-May | 16
2018-03-28 | 09-May | 10
2018-05-28 | 10-May | 17
2018-04-17 | 11-May | 15
2018-04-13 | 14-May | 16
2018-04-20 | 15-May | 20
2018-04-24 | 16-May | 18
2018-05-25 | 17-May | 9
2018-05-15 | 18-May | 15
2018-04-25 | 21-May | 14
2018-06-06 | 22-May | 14
2018-04-24 | 23-May | 9
2018-03-21 | 24-May | 15
2018-04-26 | 25-May | 11
2018-05-07 | 28-May | 12
2018-04-23 | 29-May | 14
2018-04-16 | 30-May | 9
2018-05-18 | 31-May | 10
2018-04-25 | 01-Jun | 6
2018-05-29 | 04-Jun | 6
2018-05-16 | 05-Jun | 5
2018-04-27 | 06-Jun | 12
2018-04-11 | 07-Jun | 8
2018-04-18 | 08-Jun | 7
2018-05-28 | 11-Jun | 3
2018-06-06 | 12-Jun | 2
2018-05-18 | 13-Jun | 3
2018-05-29 | 14-Jun | 9
2018-04-12 | 15-Jun | 4
2018-04-04 | 18-Jun | 2
2018-04-18 | 19-Jun | 4
2018-05-09 | 20-Jun | 7
2018-05-16 | 21-Jun | 2
2018-04-10 | 22-Jun | 2
2018-04-25 | 25-Jun | 3
2018-06-06 | 26-Jun | 4
2018-04-30 | 27-Jun | 1
2018-05-09 | 28-Jun | 2
2018-06-26 | 02-Jul | 4
2018-05-14 | 03-Jul | 1
2018-03-22 | 04-Jul | 1
2018-05-15 | 05-Jul | 2
2018-04-11 | 09-Jul | 2
2018-05-25 | 11-Jul | 1
2018-05-23 | 18-Jul | 2
2018-03-21 | 19-Jul | 1
2018-07-04 | 24-Jul | 1
2018-05-29 | 27-Jul | 1
2018-05-25 | 02-Aug | 1
2018-06-06 | 07-Aug | 1
2018-03-26 | 09-Aug | 1
2018-05-04 | 14-Aug | 1
2018-06-08 | Grand Total | 1000
2018-04-20
2018-03-06
2018-04-10
2018-04-10
2018-06-15
2018-04-23
2018-03-22
2018-03-01
2018-04-25
2018-07-09
2018-05-29
2018-04-09
2018-06-22
2018-04-26
2018-06-15
2018-04-18
2018-04-23
2018-04-25
2018-05-03
2018-04-13
2018-03-27
2018-04-26
2018-03-28
2018-03-21
2018-05-09
2018-04-26
2018-04-24
2018-03-21
2018-04-13
2018-04-09
2018-04-12
2018-04-05
2018-05-31
2018-04-11
2018-05-29
2018-05-14
2018-06-28
2018-03-27
2018-05-11
2018-06-05
2018-05-18
2018-04-19
2018-03-30
2018-05-23
2018-06-01
2018-04-12
2018-05-08
2018-03-29
2018-03-19
2018-05-31
2018-03-26
2018-04-05
2018-04-11
2018-03-29
2018-05-16
2018-03-27
2018-05-29
2018-05-10
2018-04-30
2018-04-19
2018-05-09
2018-04-06
2018-05-18
2018-05-10
2018-04-20
2018-04-02
2018-06-04
2018-05-03
2018-04-05
2018-05-16
2018-05-02
2018-05-10
2018-06-07
2018-05-15
2018-05-18
2018-03-28
2018-04-12
2018-04-25
2018-04-09
2018-05-08
2018-06-06
2018-04-24
2018-03-13
2018-05-31
2018-05-16
2018-04-12
2018-04-04
2018-05-17
2018-06-06
2018-05-15
2018-04-16
2018-08-09
2018-04-11
2018-04-04
2018-04-12
2018-04-19
2018-05-16
2018-05-18
2018-05-24
2018-07-02
2018-04-06
2018-04-09
2018-04-12
2018-04-20
2018-04-03
2018-04-03
2018-03-21
2018-03-26
2018-05-22
2018-04-26
2018-04-16
2018-04-06
2018-03-30
2018-04-18
2018-04-11
2018-05-08
2018-04-05
2018-05-24
2018-05-24
2018-04-11
2018-04-04
2018-04-20
2018-03-30
2018-05-22
2018-04-03
2018-04-26
2018-03-29
2018-05-07
2018-06-05
2018-05-24
2018-04-02
2018-05-22
2018-03-12
2018-03-13
2018-06-04
2018-05-25
2018-05-28
2018-05-01
2018-05-31
2018-06-20
2018-05-15
2018-05-28
2018-03-28
2018-04-09
2018-04-20
2018-07-09
2018-05-17
2018-03-27
2018-04-04
2018-05-10
2018-04-23
2018-05-24
2018-03-27
2018-06-06
2018-04-06
2018-04-06
2018-04-16
2018-03-22
2018-04-18
2018-03-22
2018-04-25
2018-03-23
2018-04-20
2018-03-28
2018-04-25
2018-04-26
2018-03-13
2018-05-14
2018-07-05
2018-04-03
2018-05-14
2018-06-14
2018-04-27
2018-03-29
2018-03-12
2018-05-02
2018-04-10
2018-04-10
2018-04-10
2018-04-16
2018-08-02
2018-04-17
2018-03-28
2018-03-27
2018-04-17
2018-04-25
2018-04-10
2018-05-03
2018-05-18
2018-05-08
2018-04-16
2018-03-27
2018-04-25
2018-05-01
2018-05-01
2018-05-09
2018-06-14
2018-05-10
2018-05-09
2018-03-28
2018-05-15
2018-04-26
2018-06-20
2018-04-06
2018-05-28
2018-04-30
2018-03-28
2018-05-16
2018-04-19
2018-05-30
2018-04-13
2018-04-12
2018-05-04
2018-04-16
2018-05-02
2018-05-21
2018-05-31
2018-05-03
2018-04-19
2018-06-22
2018-06-20
2018-04-06
2018-06-01
2018-05-14
2018-05-18
2018-04-17
2018-05-02
2018-03-28
2018-05-10
2018-05-22
2018-05-02
2018-03-27
2018-04-06
2018-05-01
2018-04-04
2018-04-23
2018-04-24
2018-05-23
2018-06-06
2018-05-11
2018-03-26
2018-05-01
2018-04-13
2018-03-26
2018-04-25
2018-04-24
2018-03-21
2018-04-19
2018-05-24
2018-08-07
2018-05-31
2018-03-27
2018-04-30
2018-05-04
2018-06-18
2018-04-16
2018-04-13
2018-03-14
2018-03-26
2018-03-16
2018-04-03
2018-05-09
2018-03-21
2018-04-16
2018-04-03
2018-04-19
2018-04-04
2018-05-08
2018-06-12
2018-03-16
2018-05-29
2018-05-31
2018-05-15
2018-03-12
2018-04-16
2018-03-30
2018-04-03
2018-04-13
2018-04-20
2018-05-04
2018-05-24
2018-04-03
2018-05-07
2018-04-02
2018-04-20
2018-04-23
2018-04-23
2018-05-02
2018-04-04
2018-03-16
2018-05-18
2018-05-24
2018-05-16
2018-04-16
2018-05-02
2018-05-28
2018-04-06
2018-03-20
2018-04-03
2018-06-08
2018-05-15
2018-06-04
2018-05-03
2018-05-04
2018-04-16
2018-03-20
2018-03-20
2018-05-25
2018-03-27
2018-04-19
2018-05-28
2018-05-04
2018-04-26
2018-04-10
2018-06-21
2018-05-22
2018-04-16
2018-05-22
2018-04-25
2018-05-17
2018-04-18
2018-05-10
2018-04-11
2018-05-22
2018-05-11
2018-05-15
2018-04-25
2018-05-07
2018-05-28
2018-04-26
2018-05-24
2018-04-26
2018-05-01
2018-03-27
2018-04-27
2018-05-10
2018-05-22
2018-03-21
2018-04-18
2018-04-30
2018-04-10
2018-05-22
2018-05-25
2018-04-24
2018-03-13
2018-06-08
2018-06-19
2018-05-08
2018-04-30
2018-05-24
2018-06-20
2018-05-11
2018-04-30
2018-06-06
2018-04-11
2018-05-23
2018-03-30
2018-05-02
2018-07-05
2018-04-27
2018-04-13
2018-04-04
2018-04-06
2018-06-05
2018-04-17
2018-04-24
2018-03-28
2018-05-28
2018-04-11
2018-05-03
2018-03-28
2018-04-19
2018-05-04
2018-04-06
2018-04-05
2018-04-05
2018-04-16
2018-04-11
2018-06-08
2018-03-28
2018-06-07
2018-05-30
2018-04-24
2018-03-13
2018-05-28
2018-05-17
2018-06-14
2018-03-13
2018-04-16
2018-04-17
2018-04-10
2018-06-11
2018-04-11
2018-05-07
2018-03-21
2018-05-14
2018-06-19
2018-04-04
2018-05-21
2018-06-14
2018-04-05
2018-08-14
2018-04-06
2018-04-24
2018-04-23
2018-04-11
2018-04-25
2018-04-09
2018-04-05
2018-05-17
2018-05-07
2018-05-14
2018-05-15
2018-05-07
2018-03-23
2018-05-15
2018-04-04
2018-05-10
2018-04-27
2018-05-21
2018-04-18
2018-06-25
2018-05-08
2018-03-02
2018-05-24
2018-03-16
2018-04-25
2018-05-18
2018-05-15
2018-05-14
2018-04-12
2018-06-26
2018-04-18
2018-04-06
2018-03-26
2018-05-15
2018-05-30
2018-04-06
2018-05-03
2018-04-24
2018-03-30
2018-05-24
2018-04-02
2018-04-19
2018-03-28
2018-04-23
2018-04-20
2018-05-02
2018-04-02
2018-05-21
2018-04-05
2018-05-11
2018-06-15
2018-04-23
2018-07-24
2018-05-21
2018-04-27
2018-05-30
2018-05-04
2018-04-26
2018-04-03
2018-03-07
2018-05-04
2018-03-30
2018-05-03
2018-06-18
2018-03-19
2018-04-06
2018-04-25
2018-04-24
2018-04-26
2018-03-29
2018-04-11
2018-04-30
2018-06-08
2018-05-01
2018-04-23
2018-05-15
2018-04-30
2018-06-07
2018-05-03
2018-04-10
2018-05-29
2018-04-09
2018-05-03
2018-04-19
2018-06-14
2018-05-03
2018-04-06
2018-03-29
2018-03-22
2018-04-18
2018-04-12
2018-04-20
2018-05-29
2018-04-06
2018-04-23
2018-04-20
2018-04-10
2018-04-30
2018-04-30
2018-05-03
2018-04-03
2018-05-01
2018-04-16
2018-04-26
2018-05-22
2018-07-02
2018-05-18
2018-04-18
2018-04-23
2018-04-10
2018-06-19
2018-05-17
2018-04-30
2018-04-26
2018-04-18
2018-03-29
2018-04-26
2018-04-06
2018-04-17
2018-04-06
2018-05-14
2018-03-06
2018-07-02
2018-04-18
2018-07-02
2018-05-03
2018-03-14
2018-04-27
2018-06-04
2018-04-10
2018-04-12
2018-03-27
2018-07-27
2018-05-17
2018-05-14
2018-04-11
2018-05-18
2018-05-11
2018-05-30
2018-05-01
2018-07-11
2018-04-24
2018-06-12
2018-03-06
2018-04-10
2018-04-12
2018-04-11
2018-04-06
2018-04-10
2018-04-10
2018-03-16
2018-05-25
2018-04-19
2018-04-12
2018-05-07
2018-05-22
2018-03-26
2018-05-09
2018-05-29
2018-04-17
2018-04-03
2018-04-20
2018-03-30
2018-03-09
2018-05-09
2018-05-28
2018-03-15
2018-05-31
2018-04-25
2018-06-08
2018-03-27
2018-04-25
2018-04-20
2018-04-25
2018-05-29
2018-05-16
2018-05-02
2018-05-02
2018-04-18
2018-04-27
2018-04-19
2018-05-04
2018-05-14
2018-03-27
2018-05-21
2018-04-13
2018-04-19
2018-04-20
2018-03-22
2018-06-07
2018-04-12
2018-04-19
2018-04-10
2018-06-20
2018-03-30
2018-04-13
2018-05-21
2018-03-13
2018-05-01
2018-04-03
2018-04-23
2018-05-08
2018-04-19
2018-06-07
2018-03-26
2018-04-11
2018-04-26
2018-03-26
2018-05-31
2018-06-04
2018-05-11
2018-05-15
2018-04-02
2018-05-08
2018-04-09
2018-03-30
2018-04-10
2018-04-25
2018-05-10
2018-03-20
2018-04-26
2018-04-11
2018-06-07
2018-06-13
2018-05-03
2018-03-26
2018-04-05
2018-04-03
2018-06-06
2018-04-16
2018-03-16
2018-04-03
2018-04-09
2018-03-28
2018-04-09
2018-05-04
2018-05-08
2018-04-11
2018-04-23
2018-04-05
2018-04-27
2018-04-20
2018-04-03
2018-04-12
2018-03-07
2018-04-11
2018-04-11
2018-06-13
2018-04-20
2018-05-29
2018-05-25
2018-05-21
2018-05-18
2018-04-25
2018-05-18
2018-06-14
2018-06-28
2018-05-11
2018-03-02
2018-06-13
2018-04-23
2018-06-11
2018-03-29
2018-06-05
2018-03-27
2018-04-11
2018-05-10
2018-06-01
2018-06-07
2018-05-29
2018-04-24
2018-04-20
2018-04-19
2018-05-03
2018-04-06
2018-06-15
2018-05-29
2018-03-27
2018-05-02
2018-05-11
2018-05-17
2018-05-02
2018-06-26
2018-05-11
2018-06-14
2018-04-26
2018-07-18
2018-05-08
2018-04-13
2018-04-02
2018-04-25
2018-05-03
2018-04-05
2018-05-24
2018-04-04
2018-03-30
2018-05-07
2018-05-21
2018-05-10
2018-04-10
2018-03-22
2018-03-26
2018-05-08
2018-05-21
2018-04-11
2018-03-29
2018-04-17
2018-04-11
2018-04-27
2018-03-16
2018-04-27
2018-06-14
2018-05-22
2018-04-16
2018-05-30
2018-05-30
2018-05-23
2018-05-07
2018-04-19
2018-04-20
2018-05-04
2018-04-18
2018-04-11
2018-05-14
2018-04-18
2018-04-26
2018-04-26
2018-07-03
2018-04-03
2018-05-10
2018-04-17
2018-05-07
2018-03-21
2018-04-23
2018-05-09
2018-04-12
2018-05-02
2018-04-24
2018-05-15
2018-05-10
2018-05-15
2018-05-07
2018-06-19
2018-03-29
2018-04-10
2018-04-03
2018-04-05
2018-06-20
2018-05-14
2018-04-25
2018-03-23
2018-05-16
2018-05-23
2018-04-10
2018-04-19
2018-05-03
2018-03-26
2018-04-18
2018-04-10
2018-05-24
2018-05-04
2018-05-30
2018-05-11
2018-04-19
2018-04-25
2018-07-19
2018-04-11
2018-03-29
2018-05-16
2018-04-26
2018-05-03
2018-05-22
2018-04-19
2018-04-03
2018-05-25
2018-04-19
2018-05-15
2018-04-30
2018-05-17
2018-04-02
2018-04-05
2018-04-20
2018-03-02
2018-05-23
2018-03-23
2018-05-02
2018-06-21
2018-04-17
2018-05-24
2018-04-24
2018-03-21
2018-03-28
2018-04-25
2018-05-16
2018-05-04
2018-07-18
2018-05-18
2018-05-15
2018-04-26
2018-05-11
2018-04-17
2018-05-04
2018-04-16
2018-05-03
2018-04-05
2018-04-16
2018-05-08
2018-04-11
2018-05-16
2018-04-02
2018-04-24
2018-03-23
2018-04-06
2018-06-04
2018-06-27
2018-03-23
2018-03-28
2018-05-02
2018-04-02
2018-05-15
2018-06-26
2018-05-10
2018-06-01
2018-04-24
2018-04-09
2018-04-23
2018-04-13
2018-04-27
2018-04-23
2018-05-28
2018-04-26
2018-03-30
2018-05-08
2018-06-14
2018-03-23
2018-04-04
2018-03-29
2018-05-01
2018-04-05
2018-05-23
2018-05-01
2018-05-30
2018-05-31
2018-05-16
2018-05-16
2018-05-08
2018-06-06
2018-04-10
2018-04-19
2018-06-08
2018-05-21
2018-04-27
2018-05-23
2018-04-26
2018-05-10
2018-06-25
2018-02-27
2018-04-18
2018-05-02
2018-06-11
2018-06-01
2018-04-06
2018-04-26
2018-04-20
2018-05-03
2018-04-09
2018-03-15
2018-04-16
2018-05-25
2018-05-25
2018-05-04
2018-03-27
2018-04-11
2018-04-13
2018-05-11
2018-04-17
2018-04-26
2018-04-11
2018-04-05
2018-04-13
2018-05-21
2018-05-01
2018-05-21
2018-04-16
2018-06-07
2018-06-05
2018-06-25
2018-04-09
2018-06-20
2018-05-14
2018-04-24
2018-03-23
2018-03-16
2018-03-19
2018-05-11
2018-03-29
2018-03-16
2018-03-30
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.