## Dummy Data
Generating example Agile data
| Exactly | From | Weighting for randomisation | To | Randomised
Start date | 2017-12-04 |  |  |  |  | CumuFlow table
X number of initial stories | 20 |  |  |  |  | Issue | Defining | Ready | In Progress | Review | Done
List skills required and spread across stories | [5 empty] | ID#1 | 2017-12-04 |  | 2017-12-06 | 2017-12-15
Potentially import actual stories & skills | [5 empty] | ID#2 | 2017-12-04 |  | 2017-12-06 |  | 2018-01-02
X people in team | 5 |  |  |  |  | ID#3 | 2017-11-23 | 2017-11-28
List skills possessed by each developer | [5 empty] | ID#4 | 2017-10-17 | 2017-10-17 | 2017-12-04 |  | 2018-01-02
Getting a story to "Ready" takes X hours |  | 4 | -¦----- | 16 | Per story | ID#5 | 2017-11-15
Each story is "In Progress" for X hours |  | 8 | ---¦--- | 80 | Per story | … | … | … | … | … | …
Each story is in "Review" for X hours |  | 2 | -¦----- | 8 | Per story | --> predicted end date
X% chance of a Blocker introduced for a story |  | 10 | ---¦--- | 30 | Per story, per day
Blockers add X days to story completion time |  | 1 | -----¦- | 4 | Per blocker | * Review Cumulative Flow diagrams at different stages in project
X% chance of new story being added |  | 10 | ---¦--- | 30 | Per day | * Review frequency bins for Completion Time
X% chance of bug(s) found for story |  | 20 | ---¦--- | 50 | Per story | * Tweak predictive graphs to get more accurate?
Bug(s) take X hours to resolve |  | 16 | ----¦-- | 32 | Per bug | * Measure the actual parameter metrics as project progresses to re-run simulation?
X% chance of each team member being unavailable |  | 10 | ---¦--- | 20 | Per individual, per day
Unavailability lasts for X days |  | 1 | ---¦--- | 4 | Per unavailability
Capacity (hours) of each developer per day |  | 2 | --¦---- | 6 | Per individual, per day | DevTime table
System testing lasts X days | % of Story count |  |  |  |  | Date | Dev#1 | Dev#2 | Dev#3 | Dev#4 | Dev#5
Rework from system testing adds X stories |  | 2 | ---¦--- | 10 | Per project | 2017-12-04 | 2 | 6 | 4 | 4 | 5
Rework from user acceptance adds X stories |  | 0 | -¦----- | 3 | Per project | 2017-12-05 | 6 | 6 | 4 | 5 | 4
Bank holidays + Developer holidays | From JSON file |  |  |  |  | 2017-12-06 | 4 | 4 | 4 | 0 | 4
[6 empty] | 2017-12-07 | 4 | 5 | 4 | 0 | 2
[6 empty] | 2017-12-08 | 6 | 3 | 4 | 0 | 2
Simulation process | [5 empty] | 2017-12-09 | 5 | 3 | 4 | 2 | 2
Populate initial CumuFlow table of issues and randomised hours per phase | [5 empty] | … | … | … | … | … | …
Populate initial DevTime table (inc Absences: 0hrs)
Main loop: Repeat until no more stories incomplete in CumuFlow table:
Increment date | [5 empty] | Input min/max/best guess for each metric
For each story | [5 empty] | Run simulation for best case/worst case/best guess
Calculate whether Blocker happens | [5 empty] | --> prediction of end date(s) with no estimation
Add randomised Blocker time to Story time | [5 empty] | Can update parameters with actual project metrics so far and re-run simulation as project progresses
Repeat until no more dev time available | [5 empty] | After a set period, calculate estimate completion date regularly during simulation and compare at end
Decrement available Story Phases by amount of dev hours available | [5 empty] | Use extrapolation of Done line and Frequency Bins to calculate estimate
If Story Phase complete add Date to CumuFlow table for that story | [5 empty] | --> Show if estimates are accurate and what factors affect them?
If Story Completed then calculate Bugs found
For each bug: | [5 empty] | Estimation of completion date via Done Rate Extrapolation or Frequency Bins calculation do not take account of new stories created, bugs found etc
Randomise time required for each bug
Add Bug as issue in CumuFlow table | [5 empty] | Assign skills to Stories and Developers
Add randomised days for System Testing (% of total stories) | [5 empty] | --> Run simulations before and after adding new resource with specific skills
Randomise new stories for from System Testing - add to CumuFlow table
Randomise new stories from User Acceptance - add to CumuFlow table
Perform main loop until no more Stories incomplete in CumuFlow table
End --> simulated end date, cumulative flow graph, frequency bins of completion time
Can now view CumuFlow graph half way through project and try to predict simulated end date

## Dummy CumuFlow (50 days)
Date | CountGrooming | CountWIP | CountReview | CountDone | DoneTrend
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 8 | 6 | 0 | 0 | 4 | 0

## Dummy CumuFlow (complete)
Date | CountGrooming | CountWIP | CountReview | CountDone
2017-12-01 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-03 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-04 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-05 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-06 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-07 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-08 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-09 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-10 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-11 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-13 | 19 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-14 | 19 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 0
2017-12-15 | 19 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-16 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-17 | 18 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2017-12-18 | 18 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2017-12-19 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-20 | 18 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-21 | 17 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
2017-12-22 | 17 | 1 | 0 | 2 | 0 | 0 | 4 | 0 | 0
2017-12-23 | 17 | 0 | 1 | 2 | 0 | 3 | 0 | 0 | 0
2017-12-24 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-25 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-26 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-27 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-28 | 16 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-29 | 16 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0
2017-12-30 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2017-12-31 | 16 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 15 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 15 | 1 | 0 | 4 | 0 | 0 | 3 | 0 | 5
2018-01-06 | 15 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
2018-01-07 | 14 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 12 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 12 | 2 | 0 | 6 | 1 | 0 | 3 | 0 | 0
2018-01-15 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0
2018-01-21 | 10 | 2 | 0 | 8 | 1 | 0 | 0 | 0 | 0
2018-01-22 | 10 | 0 | 1 | 9 | 3 | 0 | 0 | 0 | 0
2018-01-23 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-24 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-25 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-26 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-27 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0
2018-01-28 | 8 | 2 | 0 | 10 | 0 | 0 | 0 | 4 | 3
2018-01-29 | 8 | 0 | 1 | 11 | 1 | 0 | 0 | 0 | 0
2018-01-30 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-01-31 | 7 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-01 | 7 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0
2018-02-02 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-03 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-04 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-05 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-06 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-07 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-08 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-09 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-10 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-11 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-12 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-13 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-14 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-15 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-16 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-17 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-18 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-19 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-20 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-21 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-22 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
2018-02-23 | 2 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 4
2018-02-24 | 2 | 4 | 0 | 14 | 0 | 0 | 0 | 0 | 0
2018-02-25 | 2 | 3 | 1 | 14 | 5 | 0 | 0 | 0 | 0
2018-02-26 | 2 | 0 | 1 | 17 | 4 | 2 | 0 | 0 | 0
2018-02-27 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-02-28 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-02 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-03 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-04 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0
2018-03-05 | 0 | 2 | 0 | 18 | 0 | 2 | 0 | 0 | 2
2018-03-06 | 0 | 0 | 0 | 20 | 0 | 0 | 4 | 4 | 3

## LinearEstimates
Date | StartError | Last5Error | Grooming | WIP | Review | Done | LinearFromStart | LinearFromLast5
2017-12-01 |  |  | 15 | 0 | 0 | 0
2017-12-04 |  |  | 15 | 0 | 0 | 0
2017-12-05 |  |  | 15 | 0 | 0 | 0
2017-12-06 |  |  | 15 | 0 | 0 | 0
2017-12-07 |  |  | 15 | 0 | 0 | 0
2017-12-08 |  |  | 15 | 0 | 0 | 0
2017-12-11 |  |  | 15 | 0 | 0 | 0
2017-12-12 |  |  | 15 | 0 | 0 | 0
2017-12-13 |  |  | 15 | 0 | 0 | 0
2017-12-14 |  |  | 15 | 0 | 0 | 0
2017-12-15 |  |  | 14 | 1 | 0 | 0
2017-12-18 |  |  | 14 | 1 | 0 | 0
2017-12-19 |  |  | 14 | 1 | 0 | 0
2017-12-20 |  |  | 14 | 1 | 0 | 0
2017-12-21 |  |  | 14 | 1 | 0 | 0
2017-12-22 |  |  | 13 | 1 | 1 | 0
2017-12-25 | 223 |  | 14 | 1 | 0 | 1 | 2018-12-20
2017-12-26 | 239 |  | 14 | 1 | 0 | 1 | 2019-01-05
2017-12-27 | 255 |  | 14 | 1 | 0 | 1 | 2019-01-21
2017-12-28 | 271 |  | 14 | 1 | 0 | 1 | 2019-02-06
2017-12-29 | 287 |  | 14 | 1 | 0 | 1 | 2019-02-22
2018-01-01 | 335 |  | 14 | 1 | 0 | 1 | 2019-04-11
2018-01-02 | 95 |  | 14 | 0 | 0 | 2 | 2018-08-14
2018-01-03 | 96 |  | 14 | 0 | 0 | 2 | 2018-08-15
2018-01-04 | 111 |  | 13 | 1 | 0 | 2 | 2018-08-30
2018-01-05 | 112 |  | 13 | 1 | 0 | 2 | 2018-08-31
2018-01-08 | 143 |  | 13 | 1 | 0 | 2 | 2018-10-01
2018-01-09 | 144 |  | 12 | 1 | 1 | 2 | 2018-10-02
2018-01-10 | 48 |  | 12 | 1 | 0 | 3 | 2018-06-28
2018-01-11 | 49 |  | 12 | 1 | 0 | 3 | 2018-06-29
2018-01-12 | 63 |  | 12 | 1 | 0 | 3 | 2018-07-13
2018-01-15 | 79 |  | 12 | 1 | 0 | 3 | 2018-07-29
2018-01-16 | 80 |  | 12 | 0 | 1 | 3 | 2018-07-30
2018-01-17 | 18 |  | 10 | 2 | 0 | 4 | 2018-05-29
2018-01-18 | 31 |  | 10 | 2 | 0 | 4 | 2018-06-11
2018-01-19 | 32 |  | 10 | 2 | 0 | 4 | 2018-06-12
2018-01-22 | 47 |  | 10 | 2 | 0 | 4 | 2018-06-27
2018-01-23 | 48 |  | 10 | 2 | 0 | 4 | 2018-06-28
2018-01-24 | 49 |  | 10 | 1 | 1 | 4 | 2018-06-29
2018-01-25 | 26 |  | 11 | 0 | 1 | 5 | 2018-06-06
2018-01-26 | -6 | -50 | 11 | 0 | 0 | 6 | 2018-05-05 | 2018-03-22
2018-01-29 | -3 | -47 | 11 | 0 | 0 | 6 | 2018-05-08 | 2018-03-25
2018-01-30 | 9 | -46 | 11 | 0 | 0 | 6 | 2018-05-20 | 2018-03-26
2018-01-31 | 10 | -34 | 9 | 2 | 0 | 6 | 2018-05-21 | 2018-04-07
2018-02-01 | 11 | -33 | 9 | 2 | 0 | 6 | 2018-05-22 | 2018-04-08
2018-02-02 | 12 | -32 | 9 | 2 | 0 | 6 | 2018-05-23 | 2018-04-09
2018-02-05 | 26 | -18 | 9 | 2 | 0 | 6 | 2018-06-06 | 2018-04-23
2018-02-06 | 27 | -17 | 9 | 0 | 2 | 6 | 2018-06-07 | 2018-04-24
2018-02-07 | -13 | -53 | 10 | 0 | 0 | 8 | 2018-04-28 | 2018-03-19
2018-02-08 | -12 | -52 | 8 | 2 | 0 | 8 | 2018-04-29 | 2018-03-20
2018-02-09 | -11 | -51 | 8 | 2 | 0 | 8 | 2018-04-30 | 2018-03-21
2018-02-12 | 2 | -38 | 8 | 2 | 0 | 8 | 2018-05-13 | 2018-04-03
2018-02-13 | 3 | -37 | 8 | 2 | 0 | 8 | 2018-05-14 | 2018-04-04
2018-02-14 | 4 | -36 | 8 | 2 | 0 | 8 | 2018-05-15 | 2018-04-05
2018-02-15 | 5 | -25 | 8 | 2 | 0 | 8 | 2018-05-16 | 2018-04-16
2018-02-16 | 6 | -24 | 8 | 1 | 1 | 8 | 2018-05-17 | 2018-04-17
2018-02-19 | -1 | -31 | 10 | 0 | 0 | 10 | 2018-05-10 | 2018-04-10
2018-02-20 | 0 | -30 | 9 | 1 | 0 | 10 | 2018-05-11 | 2018-04-11
2018-02-21 | 1 | -29 | 9 | 1 | 0 | 10 | 2018-05-12 | 2018-04-12
2018-02-22 | 2 | -28 | 9 | 1 | 0 | 10 | 2018-05-13 | 2018-04-13
2018-02-23 | 3 | -27 | 9 | 1 | 0 | 10 | 2018-05-14 | 2018-04-14
2018-02-26 | -11 | -38 | 7 | 2 | 0 | 11 | 2018-04-30 | 2018-04-03
2018-02-27 | -1 | -37 | 7 | 2 | 0 | 11 | 2018-05-10 | 2018-04-04
2018-02-28 | 0 | -36 | 7 | 2 | 0 | 11 | 2018-05-11 | 2018-04-05
2018-03-01 | 1 | -35 | 7 | 2 | 0 | 11 | 2018-05-12 | 2018-04-06
2018-03-02 | 2 | -34 | 7 | 2 | 0 | 11 | 2018-05-13 | 2018-04-07
2018-03-05 | 5 | -22 | 7 | 2 | 0 | 11 | 2018-05-16 | 2018-04-19
2018-03-06 | 6 | -21 | 7 | 1 | 1 | 11 | 2018-05-17 | 2018-04-20
2018-03-07 | -1 | -33 | 7 | 0 | 1 | 12 | 2018-05-10 | 2018-04-08
2018-03-08 | 0 | -24 | 7 | 0 | 1 | 12 | 2018-05-11 | 2018-04-17
2018-03-09 | -7 | -31 | 8 | 0 | 0 | 13 | 2018-05-04 | 2018-04-10
2018-03-12 | -4 | -28 | 6 | 2 | 0 | 13 | 2018-05-07 | 2018-04-13
2018-03-13 | -3 | -19 | 6 | 2 | 0 | 13 | 2018-05-08 | 2018-04-22
2018-03-14 | -2 | -18 | 6 | 2 | 0 | 13 | 2018-05-09 | 2018-04-23
2018-03-15 | 7 | -17 | 6 | 2 | 0 | 13 | 2018-05-18 | 2018-04-24
2018-03-16 | 8 | -16 | 6 | 2 | 0 | 13 | 2018-05-19 | 2018-04-25
2018-03-19 | 11 | -5 | 6 | 2 | 0 | 13 | 2018-05-22 | 2018-05-06
2018-03-20 | 12 | -4 | 6 | 2 | 0 | 13 | 2018-05-23 | 2018-05-07
2018-03-21 | 13 | -3 | 6 | 2 | 0 | 13 | 2018-05-24 | 2018-05-08
2018-03-22 | 14 | -2 | 6 | 1 | 1 | 13 | 2018-05-25 | 2018-05-09
2018-03-23 | -7 | -19 | 2 | 4 | 0 | 15 | 2018-05-04 | 2018-04-22
2018-03-26 | -4 | -10 | 2 | 4 | 0 | 15 | 2018-05-07 | 2018-05-01
2018-03-27 | -3 | -9 | 2 | 4 | 0 | 15 | 2018-05-08 | 2018-05-02
2018-03-28 | -2 | -8 | 2 | 4 | 0 | 15 | 2018-05-09 | 2018-05-03
2018-03-29 | -1 | -7 | 2 | 4 | 0 | 15 | 2018-05-10 | 2018-05-04
2018-03-30 | 0 | 0 | 2 | 4 | 0 | 15 | 2018-05-11 | 2018-05-11
2018-04-02 | 9 | 3 | 2 | 4 | 0 | 15 | 2018-05-20 | 2018-05-14
2018-04-03 | 10 | 4 | 2 | 4 | 0 | 15 | 2018-05-21 | 2018-05-15
2018-04-04 | -9 | -17 | 1 | 1 | 2 | 17 | 2018-05-02 | 2018-04-24
2018-04-05 | -24 | -32 | 1 | 1 | 0 | 19 | 2018-04-17 | 2018-04-09
2018-04-06 | -23 | -31 | 1 | 1 | 0 | 19 | 2018-04-18 | 2018-04-10
2018-04-09 | -20 | -26 | 1 | 1 | 0 | 19 | 2018-04-21 | 2018-04-15
2018-04-10 | -19 | -25 | 1 | 1 | 0 | 19 | 2018-04-22 | 2018-04-16
2018-04-11 | -18 | -24 | 1 | 1 | 0 | 19 | 2018-04-23 | 2018-04-17
2018-04-12 | -17 | -27 | 1 | 1 | 0 | 20 | 2018-04-24 | 2018-04-14
2018-04-13 | -16 | -24 | 1 | 1 | 0 | 20 | 2018-04-25 | 2018-04-17
2018-04-16 | -13 | -21 | 1 | 1 | 0 | 20 | 2018-04-28 | 2018-04-20
2018-04-17 | -12 | -20 | 1 | 1 | 0 | 20 | 2018-04-29 | 2018-04-21
2018-04-18 | -11 | -17 | 1 | 1 | 0 | 20 | 2018-04-30 | 2018-04-24
2018-04-19 | -10 | -16 | 1 | 1 | 0 | 20 | 2018-05-01 | 2018-04-25
2018-04-20 | -7 | -15 | 1 | 1 | 0 | 20 | 2018-05-04 | 2018-04-26
2018-04-23 | -12 | -15 | 1 | 0 | 0 | 21 | 2018-04-29 | 2018-04-26
2018-04-24 | -11 | -14 | 0 | 1 | 0 | 21 | 2018-04-30 | 2018-04-27
2018-04-25 | -10 | -13 | 0 | 1 | 0 | 21 | 2018-05-01 | 2018-04-28
2018-04-26 | -9 | -12 | 0 | 1 | 0 | 21 | 2018-05-02 | 2018-04-29
2018-04-27 | -7 | -10 | 0 | 0 | 1 | 21 | 2018-05-04 | 2018-05-01
2018-04-30 | -4 | -7 | 0 | 0 | 1 | 21 | 2018-05-07 | 2018-05-04
2018-05-01 | -4 | -5 | 1 | 0 | 0 | 22 | 2018-05-07 | 2018-05-06
2018-05-02 | -3 | -4 | 1 | 0 | 0 | 22 | 2018-05-08 | 2018-05-07
2018-05-03 | -2 | -3 | 0 | 1 | 0 | 22 | 2018-05-09 | 2018-05-08
2018-05-04 | 0 | -1 | 0 | 1 | 0 | 22 | 2018-05-11 | 2018-05-10
2018-05-07 | 2 | 1 | 1 | 0 | 0 | 23 | 2018-05-13 | 2018-05-12
2018-05-08 | 3 | 2 | 1 | 0 | 0 | 23 | 2018-05-14 | 2018-05-13
2018-05-09 | 4 | 3 | 0 | 1 | 0 | 23 | 2018-05-15 | 2018-05-14
2018-05-10 | 5 | 5 | 0 | 1 | 0 | 23 | 2018-05-16 | 2018-05-16
2018-05-11 | 0 | 0 | 0 | 0 | 0 | 24 | 2018-05-11 | 2018-05-11

## MonteCarlo
Monte Carlo 1000 run |  |  |  | Parameters
Completion Date | Row Labels | Frequency | 2017-12-01 | Start Date
2018-04-17 | 2018-02-27 | 1 | 15 | User Stories
2018-04-20 | 2018-03-01 | 1 | 5 | Developers
2018-03-27 | 2018-03-02 | 3 | 4-16hrs | Grooming Phase
2018-03-06 | 2018-03-06 | 4 | 8-80hrs | In Progress Phase | =16-104hrs
2018-03-14 | 2018-03-07 | 2 | 2-8hrs | Review Phase
2018-03-28 | 2018-03-09 | 1 | 30% | Chance of bug raised on story
2018-06-01 | 2018-03-12 | 3 | 8-32hrs | Work required to resolve bug
2018-05-11 | 2018-03-13 | 7 | 20% | Chance of developer being absent
2018-03-28 | 2018-03-14 | 3 | 1-4days | Length of developer absence
2018-04-26 | 2018-03-15 | 3 | 2-6hrs | Developer capacity per day
2018-04-20 | 2018-03-16 | 9 | to do | Chance of new stories raised per week
2018-04-30 | 2018-03-19 | 3 | to do | Degree of dependency
2018-05-08 | 2018-03-20 | 4 | to do | Breadth of dependency
2018-04-16 | 2018-03-21 | 11 | to do | Chance of being blocked on a story
2018-03-22 | 2018-03-22 | 9 | to do | Length of block on story
2018-04-18 | 2018-03-23 | 10
2018-03-22 | 2018-03-26 | 13
2018-05-22 | 2018-03-27 | 18
2018-04-24 | 2018-03-28 | 18
2018-03-23 | 2018-03-29 | 13
2018-04-20 | 2018-03-30 | 15
2018-05-21 | 2018-04-02 | 11
2018-03-23 | 2018-04-03 | 19
2018-04-05 | 2018-04-04 | 13
2018-04-27 | 2018-04-05 | 18
2018-03-15 | 2018-04-06 | 23
2018-05-16 | 2018-04-09 | 13
2018-04-19 | 2018-04-10 | 25
2018-05-16 | 2018-04-11 | 30
2018-05-14 | 2018-04-12 | 16
2018-04-26 | 2018-04-13 | 14
2018-04-11 | 2018-04-16 | 23
2018-04-17 | 2018-04-17 | 15
2018-04-19 | 2018-04-18 | 19
2018-04-23 | 2018-04-19 | 27
2018-04-02 | 2018-04-20 | 25
2018-04-19 | 2018-04-23 | 20
2018-06-06 | 2018-04-24 | 20
2018-04-20 | 2018-04-25 | 26
2018-05-10 | 2018-04-26 | 29
2018-03-30 | 2018-04-27 | 14
2018-04-30 | 2018-04-30 | 15
2018-04-10 | 2018-05-01 | 13
2018-05-16 | 2018-05-02 | 17
2018-03-30 | 2018-05-03 | 20
2018-05-14 | 2018-05-04 | 16
2018-04-25 | 2018-05-07 | 12
2018-04-19 | 2018-05-08 | 16
2018-03-28 | 2018-05-09 | 10
2018-05-28 | 2018-05-10 | 17
2018-04-17 | 2018-05-11 | 15
2018-04-13 | 2018-05-14 | 16
2018-04-20 | 2018-05-15 | 20
2018-04-24 | 2018-05-16 | 18
2018-05-25 | 2018-05-17 | 9
2018-05-15 | 2018-05-18 | 15
2018-04-25 | 2018-05-21 | 14
2018-06-06 | 2018-05-22 | 14
2018-04-24 | 2018-05-23 | 9
2018-03-21 | 2018-05-24 | 15
2018-04-26 | 2018-05-25 | 11
2018-05-07 | 2018-05-28 | 12
2018-04-23 | 2018-05-29 | 14
2018-04-16 | 2018-05-30 | 9
2018-05-18 | 2018-05-31 | 10
2018-04-25 | 2018-06-01 | 6
2018-05-29 | 2018-06-04 | 6
2018-05-16 | 2018-06-05 | 5
2018-04-27 | 2018-06-06 | 12
2018-04-11 | 2018-06-07 | 8
2018-04-18 | 2018-06-08 | 7
2018-05-28 | 2018-06-11 | 3
2018-06-06 | 2018-06-12 | 2
2018-05-18 | 2018-06-13 | 3
2018-05-29 | 2018-06-14 | 9
2018-04-12 | 2018-06-15 | 4
2018-04-04 | 2018-06-18 | 2
2018-04-18 | 2018-06-19 | 4
2018-05-09 | 2018-06-20 | 7
2018-05-16 | 2018-06-21 | 2
2018-04-10 | 2018-06-22 | 2
2018-04-25 | 2018-06-25 | 3
2018-06-06 | 2018-06-26 | 4
2018-04-30 | 2018-06-27 | 1
2018-05-09 | 2018-06-28 | 2
2018-06-26 | 2018-07-02 | 4
2018-05-14 | 2018-07-03 | 1
2018-03-22 | 2018-07-04 | 1
2018-05-15 | 2018-07-05 | 2
2018-04-11 | 2018-07-09 | 2
2018-05-25 | 2018-07-11 | 1
2018-05-23 | 2018-07-18 | 2
2018-03-21 | 2018-07-19 | 1
2018-07-04 | 2018-07-24 | 1
2018-05-29 | 2018-07-27 | 1
2018-05-25 | 2018-08-02 | 1
2018-06-06 | 2018-08-07 | 1
2018-03-26 | 2018-08-09 | 1
2018-05-04 | 2018-08-14 | 1
2018-06-08 | Grand Total | 1000
2018-04-20
2018-03-06
2018-04-10
2018-04-10
2018-06-15
2018-04-23
2018-03-22
2018-03-01
2018-04-25
2018-07-09
2018-05-29
2018-04-09
2018-06-22
2018-04-26
2018-06-15
2018-04-18
2018-04-23
2018-04-25
2018-05-03
2018-04-13
2018-03-27
2018-04-26
2018-03-28
2018-03-21
2018-05-09
2018-04-26
2018-04-24
2018-03-21
2018-04-13
2018-04-09
2018-04-12
2018-04-05
2018-05-31
2018-04-11
2018-05-29
2018-05-14
2018-06-28
2018-03-27
2018-05-11
2018-06-05
2018-05-18
2018-04-19
2018-03-30
2018-05-23
2018-06-01
2018-04-12
2018-05-08
2018-03-29
2018-03-19
2018-05-31
2018-03-26
2018-04-05
2018-04-11
2018-03-29
2018-05-16
2018-03-27
2018-05-29
2018-05-10
2018-04-30
2018-04-19
2018-05-09
2018-04-06
2018-05-18
2018-05-10
2018-04-20
2018-04-02
2018-06-04
2018-05-03
2018-04-05
2018-05-16
2018-05-02
2018-05-10
2018-06-07
2018-05-15
2018-05-18
2018-03-28
2018-04-12
2018-04-25
2018-04-09
2018-05-08
2018-06-06
2018-04-24
2018-03-13
2018-05-31
2018-05-16
2018-04-12
2018-04-04
2018-05-17
2018-06-06
2018-05-15
2018-04-16
2018-08-09
2018-04-11
2018-04-04
2018-04-12
2018-04-19
2018-05-16
2018-05-18
2018-05-24
2018-07-02
2018-04-06
2018-04-09
2018-04-12
2018-04-20
2018-04-03
2018-04-03
2018-03-21
2018-03-26
2018-05-22
2018-04-26
2018-04-16
2018-04-06
2018-03-30
2018-04-18
2018-04-11
2018-05-08
2018-04-05
2018-05-24
2018-05-24
2018-04-11
2018-04-04
2018-04-20
2018-03-30
2018-05-22
2018-04-03
2018-04-26
2018-03-29
2018-05-07
2018-06-05
2018-05-24
2018-04-02
2018-05-22
2018-03-12
2018-03-13
2018-06-04
2018-05-25
2018-05-28
2018-05-01
2018-05-31
2018-06-20
2018-05-15
2018-05-28
2018-03-28
2018-04-09
2018-04-20
2018-07-09
2018-05-17
2018-03-27
2018-04-04
2018-05-10
2018-04-23
2018-05-24
2018-03-27
2018-06-06
2018-04-06
2018-04-06
2018-04-16
2018-03-22
2018-04-18
2018-03-22
2018-04-25
2018-03-23
2018-04-20
2018-03-28
2018-04-25
2018-04-26
2018-03-13
2018-05-14
2018-07-05
2018-04-03
2018-05-14
2018-06-14
2018-04-27
2018-03-29
2018-03-12
2018-05-02
2018-04-10
2018-04-10
2018-04-10
2018-04-16
2018-08-02
2018-04-17
2018-03-28
2018-03-27
2018-04-17
2018-04-25
2018-04-10
2018-05-03
2018-05-18
2018-05-08
2018-04-16
2018-03-27
2018-04-25
2018-05-01
2018-05-01
2018-05-09
2018-06-14
2018-05-10
2018-05-09
2018-03-28
2018-05-15
2018-04-26
2018-06-20
2018-04-06
2018-05-28
2018-04-30
2018-03-28
2018-05-16
2018-04-19
2018-05-30
2018-04-13
2018-04-12
2018-05-04
2018-04-16
2018-05-02
2018-05-21
2018-05-31
2018-05-03
2018-04-19
2018-06-22
2018-06-20
2018-04-06
2018-06-01
2018-05-14
2018-05-18
2018-04-17
2018-05-02
2018-03-28
2018-05-10
2018-05-22
2018-05-02
2018-03-27
2018-04-06
2018-05-01
2018-04-04
2018-04-23
2018-04-24
2018-05-23
2018-06-06
2018-05-11
2018-03-26
2018-05-01
2018-04-13
2018-03-26
2018-04-25
2018-04-24
2018-03-21
2018-04-19
2018-05-24
2018-08-07
2018-05-31
2018-03-27
2018-04-30
2018-05-04
2018-06-18
2018-04-16
2018-04-13
2018-03-14
2018-03-26
2018-03-16
2018-04-03
2018-05-09
2018-03-21
2018-04-16
2018-04-03
2018-04-19
2018-04-04
2018-05-08
2018-06-12
2018-03-16
2018-05-29
2018-05-31
2018-05-15
2018-03-12
2018-04-16
2018-03-30
2018-04-03
2018-04-13
2018-04-20
2018-05-04
2018-05-24
2018-04-03
2018-05-07
2018-04-02
2018-04-20
2018-04-23
2018-04-23
2018-05-02
2018-04-04
2018-03-16
2018-05-18
2018-05-24
2018-05-16
2018-04-16
2018-05-02
2018-05-28
2018-04-06
2018-03-20
2018-04-03
2018-06-08
2018-05-15
2018-06-04
2018-05-03
2018-05-04
2018-04-16
2018-03-20
2018-03-20
2018-05-25
2018-03-27
2018-04-19
2018-05-28
2018-05-04
2018-04-26
2018-04-10
2018-06-21
2018-05-22
2018-04-16
2018-05-22
2018-04-25
2018-05-17
2018-04-18
2018-05-10
2018-04-11
2018-05-22
2018-05-11
2018-05-15
2018-04-25
2018-05-07
2018-05-28
2018-04-26
2018-05-24
2018-04-26
2018-05-01
2018-03-27
2018-04-27
2018-05-10
2018-05-22
2018-03-21
2018-04-18
2018-04-30
2018-04-10
2018-05-22
2018-05-25
2018-04-24
2018-03-13
2018-06-08
2018-06-19
2018-05-08
2018-04-30
2018-05-24
2018-06-20
2018-05-11
2018-04-30
2018-06-06
2018-04-11
2018-05-23
2018-03-30
2018-05-02
2018-07-05
2018-04-27
2018-04-13
2018-04-04
2018-04-06
2018-06-05
2018-04-17
2018-04-24
2018-03-28
2018-05-28
2018-04-11
2018-05-03
2018-03-28
2018-04-19
2018-05-04
2018-04-06
2018-04-05
2018-04-05
2018-04-16
2018-04-11
2018-06-08
2018-03-28
2018-06-07
2018-05-30
2018-04-24
2018-03-13
2018-05-28
2018-05-17
2018-06-14
2018-03-13
2018-04-16
2018-04-17
2018-04-10
2018-06-11
2018-04-11
2018-05-07
2018-03-21
2018-05-14
2018-06-19
2018-04-04
2018-05-21
2018-06-14
2018-04-05
2018-08-14
2018-04-06
2018-04-24
2018-04-23
2018-04-11
2018-04-25
2018-04-09
2018-04-05
2018-05-17
2018-05-07
2018-05-14
2018-05-15
2018-05-07
2018-03-23
2018-05-15
2018-04-04
2018-05-10
2018-04-27
2018-05-21
2018-04-18
2018-06-25
2018-05-08
2018-03-02
2018-05-24
2018-03-16
2018-04-25
2018-05-18
2018-05-15
2018-05-14
2018-04-12
2018-06-26
2018-04-18
2018-04-06
2018-03-26
2018-05-15
2018-05-30
2018-04-06
2018-05-03
2018-04-24
2018-03-30
2018-05-24
2018-04-02
2018-04-19
2018-03-28
2018-04-23
2018-04-20
2018-05-02
2018-04-02
2018-05-21
2018-04-05
2018-05-11
2018-06-15
2018-04-23
2018-07-24
2018-05-21
2018-04-27
2018-05-30
2018-05-04
2018-04-26
2018-04-03
2018-03-07
2018-05-04
2018-03-30
2018-05-03
2018-06-18
2018-03-19
2018-04-06
2018-04-25
2018-04-24
2018-04-26
2018-03-29
2018-04-11
2018-04-30
2018-06-08
2018-05-01
2018-04-23
2018-05-15
2018-04-30
2018-06-07
2018-05-03
2018-04-10
2018-05-29
2018-04-09
2018-05-03
2018-04-19
2018-06-14
2018-05-03
2018-04-06
2018-03-29
2018-03-22
2018-04-18
2018-04-12
2018-04-20
2018-05-29
2018-04-06
2018-04-23
2018-04-20
2018-04-10
2018-04-30
2018-04-30
2018-05-03
2018-04-03
2018-05-01
2018-04-16
2018-04-26
2018-05-22
2018-07-02
2018-05-18
2018-04-18
2018-04-23
2018-04-10
2018-06-19
2018-05-17
2018-04-30
2018-04-26
2018-04-18
2018-03-29
2018-04-26
2018-04-06
2018-04-17
2018-04-06
2018-05-14
2018-03-06
2018-07-02
2018-04-18
2018-07-02
2018-05-03
2018-03-14
2018-04-27
2018-06-04
2018-04-10
2018-04-12
2018-03-27
2018-07-27
2018-05-17
2018-05-14
2018-04-11
2018-05-18
2018-05-11
2018-05-30
2018-05-01
2018-07-11
2018-04-24
2018-06-12
2018-03-06
2018-04-10
2018-04-12
2018-04-11
2018-04-06
2018-04-10
2018-04-10
2018-03-16
2018-05-25
2018-04-19
2018-04-12
2018-05-07
2018-05-22
2018-03-26
2018-05-09
2018-05-29
2018-04-17
2018-04-03
2018-04-20
2018-03-30
2018-03-09
2018-05-09
2018-05-28
2018-03-15
2018-05-31
2018-04-25
2018-06-08
2018-03-27
2018-04-25
2018-04-20
2018-04-25
2018-05-29
2018-05-16
2018-05-02
2018-05-02
2018-04-18
2018-04-27
2018-04-19
2018-05-04
2018-05-14
2018-03-27
2018-05-21
2018-04-13
2018-04-19
2018-04-20
2018-03-22
2018-06-07
2018-04-12
2018-04-19
2018-04-10
2018-06-20
2018-03-30
2018-04-13
2018-05-21
2018-03-13
2018-05-01
2018-04-03
2018-04-23
2018-05-08
2018-04-19
2018-06-07
2018-03-26
2018-04-11
2018-04-26
2018-03-26
2018-05-31
2018-06-04
2018-05-11
2018-05-15
2018-04-02
2018-05-08
2018-04-09
2018-03-30
2018-04-10
2018-04-25
2018-05-10
2018-03-20
2018-04-26
2018-04-11
2018-06-07
2018-06-13
2018-05-03
2018-03-26
2018-04-05
2018-04-03
2018-06-06
2018-04-16
2018-03-16
2018-04-03
2018-04-09
2018-03-28
2018-04-09
2018-05-04
2018-05-08
2018-04-11
2018-04-23
2018-04-05
2018-04-27
2018-04-20
2018-04-03
2018-04-12
2018-03-07
2018-04-11
2018-04-11
2018-06-13
2018-04-20
2018-05-29
2018-05-25
2018-05-21
2018-05-18
2018-04-25
2018-05-18
2018-06-14
2018-06-28
2018-05-11
2018-03-02
2018-06-13
2018-04-23
2018-06-11
2018-03-29
2018-06-05
2018-03-27
2018-04-11
2018-05-10
2018-06-01
2018-06-07
2018-05-29
2018-04-24
2018-04-20
2018-04-19
2018-05-03
2018-04-06
2018-06-15
2018-05-29
2018-03-27
2018-05-02
2018-05-11
2018-05-17
2018-05-02
2018-06-26
2018-05-11
2018-06-14
2018-04-26
2018-07-18
2018-05-08
2018-04-13
2018-04-02
2018-04-25
2018-05-03
2018-04-05
2018-05-24
2018-04-04
2018-03-30
2018-05-07
2018-05-21
2018-05-10
2018-04-10
2018-03-22
2018-03-26
2018-05-08
2018-05-21
2018-04-11
2018-03-29
2018-04-17
2018-04-11
2018-04-27
2018-03-16
2018-04-27
2018-06-14
2018-05-22
2018-04-16
2018-05-30
2018-05-30
2018-05-23
2018-05-07
2018-04-19
2018-04-20
2018-05-04
2018-04-18
2018-04-11
2018-05-14
2018-04-18
2018-04-26
2018-04-26
2018-07-03
2018-04-03
2018-05-10
2018-04-17
2018-05-07
2018-03-21
2018-04-23
2018-05-09
2018-04-12
2018-05-02
2018-04-24
2018-05-15
2018-05-10
2018-05-15
2018-05-07
2018-06-19
2018-03-29
2018-04-10
2018-04-03
2018-04-05
2018-06-20
2018-05-14
2018-04-25
2018-03-23
2018-05-16
2018-05-23
2018-04-10
2018-04-19
2018-05-03
2018-03-26
2018-04-18
2018-04-10
2018-05-24
2018-05-04
2018-05-30
2018-05-11
2018-04-19
2018-04-25
2018-07-19
2018-04-11
2018-03-29
2018-05-16
2018-04-26
2018-05-03
2018-05-22
2018-04-19
2018-04-03
2018-05-25
2018-04-19
2018-05-15
2018-04-30
2018-05-17
2018-04-02
2018-04-05
2018-04-20
2018-03-02
2018-05-23
2018-03-23
2018-05-02
2018-06-21
2018-04-17
2018-05-24
2018-04-24
2018-03-21
2018-03-28
2018-04-25
2018-05-16
2018-05-04
2018-07-18
2018-05-18
2018-05-15
2018-04-26
2018-05-11
2018-04-17
2018-05-04
2018-04-16
2018-05-03
2018-04-05
2018-04-16
2018-05-08
2018-04-11
2018-05-16
2018-04-02
2018-04-24
2018-03-23
2018-04-06
2018-06-04
2018-06-27
2018-03-23
2018-03-28
2018-05-02
2018-04-02
2018-05-15
2018-06-26
2018-05-10
2018-06-01
2018-04-24
2018-04-09
2018-04-23
2018-04-13
2018-04-27
2018-04-23
2018-05-28
2018-04-26
2018-03-30
2018-05-08
2018-06-14
2018-03-23
2018-04-04
2018-03-29
2018-05-01
2018-04-05
2018-05-23
2018-05-01
2018-05-30
2018-05-31
2018-05-16
2018-05-16
2018-05-08
2018-06-06
2018-04-10
2018-04-19
2018-06-08
2018-05-21
2018-04-27
2018-05-23
2018-04-26
2018-05-10
2018-06-25
2018-02-27
2018-04-18
2018-05-02
2018-06-11
2018-06-01
2018-04-06
2018-04-26
2018-04-20
2018-05-03
2018-04-09
2018-03-15
2018-04-16
2018-05-25
2018-05-25
2018-05-04
2018-03-27
2018-04-11
2018-04-13
2018-05-11
2018-04-17
2018-04-26
2018-04-11
2018-04-05
2018-04-13
2018-05-21
2018-05-01
2018-05-21
2018-04-16
2018-06-07
2018-06-05
2018-06-25
2018-04-09
2018-06-20
2018-05-14
2018-04-24
2018-03-23
2018-03-16
2018-03-19
2018-05-11
2018-03-29
2018-03-16
2018-03-30
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## MonteCarlo (2)
Monte Carlo 1000 run |  |  |  | Parameters
Completion Date | Row Labels | Freq | 2017-12-01 | Start Date
2018-05-10 | 2018-03-06 | 1 | 15 | User Stories
2018-06-08 | 2018-03-15 | 1 | 5 | Developers
2018-07-04 | 2018-03-16 | 1 | 4-16hrs | Grooming Phase
2018-04-12 | 2018-03-19 | 1 | 8-80hrs | In Progress Phase | =16-104hrs
2018-08-24 | 2018-03-27 | 1 | 2-8hrs | Review Phase
2018-10-05 | 2018-03-28 | 1 | 30% | Chance of bug raised on story
2018-08-10 | 2018-03-30 | 1 | 8-32hrs | Work required to resolve bug
2018-10-10 | 2018-04-02 | 2 | 20% | Chance of developer being absent
2018-08-31 | 2018-04-03 | 3 | 1-4days | Length of developer absence
2018-05-09 | 2018-04-04 | 1 | 2-6hrs | Developer capacity per day
2018-10-11 | 2018-04-05 | 2 | 0-3 | Number of stories added every 4w
2018-07-25 | 2018-04-06 | 2 | to do | Degree of dependency
2018-09-21 | 2018-04-09 | 5 | to do | Breadth of dependency
2018-08-09 | 2018-04-10 | 3 | to do | Chance of being blocked on a story
2018-08-14 | 2018-04-11 | 1 | to do | Length of block on story
2018-11-01 | 2018-04-12 | 4
2018-12-20 | 2018-04-13 | 4
2019-02-01 | 2018-04-16 | 2
2018-12-11 | 2018-04-17 | 2
2018-09-14 | 2018-04-18 | 6
2018-10-08 | 2018-04-19 | 1
2018-07-03 | 2018-04-20 | 2
2018-09-27 | 2018-04-23 | 4
2018-04-12 | 2018-04-24 | 1
2018-06-27 | 2018-04-25 | 5
2018-05-08 | 2018-04-26 | 4
2018-12-24 | 2018-04-27 | 2
2018-06-15 | 2018-04-30 | 2
2018-05-11 | 2018-05-01 | 8
2018-10-18 | 2018-05-02 | 6
2018-06-14 | 2018-05-03 | 10
2018-05-07 | 2018-05-04 | 6
2018-10-24 | 2018-05-07 | 10
2018-06-01 | 2018-05-08 | 14
2018-08-10 | 2018-05-09 | 12
2018-10-08 | 2018-05-10 | 13
2018-07-06 | 2018-05-11 | 5
2018-08-15 | 2018-05-14 | 1
2018-05-25 | 2018-05-15 | 1
2018-08-08 | 2018-05-16 | 3
2018-09-19 | 2018-05-17 | 2
2018-05-08 | 2018-05-18 | 4
2018-06-11 | 2018-05-21 | 3
2018-05-10 | 2018-05-22 | 8
2018-08-31 | 2018-05-23 | 9
2018-09-03 | 2018-05-24 | 7
2018-08-21 | 2018-05-25 | 12
2018-09-27 | 2018-05-28 | 5
2018-06-08 | 2018-05-29 | 8
2018-10-18 | 2018-05-30 | 10
2018-05-31 | 2018-05-31 | 12
2018-07-04 | 2018-06-01 | 13
2018-10-16 | 2018-06-04 | 11
2018-08-29 | 2018-06-05 | 14
2018-05-22 | 2018-06-06 | 10
2018-05-08 | 2018-06-07 | 12
2018-05-07 | 2018-06-08 | 15
2018-06-08 | 2018-06-11 | 4
2018-07-13 | 2018-06-12 | 3
2018-07-16 | 2018-06-13 | 4
2018-08-06 | 2018-06-14 | 3
2018-07-27 | 2018-06-15 | 3
2018-04-05 | 2018-06-18 | 7
2018-05-31 | 2018-06-19 | 10
2018-07-13 | 2018-06-20 | 5
2018-08-02 | 2018-06-21 | 8
2018-07-05 | 2018-06-22 | 6
2018-07-03 | 2018-06-25 | 9
2018-10-18 | 2018-06-26 | 5
2018-08-07 | 2018-06-27 | 9
2018-10-19 | 2018-06-28 | 5
2018-09-24 | 2018-06-29 | 9
2018-09-11 | 2018-07-02 | 12
2018-10-26 | 2018-07-03 | 15
2018-05-29 | 2018-07-04 | 10
2018-05-23 | 2018-07-05 | 12
2018-04-25 | 2018-07-06 | 18
2018-11-20 | 2018-07-09 | 6
2018-12-11 | 2018-07-10 | 5
2018-08-03 | 2018-07-11 | 2
2018-05-25 | 2018-07-12 | 4
2018-07-19 | 2018-07-13 | 5
2018-05-22 | 2018-07-16 | 2
2018-07-12 | 2018-07-17 | 7
2018-08-17 | 2018-07-18 | 6
2018-12-13 | 2018-07-19 | 11
2018-04-13 | 2018-07-20 | 2
2018-08-21 | 2018-07-23 | 7
2018-06-05 | 2018-07-24 | 8
2018-05-22 | 2018-07-25 | 14
2018-07-30 | 2018-07-26 | 13
2018-07-26 | 2018-07-27 | 14
2018-05-31 | 2018-07-30 | 12
2018-08-08 | 2018-07-31 | 11
2018-05-29 | 2018-08-01 | 11
2018-07-24 | 2018-08-02 | 11
2018-07-26 | 2018-08-03 | 10
2018-06-18 | 2018-08-06 | 3
2018-05-08 | 2018-08-07 | 2
2018-04-09 | 2018-08-08 | 6
2018-09-25 | 2018-08-09 | 4
2018-05-09 | 2018-08-10 | 5
2018-08-29 | 2018-08-14 | 7
2018-08-31 | 2018-08-15 | 3
2018-06-05 | 2018-08-16 | 5
2018-07-19 | 2018-08-17 | 9
2018-08-08 | 2018-08-20 | 15
2018-10-19 | 2018-08-21 | 8
2018-10-23 | 2018-08-22 | 5
2018-07-23 | 2018-08-23 | 4
2018-11-12 | 2018-08-24 | 9
2018-08-02 | 2018-08-27 | 5
2018-07-25 | 2018-08-28 | 2
2019-01-15 | 2018-08-29 | 9
2018-12-04 | 2018-08-30 | 6
2018-05-10 | 2018-08-31 | 7
2018-07-25 | 2018-09-03 | 3
2018-06-29 | 2018-09-04 | 5
2018-06-04 | 2018-09-05 | 7
2018-06-25 | 2018-09-06 | 5
2018-05-23 | 2018-09-07 | 4
2019-05-20 | 2018-09-10 | 1
2018-08-30 | 2018-09-11 | 4
2018-11-08 | 2018-09-12 | 5
2018-05-29 | 2018-09-13 | 6
2018-09-14 | 2018-09-14 | 7
2018-06-27 | 2018-09-17 | 6
2018-05-02 | 2018-09-18 | 1
2018-08-27 | 2018-09-19 | 8
2018-07-06 | 2018-09-20 | 6
2018-08-01 | 2018-09-21 | 6
2018-04-09 | 2018-09-24 | 6
2018-07-26 | 2018-09-25 | 7
2018-10-12 | 2018-09-26 | 3
2018-04-04 | 2018-09-27 | 10
2018-08-24 | 2018-09-28 | 7
2018-07-25 | 2018-10-01 | 1
2019-04-03 | 2018-10-02 | 1
2018-07-03 | 2018-10-03 | 2
2018-06-27 | 2018-10-05 | 7
2018-10-09 | 2018-10-08 | 2
2018-08-31 | 2018-10-09 | 2
2018-08-08 | 2018-10-10 | 1
2018-06-05 | 2018-10-11 | 3
2018-07-25 | 2018-10-12 | 2
2018-06-08 | 2018-10-15 | 2
2018-10-11 | 2018-10-16 | 4
2018-06-06 | 2018-10-17 | 2
2018-07-31 | 2018-10-18 | 4
2018-07-06 | 2018-10-19 | 6
2018-11-20 | 2018-10-22 | 5
2018-08-16 | 2018-10-23 | 3
2018-10-24 | 2018-10-24 | 5
2018-05-09 | 2018-10-25 | 2
2018-05-03 | 2018-10-26 | 3
2018-05-08 | 2018-10-29 | 1
2018-07-02 | 2018-10-31 | 4
2018-09-12 | 2018-11-01 | 4
2018-05-07 | 2018-11-02 | 2
2018-05-16 | 2018-11-07 | 3
2018-07-05 | 2018-11-08 | 4
2018-04-11 | 2018-11-09 | 3
2018-08-14 | 2018-11-12 | 4
2018-03-19 | 2018-11-13 | 1
2018-10-05 | 2018-11-14 | 2
2018-10-16 | 2018-11-15 | 4
2018-07-06 | 2018-11-19 | 2
2018-08-02 | 2018-11-20 | 2
2018-05-10 | 2018-11-21 | 4
2018-08-14 | 2018-11-22 | 3
2018-12-20 | 2018-11-23 | 1
2018-10-22 | 2018-11-30 | 2
2018-06-19 | 2018-12-04 | 1
2018-09-27 | 2018-12-05 | 2
2018-06-18 | 2018-12-06 | 3
2018-07-25 | 2018-12-07 | 3
2018-05-07 | 2018-12-11 | 2
2018-11-22 | 2018-12-12 | 1
2018-10-26 | 2018-12-13 | 1
2018-07-26 | 2018-12-14 | 1
2018-07-17 | 2018-12-17 | 1
2018-06-22 | 2018-12-19 | 2
2018-07-06 | 2018-12-20 | 2
2018-07-24 | 2018-12-21 | 1
2018-07-02 | 2018-12-24 | 1
2018-07-03 | 2018-12-26 | 1
2018-06-08 | 2018-12-27 | 1
2018-08-16 | 2019-01-01 | 2
2018-05-30 | 2019-01-02 | 1
2018-06-06 | 2019-01-04 | 2
2018-12-07 | 2019-01-15 | 1
2018-05-25 | 2019-01-17 | 1
2018-07-25 | 2019-01-18 | 1
2018-08-17 | 2019-01-30 | 2
2018-08-01 | 2019-01-31 | 1
2018-07-09 | 2019-02-01 | 1
2018-09-13 | 2019-02-05 | 1
2018-06-29 | 2019-02-06 | 1
2018-06-21 | 2019-02-07 | 1
2018-12-19 | 2019-02-12 | 1
2018-09-07 | 2019-02-15 | 1
2018-04-26 | 2019-03-05 | 1
2019-03-08 | 2019-03-08 | 1
2018-05-24 | 2019-03-12 | 1
2018-12-05 | 2019-03-15 | 1
2018-09-04 | 2019-04-03 | 1
2018-04-12 | 2019-04-04 | 2
2019-02-07 | 2019-04-24 | 1
2018-09-19 | 2019-05-20 | 1
2018-05-07 | Grand Total | 1000
2018-06-13
2018-05-04
2018-07-20
2018-09-17
2018-05-02
2018-04-25
2018-11-12
2018-06-22
2018-05-21
2018-03-15
2018-09-20
2018-05-01
2018-08-01
2018-09-11
2018-07-03
2018-06-26
2018-08-01
2018-08-09
2018-04-17
2018-05-04
2018-12-06
2018-07-17
2018-10-19
2019-01-30
2018-10-23
2018-06-01
2019-04-24
2018-06-05
2019-02-06
2018-05-08
2018-07-31
2018-07-06
2018-09-28
2018-06-25
2018-08-06
2018-04-03
2018-09-05
2018-06-11
2018-09-21
2018-07-12
2018-07-05
2018-07-31
2018-09-14
2018-07-03
2018-08-21
2018-06-19
2018-05-04
2018-04-09
2019-01-02
2019-01-04
2018-09-13
2018-10-15
2018-09-28
2018-09-13
2018-07-27
2018-08-03
2018-08-21
2018-05-09
2018-07-23
2018-07-18
2018-05-25
2018-05-23
2018-07-12
2018-05-01
2018-06-29
2018-11-07
2018-05-03
2018-06-01
2018-09-20
2018-06-21
2018-11-14
2019-01-17
2018-05-31
2018-04-23
2018-11-15
2018-11-09
2018-09-06
2018-11-07
2018-08-20
2018-06-19
2018-07-27
2018-05-11
2018-06-04
2018-09-03
2018-05-03
2018-06-27
2018-07-06
2018-11-30
2018-08-20
2018-06-05
2018-10-31
2018-09-13
2018-05-30
2018-07-25
2018-12-12
2018-07-30
2018-05-09
2018-06-19
2018-05-17
2018-05-10
2018-08-17
2018-07-24
2018-06-06
2018-07-30
2018-06-27
2018-06-08
2018-08-31
2018-06-20
2018-05-02
2018-05-01
2018-10-16
2018-06-13
2018-12-19
2018-07-02
2018-06-05
2018-08-29
2018-05-10
2018-06-04
2018-07-06
2018-11-12
2018-05-07
2018-04-25
2018-05-18
2018-06-18
2018-06-08
2018-08-20
2018-08-21
2018-04-12
2018-07-05
2018-07-17
2018-09-26
2018-04-09
2018-05-07
2018-07-23
2018-11-21
2018-07-05
2018-08-03
2018-05-29
2018-06-01
2018-10-17
2018-06-01
2018-05-01
2018-09-05
2018-09-21
2018-04-23
2018-11-30
2018-05-24
2018-06-08
2018-06-19
2018-08-20
2018-08-03
2018-06-06
2018-07-02
2018-09-12
2018-06-21
2018-06-08
2018-08-16
2018-05-25
2018-05-03
2018-09-25
2018-05-08
2018-08-29
2018-08-01
2018-11-07
2018-06-06
2018-04-26
2018-06-04
2018-06-29
2018-07-19
2018-07-19
2018-06-25
2018-07-17
2018-08-29
2018-09-21
2018-10-19
2018-06-21
2019-02-05
2018-05-23
2018-05-08
2018-07-27
2018-05-07
2018-07-18
2018-10-24
2018-04-23
2018-10-24
2018-07-26
2018-06-26
2018-05-31
2018-06-01
2018-06-04
2018-07-03
2018-05-29
2018-05-09
2019-01-31
2018-06-07
2018-05-09
2018-04-30
2018-10-03
2018-07-03
2018-11-01
2018-09-11
2018-09-27
2018-06-26
2018-05-18
2018-03-06
2018-08-20
2018-06-26
2018-09-04
2018-09-06
2018-08-21
2018-08-30
2018-07-17
2018-05-28
2018-06-06
2018-12-14
2018-07-19
2018-11-23
2018-05-24
2018-04-02
2018-07-10
2018-05-22
2018-05-04
2018-08-03
2018-07-06
2018-06-05
2018-04-09
2018-09-14
2018-05-10
2018-07-03
2018-06-29
2018-08-17
2018-10-05
2018-08-14
2018-07-12
2018-03-27
2018-05-23
2018-08-20
2018-11-22
2018-08-17
2018-05-31
2018-06-25
2018-06-22
2018-10-22
2018-05-23
2018-06-25
2018-09-28
2018-07-18
2018-05-03
2018-11-15
2018-05-03
2018-06-07
2018-07-04
2018-04-27
2018-11-19
2019-04-04
2018-07-31
2018-06-14
2018-04-05
2018-10-26
2018-04-06
2018-07-02
2018-07-02
2018-06-01
2018-08-28
2018-03-28
2018-10-25
2018-05-28
2018-12-26
2018-05-10
2018-06-01
2018-06-21
2018-08-10
2018-09-14
2018-08-23
2018-11-14
2018-07-04
2018-06-04
2018-09-14
2018-06-28
2018-10-19
2018-06-27
2018-08-09
2018-07-26
2018-06-06
2018-07-02
2018-06-18
2018-10-22
2018-05-30
2018-07-25
2018-11-15
2018-09-19
2018-08-20
2018-07-30
2018-09-27
2018-08-27
2018-09-25
2018-05-08
2018-11-09
2018-07-04
2018-09-10
2018-04-19
2018-08-08
2018-05-09
2018-06-29
2018-08-22
2018-08-24
2018-10-17
2018-06-07
2018-06-11
2018-08-22
2018-05-18
2018-09-19
2018-08-03
2018-08-30
2018-10-31
2018-06-25
2018-07-26
2018-08-23
2018-04-26
2018-08-24
2018-08-16
2018-06-04
2018-08-22
2019-01-01
2018-06-08
2018-07-03
2018-05-25
2018-07-13
2018-07-04
2018-11-21
2018-06-27
2018-06-07
2018-09-19
2018-06-12
2018-06-18
2018-07-27
2018-09-12
2018-05-21
2018-08-06
2018-05-23
2018-07-27
2018-07-30
2018-07-17
2018-08-02
2018-10-05
2018-07-17
2018-08-31
2018-08-31
2018-07-26
2018-04-16
2018-07-06
2018-08-15
2018-09-20
2018-09-24
2018-05-30
2018-08-24
2018-08-23
2018-06-05
2018-04-17
2018-05-18
2018-07-10
2018-08-21
2018-08-01
2018-05-02
2018-11-01
2018-09-06
2018-06-15
2018-11-22
2018-08-20
2018-08-17
2018-07-26
2018-09-14
2018-09-17
2018-08-20
2018-08-17
2018-06-21
2018-09-24
2018-08-14
2018-08-27
2018-07-26
2018-07-31
2018-09-25
2018-07-30
2018-06-25
2018-11-13
2018-07-26
2018-09-17
2018-06-21
2018-06-01
2018-09-27
2018-06-05
2018-05-24
2018-05-02
2018-06-07
2018-07-31
2018-10-19
2018-07-06
2018-07-06
2018-04-18
2018-09-05
2018-11-08
2018-06-07
2018-07-05
2018-09-28
2018-09-19
2018-06-29
2018-07-24
2018-08-14
2018-09-05
2018-08-03
2018-07-13
2018-10-25
2018-09-20
2018-07-27
2018-05-31
2018-07-09
2018-08-21
2018-07-31
2018-06-28
2018-04-20
2018-09-05
2018-07-30
2018-07-24
2018-07-11
2018-06-13
2018-07-24
2018-05-31
2018-07-05
2018-10-05
2018-08-02
2018-06-05
2018-10-31
2018-05-31
2018-10-05
2018-05-10
2018-08-01
2019-04-04
2018-05-01
2018-06-08
2018-07-27
2018-07-06
2018-05-07
2018-11-09
2018-05-22
2018-11-12
2018-09-26
2018-08-20
2018-06-19
2018-12-06
2018-05-25
2018-07-09
2018-08-29
2018-09-05
2019-03-12
2018-05-08
2018-12-21
2018-08-28
2018-04-18
2018-08-02
2018-10-02
2018-05-09
2018-10-22
2018-07-30
2018-08-20
2018-09-06
2018-05-24
2018-06-01
2018-05-08
2018-09-12
2018-05-28
2018-08-01
2018-07-25
2018-06-28
2018-06-04
2018-10-11
2018-08-02
2018-08-02
2018-05-21
2018-10-05
2018-07-06
2018-09-24
2018-09-25
2018-06-01
2018-07-09
2018-08-24
2018-09-28
2018-08-16
2018-07-31
2018-08-30
2018-08-01
2019-02-12
2018-07-06
2018-07-09
2018-07-16
2018-07-04
2018-04-10
2018-08-20
2018-08-20
2018-04-18
2018-09-28
2018-08-17
2018-12-17
2018-05-09
2018-07-26
2018-12-05
2018-08-22
2018-06-07
2018-09-17
2018-03-16
2018-04-20
2018-07-30
2018-06-01
2018-06-28
2018-07-25
2018-04-06
2018-05-01
2018-05-23
2018-07-05
2018-05-10
2018-11-21
2018-09-27
2018-09-06
2018-09-17
2018-04-02
2018-07-10
2018-05-25
2018-05-31
2018-04-25
2018-07-05
2018-06-20
2018-04-10
2018-05-08
2018-07-25
2018-05-16
2018-06-07
2018-10-09
2018-05-10
2018-05-30
2018-05-09
2018-04-18
2018-10-18
2018-09-24
2018-06-20
2018-06-21
2018-09-19
2018-11-08
2018-05-15
2018-06-07
2018-08-29
2018-04-25
2018-06-19
2019-01-18
2018-06-28
2018-07-06
2018-10-23
2018-05-10
2019-01-04
2018-07-19
2018-07-05
2018-11-02
2018-07-09
2018-07-03
2018-06-08
2018-04-10
2018-07-02
2018-06-05
2018-06-14
2018-05-30
2018-12-27
2018-09-07
2018-07-30
2018-07-06
2018-09-18
2018-08-02
2018-04-03
2018-05-03
2018-06-04
2018-05-29
2018-09-27
2018-11-21
2018-07-04
2018-09-04
2018-07-23
2018-07-04
2018-06-19
2018-09-20
2018-08-03
2018-11-19
2018-07-02
2018-05-30
2018-08-20
2018-07-19
2018-05-08
2018-05-09
2019-02-15
2018-07-11
2018-06-07
2018-05-31
2018-09-17
2018-07-03
2018-07-19
2018-04-03
2018-07-05
2018-07-26
2018-08-01
2018-06-29
2018-10-29
2018-09-12
2018-07-20
2018-07-19
2018-05-25
2018-06-11
2018-04-26
2018-09-20
2018-11-01
2018-08-24
2018-07-18
2018-06-20
2018-11-15
2018-06-12
2018-04-13
2018-07-04
2018-07-02
2018-07-02
2018-06-22
2018-08-27
2018-07-02
2018-12-06
2018-05-03
2018-06-13
2018-11-08
2018-07-27
2018-08-23
2018-05-08
2018-05-01
2018-08-09
2018-09-04
2019-01-30
2018-08-22
2018-04-18
2018-06-27
2018-08-27
2019-01-01
2018-05-28
2018-06-22
2018-08-01
2018-06-06
2018-06-08
2018-08-07
2018-05-14
2018-06-12
2018-07-18
2018-07-05
2018-05-29
2018-09-19
2018-09-13
2018-09-25
2018-07-30
2018-05-16
2018-05-02
2018-07-27
2018-07-24
2018-09-03
2018-03-30
2018-08-08
2018-09-21
2018-05-24
2018-07-10
2018-06-18
2018-07-25
2018-09-26
2018-07-06
2018-05-11
2018-05-30
2018-12-07
2018-05-04
2018-05-30
2018-09-11
2018-05-29
2018-05-22
2018-08-30
2018-07-27
2018-07-03
2018-06-05
2018-06-22
2018-09-07
2018-09-27
2018-05-25
2018-08-29
2018-07-18
2018-05-11
2018-06-15
2018-08-24
2018-06-06
2018-07-23
2018-08-10
2018-06-04
2018-04-30
2018-05-01
2019-03-05
2018-07-03
2018-05-11
2018-09-25
2018-06-29
2018-06-25
2018-05-31
2018-05-30
2018-09-27
2018-10-03
2018-06-04
2018-06-05
2018-07-31
2018-05-25
2018-07-27
2018-06-08
2018-04-27
2018-06-18
2018-07-23
2018-04-24
2018-08-03
2018-07-24
2018-10-01
2018-07-31
2018-07-25
2018-10-31
2019-03-15
2018-05-24
2018-06-06
2018-08-14
2018-06-20
2018-04-13
2018-08-20
2018-08-24
2018-05-22
2018-07-31
2018-09-28
2018-08-02
2018-09-24
2018-10-15
2018-10-22
2018-08-17
2018-09-07
2018-07-23
2018-04-18
2018-05-28
2018-05-03
2018-06-07
2018-08-29
2018-05-25
2018-08-02
2018-08-10
2018-07-19
2018-11-02
2018-05-04
2018-07-27
2018-05-07
2018-07-19
2018-10-16
2018-06-27
2018-10-12
2018-06-05
2018-07-13
2018-07-03
2018-07-10
2018-06-19
2018-05-17
2018-08-03
2018-05-23
2018-04-13
2018-06-26
2018-06-19
2018-06-07
2018-07-27
2018-10-24
2018-12-07
2018-09-13
2018-04-16
2018-06-01
2018-09-04
2018-09-21
2018-05-10
2018-06-25
2018-04-23
2018-06-08
2018-08-15
2018-08-30
2018-05-22
2018-09-05
2018-05-03
2018-07-30
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.